## Slide 1: Technical Brief: Part 3 Work Package Plan (WPP)
Issue 2 - A guide to completion
January 2017

## Slide 2: Work Package Plan – Issue 2
The new Network Rail template has been updated to reflect changes in CDM 2015 and recent changes to the Construction Phase Plan template
Must be used for all construction work - the level of detail required must relate to the complexity of the work

## Slide 3: Work Package Plan – What is it?
A document that details:
  the methodology of how the work will be undertaken
  arrangements for managing health and safety risks
  emergency arrangements

## Slide 4: Work Package Plan – Rules for use
Text has been specifically coloured to aid the construction of the document – green text provides guidance throughout
Never re-badge a previous WPP – always use a new template
This is a LIVE document that needs to be maintained/updated for as long as the work package is required

## Slide 5: Work Package Plan Template
Front page
  The WPP must:
    Detail the start and finish date
    Reference back to the CPP
    be approved by the Contractor’s Engineering Manager (or as agreed and authorised in the CDM Plan and documented in the CPP)
    if applicable, be accepted on behalf of Network Rail / Client (normally the Network Rail Project Manager)
      (delete the relevant section if acceptance by Network Rail is not required)
    Approved and accepted each time that significant changes are made
  Wet (not electronic) signatures must be used

## Slide 6: Section 1
Introduction

## Slide 7: Work Package Plan Template
Section 1.1 – Brief outline of work methodology
  This section should provide an outline of the work methodology
  This should not be a complex description, but provide sufficient detail to assess the risk control measures, for example:
    Working arrangements with organisations other than Network Rail (e.g. Station Operators, trackside neighbours)
    Indicate how restrictions might affect the execution of the work and how the work will be planned to take account of these (e.g. possession and isolation requirements, neighbouring buildings, utility services)
  List the tasks that will be undertaken during the work package

## Slide 8: Work Package Plan Template
Section 1.2 – (Principal) Contractor’s delivery organisation
  Delete “Principal” if only one contractor
    1.2.1 – details can be taken from the CPP
      Note – only suggested titles; the equivalent titles (and details) should be added
      Note – specific roles relating to Any line Open (ALO) activities or temporary works should be included in this section
    1.2.2 – details can be taken from the CPP
      Details the companies, specialist contractors and/or individuals, appointed by the PC, involved during the construction phase

## Slide 9: Work Package Plan Template
Section 1.3 – Resources
  Delete “Principal” if only one contractor
    Detail documents that provide detail of the work being undertaken.
    Document applicable “Approved for Construction (AFC)” design documents, including title and document reference.
    Document the number of people and their competences to complete each task safely
      This should also consider operators of plant, machinery, engineering trains, etc.
    Document the quantity of plant, equipment and tools to complete each task
    Document the quantity of materials to complete each task

## Slide 10: Section 2
Working Together

## Slide 11: Work Package Plan Template
Section 2.1 – At site communication
  Detail the means of communication for undertaking each task safely, including:
    Systems to be made available and back up systems where required
    the conditions where communication failures might require work to be stopped or restricted;
    means of communication at site within work groups and outside parties; and,
    alternative means of communication in areas of poor coverage for mobile phones.

## Slide 12: Work Package Plan Template
Section 2.2 – Contact details
  Detail the main contacts for the work package.
Section 2.3 – Other parties (interfaces)
  Identify the interfacing organisations (i.e. other Network Rail teams, Train or Freight Operating Companies or external parties)
  Detail the interface point and the point of contact
  Document the interface arrangements i.e.:
    Who is accountable / responsible for communicating at each stage
    How information will be provided on the work
    How work will be coordinated (i.e. de-confliction meetings, possession / white-board meetings)
    How you will keep them updated of any changes
    Who will make the key decisions about how the work will be done

## Slide 13: Section 3
Hazard Management

## Slide 14: Work Package Plan Template
Section 3.1 – Work involving particular risks
  Refer back to Section 4 of the CPP.
  Were particular risks for this work package identified?
    If no, then delete the second section and table
    If yes, then document which risks are applicable; then,
  Detail when and where the risk will be present
  Detail any permits required
  Then detail how each of the risk will be controlled
  NOTE – if any of these particular risks are considered significant (post mitigation controls) then the Work Package Plan will require acceptance by Network Rail

## Slide 15: Work Package Plan Template
Section 3.2 – Significant railway and construction risks
  Refer back to Section 4 of the CPP.
  These hazards should be:
    site and activity specific
    supported by an associated risk assessment
  Detail when and where the risk will be present
  Detail any permits required
  Then detail how each of the risk will be controlled

## Slide 16: Work Package Plan Template
Section 3.2 – Significant railway and construction risks
  NOTE – The Work Package Plan will require acceptance by Network Rail if:
    Hazards are present that give rise to risks that are assessed to have a significant impact (post mitigation) on the safe operation of the railway and/ or the health and safety of workers.
    The mitigation measures put in place to control risk are unusual, complex, or rely on a high level of engagement or competence within the workforce or other stakeholders.
    There is the likelihood of a significant level of change to the assessed risks due to emerging conditions on site or the immature level of detail presented in the design documentation.

## Slide 17: Section 4
Environmental and Waste Management Arrangements

## Slide 18: Work Package Plan Template
Section 4.1 – Environmental management arrangements
  Refer to the environment management plan and detail the arrangements for protecting the environment.
    The contact details for the (Principal) Contractor’s environment advisor should be added to the contacts section of the WPP
  If there are no specific environment management arrangements, state that not relevant.
Section 4.2 – Waste management arrangements
  Refer to the site waste management plan and detail the arrangements for managing waste
  If there are no specific waste management arrangements, state that not relevant.

## Slide 19: Section 5
Emergency Arrangements

## Slide 20: Work Package Plan Template
Section 5.1 – Site emergency arrangements
  Details should be provided based on the results of a project specific assessment of the likely emergencies and arrangements detailed in the CPP
  Additional sections must be added for other emergency arrangements not detailed i.e. working over water; working in confined spaces
  The information detailed should provide greater, but more specific, detail than that documented in the CPP
  Note – nothing needs to be added in Section 5.1. The detail needs to be added in Sections 5.1.1 to 5.1.8.

## Slide 21: Work Package Plan Template
Section 5.1.1 – First aid arrangements
  This should be based on the type and level of injuries that could arise on the site
  Should consider non-accident events (i.e. heart attacks) and the ability and ease for emergency services to attend
    Confined spaces; remote locations
  Must not just be directions to the local hospital
  Detail must include:
    the number and qualifications of first aiders
    the amount and location of equipment required
    Specialist first aid equipment i.e. rescue stretchers, burns kits
  Can be provided as an appendix

## Slide 22: Work Package Plan Template
Section 5.1.2 – Evacuation arrangements
  This should be based on the type and level of work activities that are taking place
  Should consider:
    evacuation of the entire site or an individual casualty
    potential changes to the site layout
    The maximum number of people on site at any one time (including any lone workers, such as security guards)
    means for accounting for all persons present on site
  Must not just be directions to the local hospital
  Should consider evacuation for security reasons
  Can be provided as an appendix

## Slide 23: Work Package Plan Template
Section 5.1.3 – Fire safety
  This should be based on the actual risk of fire present during the construction phase
  Should consider:
    measures to prevent fires starting (e.g. control of hot works, smoking or re-fuelling activities
    Methods for raising the alarm
    Fire-fighting arrangements
    Details for temporary fire alarm panels or connections to permanent fire alarm systems
    Locating existing fire alarm equipment (i.e. smoke or heat detectors) that might be affected during construction
  Can be provided as an appendix

## Slide 24: Work Package Plan Template
Section 5.1.4 – Security
  Should consider:
    Arrangements for preventing unauthorised access to:
      the construction site
      the operational railway (and associated infrastructure)
    Security arrangements, such as security guards, cameras
    Potential terrorism threats
  For activities and sites that are likely to attract unwelcome attention then contact the British Transport Police and/or Railway Route Crime Prevention Specialist.

## Slide 25: Work Package Plan Template
Section 5.1.5 – Summoning emergency services
  Detail:
    How emergency services will be summoned
    Who will call the emergency services
    Who will meet the emergency services, and where
    How the emergency services will access the site
    Who will escort the emergency services
  Consider prior contact with the emergency services and possible simulated emergency exercises
  Consider other emergency services i.e. bomb disposal; mountain rescue; coastguard and lifeboat; utilities
  Can be provided as an appendix

## Slide 26: Work Package Plan Template
Section 5.1.6 – Railway emergency
  This section should consider the specific arrangements for:
    Stopping trains in an emergency
    Isolating the hazard of electricity
    Contact details for each Signaller, Electrical Control Room (where applicable) and Route Control
  Note - checks should be made in advance to confirm the correct contact details (including any placed on information boards at access points)

## Slide 27: Work Package Plan Template
Section 5.1.7 – Asbestos
  Detail the arrangements for responding to the unexpected discovery of asbestos containing materials
    Even if asbestos has not been identified in any surveys
  Include the arrangements for :
    Informing workers on stopping work if suspected
    Isolating and securing the affected area

## Slide 28: Work Package Plan Template
Section 5.1.8 – Utilities
  Detail the arrangements for responding to the unexpected discovery of utilities - even if utilities has not been identified in any surveys
  Include:
    Emergency contact details for all utilities operating in the location of construction
    Arrangements for isolating and securing the affected area

## Slide 29: Work Package Plan Template
Other emergency arrangements
  Additional sections must be added to detail the arrangements for any other emergencies that could potentially arise during construction, for instance:
    working over water;
    working in confined spaces;
    working in excavations
    working at height
    unexploded ordinance
    flooding
    environmental events

## Slide 30: Section 6
Work Package Arrangements

## Slide 31: Work Package Plan Template
Section 6.1 – Site Layout
  Provide details of the site layout
  This can include:
    Photographs;
    Diagrams / maps;
    Plans
  This should not just detail the location of the site welfare facilities, but all work areas

## Slide 32: Work Package Plan Template
Section 6.2 – Access and Egress
  Provide details of the arrangements for access and egress
  Include all routes to each site of work for:
    People, tools, plant (including rail plant), equipment and materials
  Include diagrams / photographs where possible

## Slide 33: Work Package Plan Template
Section 6.3 – Welfare
  Provide details on site specific arrangements, for instance:
    The maximum number of people on site at any one time during the construction phase
    The number of toilets, wash hand basins, eating facilities, etc
    PPE and personal storage arrangements
  Network Rail standard NR/L3/INI/CP0036 provides a form for quantifying welfare arrangements – this should be used as an appendix

## Slide 34: Work Package Plan Template
Section 6.4 – Rail Traffic Management
  If no rail movements (including those by others) then state “no rail traffic during this work package”.
  Provide details on the arrangements for managing rail traffic, including:
    How rail vehicles movements will be managed;
    How interfaces and means of communication will be managed with other contractors and Network Rail teams within possessions/worksites;
    Details of planned rail movements including engineering trains, on-track machines/plant
    All ALO operations (with the ALO Plan attached as an appendix)
      If ALO is covered by a specific Work Package Plan then this should be detailed.

## Slide 35: Work Package Plan Template
Section 6.5 – Road Traffic Management
  If no road traffic arrangements then state “no road traffic arrangements during this work package”.
  Provide details on the arrangements for managing road traffic, including:
    How road vehicles, including parking, will be managed;
    How pedestrians and vehicles will be segregated
    Arrangements when affecting the normal operation of all types of levels crossings (including foot, occupation and accommodation crossings)
    All ALO operations, including deliveries (with the ALO Plan attached as an appendix)
      If ALO is covered by a specific Work Package Plan then this should be detailed.

## Slide 36: Section 7
Hand over and hand back Arrangements

## Slide 37: Work Package Plan Template
Section 7.1 – Hand over and hand back arrangements
  This section should detail the arrangements for:
    Handing the site over to another contractor (or between contractors working under the same Principal Contractor)
    Hand back to the asset owner at the end of the work