## CPP
Construction Phase Plan Checklist
Introduction: This checklist is designed to assist in the preparation and evaluation of the Construction Phase Plan as defined in NR/L2/OHS/0044. |  |  |  |  | Yes
No
Project Details |  |  |  |  | Not Applicable
Project title and reference |  |  |  |  | Clarification Required
Reference, version number and date
Front Page
Has the Principal Contractor been identified? |  |  |  | Clarification Required
Has the plan been prepared by the Principal Contractor? |  |  |  | Clarification Required
Has the plan been signed (wet signature) by the Contractor’s Engineering Manager (or by other person detailed in the CDM Plan)? |  |  |  | Clarification Required
Has this Construction Phase Plan been signed by the appropriate Network Rail Project Manager? |  |  |  | Clarification Required
Is there a controlled copy number? |  |  |  | Clarification Required
General
Has the distribution list been completed? |  |  |  | Clarification Required
Has the version control table been completed (and is it maintained for each version)? |  |  |  | Clarification Required
Have the important note for completing this document and all green text throughout the document been deleted? |  |  |  | Clarification Required
Has the contents been updated once the plan has been completed? |  |  |  | Clarification Required
1. Introduction
1.1.2 - Has the (Principal) Contractor added their name? |  |  |  | Clarification Required
1.1.3 - Has the CDM Plan document reference number been added? |  |  |  | Clarification Required
2. Planning for the Construction
2.1 Project specific H&S Goals
Have H&S goals been documented? |  |  |  | Clarification Required
Do they also reflect those detailed as part of pre-construction information? |  |  |  | Clarification Required
2.2 Project description and programme details
Has the location of the construction phase been detailed and is it adequate to cover all the works? |  |  |  | Clarification Required
Has a brief description of the works been included, and is it adequate? |  |  |  | Clarification Required
Has the planned start and completion dates been added, and are they correct? |  |  |  | Clarification Required
Have the key construction stages for the project been added, and do they cover all the planned works? (Note this is a live document, so the planned start and end dates might not be available) |  |  |  | Clarification Required
2.3 Services and isolation points
Have the detail of services that need to be disconnected or connected been documented? (Note this is a live document, so all details might not be available, such as the planned date) |  |  |  | Clarification Required
2.4 Access Restrictions
Have access restrictions been defined (or if none, does it state none)? |  |  |  | Clarification Required
2.5 Asbestos
Have the detail of any asbestos been identified and information provided. If asbestos has not been identified has the appropriate section been added to state that none have been identified? |  |  |  | Clarification Required
2.6 Any line open operations
Have the details of any line open operations been identified. If ALO will not take place has the appropriate section been added to state that none are proposed? |  |  |  | Clarification Required
If ALO operations are planned have the details of all ALO activities (including deliveries) been identified? |  |  |  | Clarification Required
If ALO operations are planned have the start and end dates of all ALO activities (including deliveries) been identified? (Note this is a live document, so all details might not be available, such as the planned date) |  |  |  | Clarification Required
If ALO operations are planned is there a link to the relevant Work Package Plan? |  |  |  | Clarification Required
If ALO operations are planned have all individuals accountable for the safe planning and delivery of ALO operations been identified? |  |  |  | Clarification Required
2.7 Temporary Works
Have the details of any temporary works been identified. If temporary works will not take place has the appropriate section been added to state that none are proposed? |  |  |  | Clarification Required
If temporary works are planned have the details of all proposed temporary works been identified? |  |  |  | Clarification Required
If temporary works are planned is there a link to the relevant Work Package Plan? |  |  |  | Clarification Required
If temporary works are planned have all individuals accountable for the safe design, planning and implementation of temporary works been identified? |  |  |  | Clarification Required
2.8 Construction phase plan review
Have details been documented on how the Construction Phase Plan will be routinely reviewed, revised and refined as the project develops? |  |  |  | Clarification Required
Does it detail when the Construction Phase Plan shall be reviewed |  |  |  | Clarification Required
Does it detail who is accountable and responsible for undertaking the review and making any revisions? |  |  |  | Clarification Required
Where significant changes have been made has the Construction Phase Plan being reviewed and accepted by the Network Rail Project Manager? |  |  |  | Clarification Required
3 Working together
3.1 Changes to key personnel
Have the arrangements for informing Network Rail and other parties of changes to the key personnel in the project? |  |  |  | Clarification Required
Are these sufficient? |  |  |  | Clarification Required
3.2 CDM appointments
Has it been defined whether the project is notifiable or non-notifiable? |  |  |  | Clarification Required
Have the CDM appointments been completed, and are they correct? |  |  |  | Clarification Required
Has the name and full address of specific duty holders been completed? |  |  |  | Clarification Required
3.3 Network Rail project organisation
Has the Network Rail project organisation been defined, and are they correct? |  |  |  | Clarification Required
Has an Engineer for all required disciplines been defined? |  |  |  | Clarification Required
3.4 (Principal) Contractor's delivery organisation
Has the (Principal) Contractor's organisation been defined, and are they correct? |  |  |  | Clarification Required
Has an Engineer for all required disciplines been defined? |  |  |  | Clarification Required
Has the Contractor’s Engineering Manager been defined? |  |  |  | Clarification Required
Have all Contractor’s Responsible Engineers been defined i.e. one for each discipline that will be affected throughout the Construction Phase? |  |  |  | Clarification Required
Have persons who are nominated to act for the Contractor’s Responsible Engineer as authorised signatories been defined? |  |  |  | Clarification Required
Does it state what they are authorised signatories for? |  |  |  | Clarification Required
Have all relevant companies, specialist contractors and / or individuals involved during the Construction Phase been identified? |  |  |  | Clarification Required
Have their work activity / specialism and point of contact details been provided? |  |  |  | Clarification Required
3.5 Communication during the Construction Phase
Have all the correct stakeholders been identified? |  |  |  | Clarification Required
Has the communication strategy for each stakeholder been detailed (this should not just be a list of names or meetings)? |  |  |  | Clarification Required
Does the information include: - who is accountable and responsible for communicating at each stage; - how the contractor will should provide information on the job; - how the contractor will coordinate the work; - how the contractor shall keep them updated of any changes e.g. to site rules; to H&S information; changes to the plan or material; delays; - who will be making the key decisions about how the work will be done. |  |  |  | Clarification Required
Does the section relating to Site Workers (including agency workers) define the processes for consulting and coordinating the views of those working on the site, or their representatives, including regular site meetings as well as specific meetings to discuss H&S matters. |  |  |  | Clarification Required
3.6 Exchange of design information
Does the document describe how design information will be exchanged between relevant parties? |  |  |  | Clarification Required
Has it identified whether the Client is specifying materials or inputting into design which is outside of Network Rail standards and that they are listed as a Designer in Section 3.2. |  |  |  | Clarification Required
Has reference been made to engineering processes (Interdisciplinary Reviews and Design Reviews) and appointments (Designated Project Engineer, Project Engineer, Contractors Engineering Manager, and Contractors Responsible Engineer) undertaken in accordance with NR/L2/INI/02009 – Engineering Management of Projects? |  |  |  | Clarification Required
3.5 Changes to design
Does the document describe the process that shall be implemented for any changes to the design once the Construction Phase has started, and how design shall be formally accepted by those accountable and responsible of design. |  |  |  | Clarification Required
Does include the arrangements for the structured coordination between all the parties that ensures all changes to permanent or temporary works design information, including the associated hazards and significant risks, is shared and reviewed? |  |  |  | Clarification Required
This shall capture the involvement of engineering appointees and the review processes described in NR/L2/INI/02009? |  |  |  | Clarification Required
4 Hazard Management
4.1 Work involving particular risks
Have the details of any work involving particular risks detailed in Regulation 12(2) (Schedule 3) of the CDM Regulations been identified (and the correct section delated)? If there are no works involving these particular risks has the appropriate section been deleted? |  |  |  | Clarification Required
If work will take place involving these particular risks has the contractor deleted those that are not applicable? |  |  |  | Clarification Required
If work will take place involving these particular risks has the contractor detailed how the risks will be controlled? Note - this should not just refer to a Work Package Plan(s). |  |  |  | Clarification Required
Has each particular risk been cross-referenced to a Work Package Plan? |  |  |  | Clarification Required
If work will take place involving these particular risks has the Work Package Plan(s) detailed in Section 5.3 show that these require Network Rail acceptance? |  |  |  | Clarification Required
4.2 Significant construction H&S risks
Does the document detail who is involved in the review of the Hazard Log (or Hazard Record under CSM) during the construction phase? |  |  |  | Clarification Required
Does the document detail how the significant risks will be communicated to all relevant parties (i.e. site inductions, safety notices, work planning packages and task briefings)? |  |  |  | Clarification Required
Does the document detail what processes the significant risks will be communicated within to operators / maintainers (i.e. Asset Management Plan, Entry into Service Strategy)? |  |  |  | Clarification Required
Has the contractor identified SIGNIFICANT safety and health risks (These hazards are unusual or complex risks that are more likely to be missed or misunderstood by contractors or others, rather than risks that are well known and understood)? |  |  |  | Clarification Required
Are the SIGNIFICANT safety and health risks project and site specific (i.e. not generic hazards, such as slips, trips and falls)? |  |  |  | Clarification Required
Has it been identified when and where the significant risk will be present? |  |  |  | Clarification Required
Has each significant safety and health risk been cross-referenced to a Work Package Plan? |  |  |  | Clarification Required
Has it been documented how each risk will be controlled? Note - this should not just refer to a Work Package Plan(s). |  |  |  | Clarification Required
5 Organise
5.1 Brief outline of work methodology
Has a brief outline of the work methodology been provided (this is not to be a list of the work tasks or a schedule of the Work Package Plans, but a brief description of the methodology for the project)? |  |  |  | Clarification Required
Does the information provide suitable and sufficient information to determine whether the risks in Section 4 have been correctly identified and controlled? |  |  |  | Clarification Required
5.2 Management of Work Package Plans
Does the contractor detail the arrangements for managing Work Package Plans? |  |  |  | Clarification Required
Does it outline how Work Package Plans are managed through to acceptance, detailing who shall review the documents? |  |  |  | Clarification Required
Does it outline the process by which Work Package Plans and additional Work Package Plans arising after the commencement of work shall be reviewed and added to the project? |  |  |  | Clarification Required
Does it highlight the parties involved in making decisions on risks and the methodology and criteria that was used? |  |  |  | Clarification Required
Has the determination of the risk level of each Work Package Plan been done in consultation between Network Rail and the (Principal) Contractor? |  |  |  | Clarification Required
Has the decision been based on objective criteria (i.e. on the risk to trains, workforce, public and business)? |  |  |  | Clarification Required
Is the criteria specific for the project and reasonable. |  |  |  | Clarification Required
5.3 Schedule for the production of Work Package Plans
Is there a list of the work packages that completely defines the breakdown of the work? |  |  |  | Clarification Required
Is it clear which work packages require formal acceptance by Network Rail? |  |  |  | Clarification Required
Does the plan identify an appropriate target date for acceptance by Network Rail that will still allow sufficient time to arrange the resources required for each of the work package plans? |  |  |  | Clarification Required
Is the timescale for Network Rail acceptance as agreed in the CDM Plan? |  |  |  | Clarification Required
Is there a clear target date to complete each of the work packages? |  |  |  | Clarification Required
For those work packages that require submission to Network Rail have the submission dates been identified? |  |  |  | Clarification Required
5.4 Site emergency arrangements
Has the contractor identified all the expected emergencies and added additional sections as necessary (i.e. working over water, working in a confined space)? |  |  |  | Clarification Required
Do the emergency arrangements cover the risks identified in Section 4? |  |  |  | Clarification Required
Does the document detail the results of the project specific first aid risk assessment? |  |  |  | Clarification Required
Do the first aid arrangements cover the likely emergencies that might occur? |  |  |  | Clarification Required
Do the arrangements identify the type and level of injury that could arise on site? |  |  |  | Clarification Required
Do the arrangements detail the number and qualifications of first aiders and the equipment that shall be on site? |  |  |  | Clarification Required
Is an overview of the evacuation procedure included? This should not just be directions to the local A&E. |  |  |  | Clarification Required
Is a detailed evacuation procedure provided as an appendix? |  |  |  | Clarification Required
Does the evacuation procedure take account of both the need to evacuate the site as a whole and the evacuation of an individual casualty? |  |  |  | Clarification Required
Does the procedure take account of the need to remove an insensible person from the railway environment to a place where they can be placed into professional medical care? |  |  |  | Clarification Required
Do the arrangements include a means of accounting for all persons present on the site? |  |  |  | Clarification Required
Is an overview of the fire safety plan included? |  |  |  | Clarification Required
Is a detailed fire safety plan provided as an appendix? |  |  |  | Clarification Required
Is the fire safety plan based on the actual risk of fire present on the site? |  |  |  | Clarification Required
Does the plan include measures to prevent a fire starting (e.g. control of hot works, smoking and refuelling activities), the method of raising the alarm with all people on site and any firefighting arrangements provided? |  |  |  | Clarification Required
Does the plan contain details about the need for any temporary fire alarm panels or connections to current fire alarm panels; also the need to locate fire alarm equipment (i.e. smoke or heat detectors) that might be affected during the construction phase? |  |  |  | Clarification Required
Is an overview of the site specific security arrangements included? |  |  |  | Clarification Required
Does it provide information that prevents unauthorised access to the worksite and also prevents the construction work from effecting members of the public? |  |  |  | Clarification Required
Does the document detail how emergency services will be summoned during the construction phase? |  |  |  | Clarification Required
Does this include specific information of: - who will summon the emergency services; - who will meet the emergency services and where; and - how the emergency services can access the site. |  |  |  | Clarification Required
Does the document detail the procedures for managing railway emergencies (not just a list of the local signalbox and electrical control room)? |  |  |  | Clarification Required
Do the site specific arrangements detail how to: a. Stop trains in an emergency; and b. Isolate the hazard of electricity (for example and including the following supplies: 25//33/66kV AC, 750V DC, 415V 3 phase AC and 240V AC) (This is the arrangements not stating how to make an emergency call) |  |  |  | Clarification Required
Has the contractor detailed the site specific arrangements for responding to the discovery of asbestos containing material (ACM) on site, EVEN IF ASBESTOS HAS NOT BEEN LOCATED IN SURVEYS? |  |  |  | Clarification Required
Does this include the arrangements for people on site to stop work and obtain competent advice for the identification and disposal of ACMs? |  |  |  | Clarification Required
Has the contractor detailed the site specific arrangements for responding to the discovery of utilities not anticipated during the planning stages? |  |  |  | Clarification Required
Do the arrangements include the emergency contact details for all utilities operating in the location where the construction work will take place? |  |  |  | Clarification Required
5.5 Safety and environmental event reporting and recording
Has the contractor detailed the arrangements (including timescales) for the reporting and recording of safety and environmental related events that occur during construction works? |  |  |  | Clarification Required
Does this include accidents, incidents (including operational close calls and environmental incidents) and close calls? |  |  |  | Clarification Required
Does this include contact details for reporting within Network Rail (i.e. the relevant Route Control and/or Project Control Room)? |  |  |  | Clarification Required
Does this include the arrangements for the investigation report to be sent to the Network Rail nominated person are to be included together with the reporting timescales, and who is responsible? |  |  |  | Clarification Required
5.6 Site specific rules
Has the contractor detailed the specific rules for the site(s) that would not normally be expected? |  |  |  | Clarification Required
5.7 Induction
Has the contractor detailed the site specific arrangements for inducting people on the site(s)? |  |  |  | Clarification Required
Does it include details of how this Construction Phase Plan and the Work Package Plans will be briefed to all personnel? |  |  |  | Clarification Required
Has the relevant section relating to general briefing and the Industry Common Induction been deleted? |  |  |  | Clarification Required
5.8 Welfare
Has the contractor detailed the site specific arrangements for welfare on this site? |  |  |  | Clarification Required
Does this identify the maximum number of people that will be on site at any one time during the construction phase? |  |  |  | Clarification Required
Does it demonstrate that the welfare arrangements that will be in place (i.e. number of toilets, wash hand basins, eating facilities, drying facilities, PPE and personal storage arrangements) are suitable and meet the requirements of both the Workplace (Health, Safety and Welfare) Regulations 1992, NR/L3/INI/CP0036 and Network Rail standards and procedures? |  |  |  | Clarification Required
Is a copy of the welfare assessment form (detailed in NR/L3/INI/CP0036) provided as an appendix? |  |  |  | Clarification Required
5.9 Monitoring arrangements
5.9.1 Has the contractor detailed the Principal Contractor / Contractor monitoring arrangements that will apply during the construction phase? |  |  |  | Clarification Required
5.9.1 Does this include (but not limited to): • Inspections by site management of the compound, work area etc.; • Inspections by people not immediately involved in the project e.g. company HSEA specialists; • Safety tours / safety conversations by senior company managers; • Specific inspections in relation to works being undertaken e.g. lifting operations, scaffolding, encapsulations etc.; • Medical interventions required for legal compliance e.g. hearing testing, blood tests for lead, HAVs, etc.; • A strategy for drug and alcohol monitoring/testing during the project; and • Periodic reviews and audits of the site and its management by persons external to the site team |  |  |  | Clarification Required
5.9.2 Has the contractor detailed programme of monitoring activities that has been set out by Network Rail to provide assurance to the Client that the arrangements in place for delivering the project are also delivering the required levels of health and safety for those doing the construction and those that will be involved with the asset in future? |  |  |  | Clarification Required
5.9.2 Does this include (but not limited to): • Planed General / Task Specific Inspections of the site, work area etc; • Safety tours / safety conversations by senior managers; • Specific inspections in relation to works being undertaken e.g. lifting operations, scaffolding, encapsulations etc.; • Periodic reviews and audits of the site and its management by persons external to the site team; and • Inspections following safety events |  |  |  | Clarification Required
5.10 Management reporting arrangements
Has the contractor detailed the reporting arrangements for the project? |  |  |  | Clarification Required
Has the Contractor and the Network Rail nominated person agreed the reporting arrangements for the project? |  |  |  | Clarification Required
Does this include (but not limited to): • Project start up meeting – to agree arrangements for the project, roles and responsibilities, lines of communication and reporting; • Periodic project progress meetings; • Readiness reviews – for example T-26, T-12, T-8 and T-4 meetings, or those associated with the Delivering of Work Within Possessions (DWWP); • Design review meetings; • Client update meetings; and • Method of calling other meetings, as required for dealing with specific issues relating to the project. |  |  |  | Clarification Required
6 Health and safety file
6.1 H&S File
Has the contractor documented the arrangements for providing H&S information both during and at the end of the construction phase in accordance with NR/L2/INF/02202? |  |  |  | Clarification Required
Does this include (but not limited to): • The information that will be needed relating to the asset(s) being worked on (this should be requested via the QF705) or in writing to the Client Representative; • How the H&S File will be compiled (as agreed in QF703); and, • On large projects or projects that involve a number of separate sites it may be possible to update the health and safety information as each distinct part of the project is completed. The process and format of how this will be undertaken should be detailed and agreed with the Client Representative and NRG using the QF703. |  |  |  | Clarification Required
Details of Check
Name of person completing checklist
Position
Signature
Date
Resulting actions from Construction Phase Plan check
| Issue / Concern |  | Name
1
2
3
4
5
6
7
8
9
10
Construction Phase Plan Summary
| Answer Given | Count | Percentage of Answer Given (%)
| Yes | 0 | 0
| No | 0 | 0
| Clarification Required | 133 | 100
| Not Applicable | 0 | 0
| Total Checked | 133 | 100