## WPP
Yes
Work Package Plan Check List |  |  |  |  | No
Not Applicable
Introduction: This checklist is designed to assist in the preparation and evaluation of a Work Package Plan as defined in NR/L2/OHS/0044. |  |  |  |  | Clarification Required
Work Package Plan Details
Work Package title and reference
Project title and reference
Format
Does the Work Package Plan include the relevant items as stated in the WPP template? |  |  |  | Clarification Required
Is the information presented in the same order as the template? |  |  |  | Clarification Required
Front Page
Has the Principal Contractor been identified? |  |  |  | Clarification Required
If this WPP is classed as "significant" has it been accepted by Network Rail / Client? |  |  |  | Clarification Required
Is the title and reference correct? |  |  |  | Clarification Required
Is the location description sufficient? |  |  |  | Clarification Required
Is the start and finish date for the work package suitable? |  |  |  | Clarification Required
Is the Work Package Plan number listed? |  |  |  | Clarification Required
Is a controlled copy number listed? |  |  |  | Clarification Required
Is the Work Package Plan linked back to a Construction Phase Plan? |  |  |  | Clarification Required
Has the plan been approved (wet signature) by the Contractor’s Engineering Manager (or by other person detailed in the CDM Plan and Section 3.4 of the CPP)? |  |  |  | Clarification Required
General
Has the distribution list been completed? |  |  |  | Clarification Required
Has the version control table been completed (and is it maintained for each version)? |  |  |  | Clarification Required
Have the important note for completing this document and all green text throughout the document been deleted? |  |  |  | Clarification Required
Has the contents been updated once the plan has been completed? |  |  |  | Clarification Required
1. Introduction
1.1 Brief outline of work methodology
Has an outline of the work methodology been provided? |  |  |  | Clarification Required
Does the outline provide sufficient detail to assess the risk control measures for the work being planned? |  |  |  | Clarification Required
Does it include working arrangements with organisations other than Network Rail (e.g. Station Operators, trackside neighbours)? |  |  |  | Clarification Required
Does it indicate how restrictions might affect the execution of the work and how the work will be planned to take account of these (e.g. possession and isolation requirements, neighbouring buildings, utility services)? |  |  |  | Clarification Required
Have the task that support the Work Package Plan been listed? |  |  |  | Clarification Required
Does each task have a reference number? |  |  |  | Clarification Required
Does it detail who each Task Briefing Sheet is to be prepared by? |  |  |  | Clarification Required
Has the start date been detailed for each task? |  |  |  | Clarification Required
1.2 (Principal) Contractor’s delivery organisation
Has "Principal" (twice) been deleted if a Principal Contractor has not been appointed? |  |  |  | Clarification Required
Has the (Principal) Contractor's organisation been defined, and are they correct? |  |  |  | Clarification Required
Has an Engineer for all required disciplines been defined? |  |  |  | Clarification Required
Has the Contractor’s Engineering Manager been defined? |  |  |  | Clarification Required
Have all Contractor’s Responsible Engineers been defined i.e. one for each discipline that will be affected throughout the work package? |  |  |  | Clarification Required
If Any Line Open activities are being undertaken during this package of works are the main duty holders (i.e. ALO Responsible Manager, ALO Planner, ALO Site Coordinators) listed? |  |  |  | Clarification Required
If Temporary Works are being undertaken during this package of works are the main duty holders (i.e. Temporary Works Designer, Temporary Works Coordinator, Temporary Works Supervisor) listed? |  |  |  | Clarification Required
Have all relevant companies, specialist contractors and / or individuals involved during the Construction Phase been identified? |  |  |  | Clarification Required
Have their work activity / specialism and point of contact details been provided? |  |  |  | Clarification Required
1.3 Resources
Have documents regarding the work being undertaken been detailed (for example: Approved for Construction (AFC) Design documents; drawings specifications, Designer's Risk Assessments)? Are these attached in the appendices? |  |  |  | Clarification Required
Does it include the document title and reference number? |  |  |  | Clarification Required
People - Does this section detail the minimum number of people required to undertake each task safely? |  |  |  | Clarification Required
People - Has this been linked into each task (briefing sheet)? |  |  |  | Clarification Required
People - Does the number of people and their competencies look suitable for the tasks being undertaken? |  |  |  | Clarification Required
Plant, Equipment and Tools - Has the plant, equipment and tools for each task been identified? |  |  |  | Clarification Required
Plant, Equipment and Tools - Does the quantity of plant, equipment and tools look suitable for the tasks being undertaken? |  |  |  | Clarification Required
Materials - Has the quantity of materials (if relevant) for each task been identified? |  |  |  | Clarification Required
Materials - Does the quantity of materials look suitable for the tasks being undertaken? |  |  |  | Clarification Required
2. Working Together
2.1 At site communication
Has the means of communication (including systems to be made available and any back up systems to be available) been documented? |  |  |  | Clarification Required
Does the at site communication arrangements look suitable for the tasks being undertaken (for example detail conditions where communication systems may fail or means of communication in areas of poor mobile phone coverage)? |  |  |  | Clarification Required
2.2 Contact Details
Are the main contacts for the work package been detailed? |  |  |  | Clarification Required
2.3 Other parties involved with the package of work (Interface details)
Have all the parties / organisations that could interface with this work package been identified (for example, other Network Rail projects, TOCs/FOCs external parties)? |  |  |  | Clarification Required
Has the interface point for each interfacing organisation been identified? |  |  |  | Clarification Required
Has a point of contact (and contact details) for each interfacing organisation been detailed? |  |  |  | Clarification Required
Have the arrangements for managing the interface with each organisation been provided? |  |  |  | Clarification Required
Are the arrangements for managing the interface with each organisation suitable (for example do that show who is accountable and responsible for communicating at each stage; how work will be coordinated; and, how interfacing organisations will be updated of any changes)? |  |  |  | Clarification Required
3. Hazard Management
3.1 Work involving particular risks
Have the details of any work involving particular risks detailed in Regulation 12(2) (Schedule 3) of the CDM Regulations been identified (and the correct section delated)? If there are no works involving these particular risks has the appropriate section been deleted? |  |  |  | Clarification Required
If work will take place involving these particular risks has the contractor documented each one? |  |  |  | Clarification Required
If work will take place involving these particular risks do the risks highlighted correspond with those documented in the CPP? |  |  |  | Clarification Required
If work will take place involving these particular risks has the contractor detailed how the risks will be controlled? Note - this should not just refer to a Task Briefing Sheet(s). |  |  |  | Clarification Required
Has each particular risk been cross-referenced to any permits that might be required? |  |  |  | Clarification Required
If work will take place involving these particular risks has the Work Package Plan(s) detailed in Section 5.3 show that these require Network Rail acceptance? |  |  |  | Clarification Required
3.2 Significant construction H&S risks
Has the contractor identified SIGNIFICANT construction safety and health risks (These hazards are unusual or complex risks that are more likely to be missed or misunderstood by contractors or others, rather than risks that are well known and understood)? |  |  |  | Clarification Required
Are the SIGNIFICANT safety and health risks project and site specific (i.e. not generic hazards, such as slips, trips and falls)? |  |  |  | Clarification Required
Has it been identified when and where the significant risk will be present? |  |  |  | Clarification Required
Has it been documented how each risk will be controlled? Note - this should not just refer to a Task Briefing Sheet(s). |  |  |  | Clarification Required
Has each particular risk been cross-referenced to any permits that might be required? |  |  |  | Clarification Required
3.3 Lifesaving Rules
Has the contractor addressed specific hazards in line with the Network Rail lifesaving rules? |  |  |  | Clarification Required
4. Environmental and Waste Management Arrangements
4.1 Environmental Management Arrangements
Have the arrangements for protecting the environment during the package of work been identified? |  |  |  | Clarification Required
Are the arrangements suitable? |  |  |  | Clarification Required
4.2 Waste Management Arrangements
Have the arrangements for managing waste during the package of work been identified? |  |  |  | Clarification Required
Are the arrangements suitable? |  |  |  | Clarification Required
5. Emergency Arrangements
5.1 Site Emergency Arrangements
Has the contractor identified all the expected emergencies and added additional sections as necessary (i.e. working at height, working over water, working in a confined space)? |  |  |  | Clarification Required
Do the emergency arrangements cover the risks identified in Sections 3 and 4? |  |  |  | Clarification Required
Does the document detail the results of the project specific first aid risk assessment? |  |  |  | Clarification Required
Do the first aid arrangements cover the likely emergencies that might occur? |  |  |  | Clarification Required
Do the arrangements identify the type and level of injury that could arise on site? |  |  |  | Clarification Required
Do the arrangements detail the number and qualifications of first aiders and the equipment that shall be on site? |  |  |  | Clarification Required
Is an overview of the evacuation procedure included? This should not just be directions to the local A&E. |  |  |  | Clarification Required
Is a detailed evacuation procedure provided as an appendix? |  |  |  | Clarification Required
Does the evacuation procedure take account of both the need to evacuate the site as a whole and the evacuation of an individual casualty? |  |  |  | Clarification Required
Does the procedure take account of the need to remove an insensible person from the railway environment to a place where they can be placed into professional medical care? |  |  |  | Clarification Required
Do the arrangements include a means of accounting for all persons present on the site? |  |  |  | Clarification Required
Are the specific fire safety arrangements included? |  |  |  | Clarification Required
Is a detailed fire safety assessment/plan provided as an appendix? |  |  |  | Clarification Required
Is the fire safety plan based on the actual risk of fire present on the site? |  |  |  | Clarification Required
Does the plan include measures to prevent a fire starting (e.g. control of hot works, smoking and refuelling activities), the method of raising the alarm with all people on site and any firefighting arrangements provided? |  |  |  | Clarification Required
Does the plan contain details about the need for any temporary fire alarm panels or connections to current fire alarm panels; also the need to locate fire alarm equipment (i.e. smoke or heat detectors) that might be affected during the construction phase? |  |  |  | Clarification Required
Is an overview of the site specific security arrangements included? |  |  |  | Clarification Required
Does it provide information that prevents unauthorised access to the worksite and also prevents the construction work from effecting members of the public? |  |  |  | Clarification Required
Does the document detail how emergency services will be summoned during the construction phase? |  |  |  | Clarification Required
Does this include specific information of: - who will summon the emergency services; - who will meet the emergency services and where; and - how the emergency services can access the site. |  |  |  | Clarification Required
Does the document detail the procedures for managing railway emergencies (not just a list of the local signalbox and electrical control room)? |  |  |  | Clarification Required
Do the site specific arrangements detail how to: a. Stop trains in an emergency; and b. Isolate the hazard of electricity (for example and including the following supplies: 25//33/66kV AC, 750V DC, 415V 3 phase AC and 240V AC) (This is the arrangements not stating how to make an emergency call) |  |  |  | Clarification Required
Has the contractor detailed the site specific arrangements for responding to the discovery of asbestos containing material (ACM) on site, EVEN IF ASBESTOS HAS NOT BEEN LOCATED IN SURVEYS? |  |  |  | Clarification Required
Does this include the arrangements for people on site to stop work and obtain competent advice for the identification and disposal of ACMs? |  |  |  | Clarification Required
Has the contractor detailed the site specific arrangements for responding to the discovery of utilities not anticipated during the planning stages? |  |  |  | Clarification Required
Do the arrangements include the emergency contact details for all utilities operating in the location where the construction work will take place? |  |  |  | Clarification Required
6. Work Package Arrangements
6.1 Work Package Arrangements
Have details on the site layout been provided? |  |  |  | Clarification Required
Where relevant, does this provide details of where the work will be working, not just the location of site welfare? |  |  |  | Clarification Required
6.2 Access and Egress
Have arrangements for accessing and egressing been detailed? |  |  |  | Clarification Required
Where relevant, does this include all routes to site(s) of work? |  |  |  | Clarification Required
Does this include access arrangements for people, tools, plant (including rail plant), equipment and materials? |  |  |  | Clarification Required
6.3 Welfare
Have the welfare arrangements been detailed? |  |  |  | Clarification Required
Are the arrangements suitable and sufficient for the number of people identified in Section 1.3? |  |  |  | Clarification Required
6.4 Rail Traffic Management
Where applicable, have the arrangements for managing rail traffic been detailed (or detailed that no rail traffic will be part of this work package)? |  |  |  | Clarification Required
Does it provide specific details on how rail movements will be managed? |  |  |  | Clarification Required
Do the arrangements include interfaces and means of communication for planning and delivering safe rail movements between other contractors and Network Rail teams within worksites/possessions? |  |  |  | Clarification Required
Does it provide details on of the planned rail movements including engineering trains, on-track machines and on-track plant (including those by other contractors and Network Rail Teams) that may affect the work activities? |  |  |  | Clarification Required
Have the arrangements for managing Any Line Open Operations relating to rail vehicles been documented (or reference made to a specific Work Package Plan detailing the arrangements for ALO Operations)? |  |  |  | Clarification Required
Has a copy of the ALO Plan been provided as an appendix? |  |  |  | Clarification Required
6.5 Road Traffic Management
Where applicable, have the arrangements for managing road traffic (including parking; vehicle and pedestrian segregation) been detailed (or detailed that no road traffic will be part of this work package)? |  |  |  | Clarification Required
Does it provide specific details on the arrangements for managing road traffic that will affect the normal operation of all types of level crossings? |  |  |  | Clarification Required
Have the arrangements for managing Any Line Open Operations relating to road vehicles been documented (or reference made to a specific Work Package Plan detailing the arrangements for ALO Operations)? |  |  |  | Clarification Required
Has a copy of the ALO Plan been provided as an appendix? |  |  |  | Clarification Required
7. Hand Over and Hand Back Arrangements
7.1 Hand Over and Hand Back Arrangements
Have arrangements for handing the site to another contractor and/or hand back of service to the asset owner at the end of the work be documented? |  |  |  | Clarification Required
Are the arrangements suitable for the work being undertaken? |  |  |  | Clarification Required
Comments
Details of Check
Name of person completing checklist
Position
Signature
Date
Resulting actions from Work Package Plan check
| Issue / Concern |  | Name | Date
1
2
3
4
5
6
7
8
9
10
Work Package Plan Summary
| Answer Given | Count | Percentage of Answer Given (%)
| Yes | 0 | 0
| No | 0 | 0
| Clarification Required | 110 | 100
| Not Applicable | 0 | 0
| Total Checked | 110 | 100
Check lists are also available for Task Briefing Sheets and Construction Phase Plans