## ESA Tool
Environmental & Social Appraisal Tool
Welcome to Network Rail’s Environmental & Social Appraisal (ESA) Tool
The purpose of the ESA Tool is to help identify and manage the environmental and social risks and opportunities associated with your project.
The ESA is aligned with Network Rail’s Standard NR/L2/ENV/015: Environment and Social Minimum Requirements - Design and Construction to build an action plan that will allow projects to be developed in accordance with compliance obligations and industry best practice. The appraisal is the first step in Network Rail’s process to effectively managing risks, identify opportunities to protect and enhance the environment and deliver value to society through railway works.
Please read the User Guide before completing the appraisal – it will help you use the tool quickly and efficiently.
If you have any questions about the use of this tool, please email: |  |  | sustainabledevelopment@networkrail.co.uk
Version | 2.5
Last updated by [Naomi Sandford-deQuincey] on [03/09/2021]

## User Guide
User guide
1. Save a copy of the ESA Tool
The first step in using the ESA Tool is to save it onto a server or to your local hard drive.
2. ESA Tool Key
The second step is to understand the different functionalities available in the ESA Tool:
these buttons are located in the top left hand corner of the tabs; they show or hide the guidance information
| i | double click' on any question marked with an "i" to open the guidance pop up windows
drop down lists provide you with the options to answer each question
free text boxes for you to provide additional information
click a blank square to select the appropriate answer, and it will turn black
3. ESA Tool Tab Overview
Finally, understand what is required of you in each of the following ESA Tool tabs:
TAB 1 - Project Info |  |  | Please enter the project information that relates to this appraisal. Once complete, please proceed to the 'Project Scope' tab.
TAB 2 - Project Scope |  |  | To set the scope for the project, confirm which of the activities are appropriate. Once your scope of work is set, review what has been included/excluded to ensure this accurately reflects your works programme. You should do this before starting your appraisal, as the project information you provide will determine which questions and actions you need to consider going forward. Proceed by clicking the 'Start Appraisal' button.
TAB 3 - Project Activities |  |  | Based on the scope of the assessment set out in the 'Project Info & Scope' tab, you will be asked to provide answers to a series of questions on environmental and social risks. Where appropriate, provide additional information. Please provide an answer to each question and then proceed by clicking the 'Move to Desktop Study' button.
TAB 4 - Desktop Study |  |  | You will be asked to respond to a series of 'Desktop Study' questions based on environmental and social risks. Use the provided links to relevant data sources and guidance to help answer the questions. Where appropriate, provide additional information. Please provide an answer to each question and then proceed by clicking the 'Move to Action Plan' button.
TAB 5 - Actions Report |  |  | Once you have completed your appraisal and clicked the 'Move to Action Plan' button, you will be taken to your works programme specific Action Plan. This will provide a summary of the specific risks and opportunities associated with your project, and actions you will need to take to respond to them. You can 'print to PDF' to generate a standalone report for your records. If you are updating your appraisal at any time, when you select the 'Move to Action Plan' button, it will give you the option to create a 'snapshot' of your appraisal at any point in your project lifecycle. Please contact sustainabledevelopment@networkrail.co.uk if you need further information or advice on the recommended actions.
4. Frequently Asked Questions
These answers are recommendations to guide project teams to use the tool effectively. For further guidance, contact your local sustainable development team.
Q.1. | Who completes, reviews and accepts the ESA?
A.1. The Network Rail Project Manager is responsible for the completion of the ESA. It is recommended that the ESA is completed by the project management team, either the Scheme Project Manager or Project Management Assistant. The ESA should be reviewed and accepted by the Project Manager. Where there are known significant environmental and social risks, such as works within a protected site, then the sustainable development team should be involved in the process. The ESA enables Network Rail to collate pre-construction information on environmental and social risks and opportunities. Consequently, it is not appropriate for the construction Contractors to complete the ESA. The ESA can be carried out by another competent party on behalf of the Project Manager, as long as the review and acceptance is carried out internally.
Q.2. | When does the ESA need to be completed and how often should it be reviewed and updated?
A.2. The ESA should initially be completed at the start of the project. It should then be reviewed and updated at each PACE milestone or when significant changes to the project occur. Additional interim reviews and updates may be required where further information (such as surveys) may change some of the answers or where the design or scope of works are changed. Where any changes are made, refresh and check the action plan and update where necessary.
Q.3. | Who should carry out the actions so that these are managed effectively?
A.3. The Project Manager is responsible for the overall management of the ESA and informing action owners (Question 5). Action owners may include, but are not restricted to, internal project personnel, designers and/or contractors. As the ESA is updated, the actions, action owners and applicable PACE milestone may change. Dependent on the PACE lifecycle, not all actions generated will be required immediately. In the first instance, a review of the actions should be carried out by the project team as part of the review process (Question 1) and the action tracker completed as far as reasonably possible. This includes designating action owners and defining which PACE milestone action is due for completion.
Q.4. | Once complete, how should the ESA be used to support project development and delivery?
A.4. The ESA is designed to help projects recognise potential risks and opportunities associated with the type of works and where they will take place. It is not a standalone tool, the outputs need to be integrated within the whole project development process. Embedding the outputs will help to manage risks to prevent delays, therefore avoiding increased costs and associated reputational damage, as well as helping to realise opportunities to reduce operational and whole life costs and deliver wider environmental and social benefits . The guidance below provides recommendations on how to utilise the ESA tool at each relevant PACE milestone to enable effective sustainable project delivery.
Filter the appropriate PACE stage in the table below for relevant guidance:
| PACE Lifecycle/ Milestone | Relevant documents |  | Use the ESA to develop these documents to:
| PHASE 1 | STRATEGIC DEVELOPMENT & PROJECT SELECTION There may be environmental and social impacts that influence the feasibility of the project, such as timescales for delivery or anticipated costs.
| ES1 | CS2 - Sponsors instruction |  | Enable development of sustainability deliverables that are relevant to the possible impacts associated with the scope of works and the local area.
| ES2 | CS3 - Feasibility Report |  | Include the environmental and/or social risks and opportunities within the feasibility study. There may be potential constraints or interfaces that need to be managed or opportunities that may deliver additional benefits. Specifically it will help inform the Constructability section of the report.
| ES3 | CS6 - Diversity Impact Assessment |  | Determine whether a Diversity Impact Assessment is required for the project.
| ES3 | PM1 - Project Management Plan |  | Develop a sustainability strategy for the project that is relevant to the risks and opportunities associated with the scope of works and local area. The project sustainability strategy should also consider the National and relevant Regional sustainability strategies. Specifically this will inform the environmental and sustainability sections of the plan.
| ES3 | PM2 - Stakeholder & Customer Management Plan |  | Establish the environmental and social stakeholders relevant to the project.
| ES3 | CA1 - Land and Consents Strategy |  | Inform the relevant sections of the strategy (Environmental Impact Assessment and Environmental Consents) on possible environmental and social consents, licences or permits that may be required.
| ES3 | CA2 - Land and Consents Commitments Register |  | Capture appropriate environmental and social consents, licences or permits.
| ES3 | RV2 - Risk Register |  | Capture the potential environmental and social risks as part of all project risks.
| ES3 | CS4 - Option Selection Report |  | Enable project specific environmental and social risks and opportunities to be considered within the option selection process, which will make sure the options appropriately eliminate or manage risks and/or deliver the opportunities. Specifically it will help inform the Constructability and Environmental Impact Assessment sections of the report.
| ES3 | R2 - Route Requirements Document |  | Incorporate the requirements for any environmental and social risks or opportunities that are considered to be higher level requirements.
| ES3 | CP5 - Lifecycle Cost Report |  | Establish cost estimates associated with managing the project specific risks or delivering opportunities and prevent unforeseen costs. Specifically use to complete the Sustainability section.
| PHASE 2 | PROJECT DEVELOPMENT AND DESIGN
| ES4 | Invitation To Tender (ITT) |  | Produce sustainability ITT questions that are relevant to the scope of works, local area and Network Rail's Sustainability Strategy. The action report may be provided as a supporting document. Having visibility of the ESA enables the Contractor to understand the project specific risks and opportunities so they can bid appropriately.
| ES4 | Design Log |  | Capture actions relevant to design within the design log.
| ES4 | Pre-Construction Information Pack (PCIP) |  | Detail the specific risks and opportunities within the environmental section of the PCIP, ensuring references to any pertinent project requirements are made. Include the ESA as an appendix.
| ES4 | Contracts Requirement - Technical (CR-T) |  | Detail specific requirements relevant to the project's significant environmental and social risks and opportunities.
Q.5. | Who should receive copies of the ESA?
A.5. The ESA should be shared with those developing the relevant documents, PACE products and otherwise, as detailed within Question 4 , as well as the relevant actions owners as discussed in response to Question 2. This includes the Principal Designers and Principal Contractors who will use the ESA to inform the design and construction ESMPs. It may also be shared with other parties within the supply chain, such as construction sub-contractors, ecologists, planning personnel, etc. The ESA should be shared with the sustainable development team in your Region where there are known significant environmental or social risks.
Q.6. | How is the RAG level of Risk & Opportunity defined for each theme?
A.6 An indicative Risk & Opportunity RAG rating was applied to each theme based on the below criteria:
| Biodiversity | - Vegetation Management, AND - Protected Species within 1km, OR - Protected sites, OR - Ancient Woodland, OR - INNS, OR - TPO |  |  | - Vegetation Management, OR - Protected Species, OR - Protected Sites, OR - Ancient Woodland, OR - INNS, OR - TPO, OR | Otherwise
| Contaminated land | - Records of Contaminated Land, AND - Watercourse within 10m, OR - Source Protection Zone |  |  | - Records of Contaminated Land, OR - Source Protection Zone | Otherwise
| Emissions to air | - AQMA, AND - Contribution to air pollution during construction, OR - Contribution to air pollution during operation |  |  | - AQMA, OR - Contribution to air pollution during construction, OR - Contribution to air pollution during operation | Otherwise
| Noise, nuisance and disturbance | - Noise Management Area OR Residents within 200m (500m for noisier works), AND - Contribution to increase in noise & vibration during construction, OR - Contribution to increase in noise & vibration during construction, OR - Public Address system, OR - Track Warning system |  |  | - Noise Management Area OR - Residents within 200m (500m for noisier works), OR - Contribution to increase in noise & vibration during construction, OR - Contribution to increase in noise & vibration during construction, OR - Public Address system, OR - Track Warning system | Otherwise
| Pollution of land / water | - Watercourse within 10min OR Source Protection Zone, AND - Handling >200L of oil, OR - Handling of other hazardous substances, OR - Ballast treated with anti-icer, OR - Water discharge |  |  | - Watercourse within 10m, OR - Source Protection Zone, OR - Handling >200L of oil, OR - Handling of other hazardous substances, OR - Ballast treated with anti-icer, OR - Water discharge | Otherwise
| Energy Efficiency & Carbon | - Building, OR - Structure, OR - Significant quantities of concrete and/or steel |  |  | - Operational power supply, OR - Construction power supply | Otherwise
| Materials - Resource Efficiency & Responsible Sourcing | - Large volumes of engineering fill and/or aggregates, OR - Significant quantities of concrete and/or steel |  |  | - Compounds, haul roads and/or access points, OR - Timber and other forest products | Otherwise
| Waste | - Significant volumes of demolition and/or excavation waste, OR - Significant volumes of other construction waste |  |  | - Building, structure or equipment decommissioned, demounted, demolished or stripped-out | Otherwise
| Weather Resilience & Climate Change Adaptation | - Watercourse within 10m OR Flood Zone, AND - Asset vulnerable to climate change |  |  | - Watercourse within 10m, OR - Flood Zone, OR - Asset vulnerable to climate change | Otherwise
| Water Resource | - Water abstraction |  |  | - Water requirements during construction, OR - Increase in water requirements during operation | Otherwise
| Sustainable Travel | - Interface with other modes of transport |  |  | - Large workforce | Otherwise
| Being a caring neighbour | - Residents within 200m (500m if noisier works), OR - High volume of complaints |  |  | - Residents within 200m (500m if noisier works) | Otherwise
| Connecting communities with the environment | - Vegetation management, AND - Schools within 20 miles, OR - Community Rail Partnership |  |  | - Vegetation management, AND - Residents within 250m, OR - Station and/or platform environment | Otherwise
| Making rail a great experience | - Community Rail Partnership, AND - Station and/or platform environment |  |  | - Community Rail Partnership, OR - Station and/or platform environment | Otherwise
| Creating industry partnerships and engaged employees | - Correctional facility or rehabilitation centre within 20 miles, OR - Homelessness service or centre within 20 miles, OR - Place of worship within 1km, OR - Social deprivation |  |  | - Heritage railway within 10km, OR - Schools within 20 miles, OR - Community Rail Partnership | Otherwise
| Inspiring tomorrow’s workforce | - Schools within 20 miles AND Project >£50 million |  |  | - Schools within 20 miles | Otherwise
| Keeping Communities safe | - Route crime, OR - OLE electrification, OR - Level Crossing renewal |  |  | - Level crossing closure | Otherwise
| Making travel inclusive and accessible | - Access to buildings, stations or bridges, OR - Public access affected during construction |  |  | - Community Rail Partnership, OR - Station and/or platform environment | Otherwise
| Respecting cultural history and rail heritage | - Heritage sites |  |  | - Heritage railway | Otherwise
| Supporting Britain’s economic development | - Social deprivation |  |  | - Large workforce | Otherwise
| Dust, odour and lighting |  |  |  | - Outdoor artificial lighting | Otherwise
Q.7. | What's the purpose of the snapshot?
A.7 | This functionality allows the user to keep versions of the Action Plan throughout the project lifecycle e.g. at the end of each PACE stage or before significant changes or updates were made.
5. Definitions
| Abbreviation | Definition
| Air Quality Management Area | Declared where the national 'air quality objective' set by UK Government is exceeded therefore, within that area, the monitoring of specific pollutants has been undertaken and a plan put in place to improve air quality.
| Area of Outstanding Natural Beauty (AONB) | An area of land protected by the government in order to conserve its significant landscape value.
| As low as reasonably practicable (ALARP) | Reasonably practicable involves weighing the risk / benefit against the effort, time and money needed to control it. Any requirements within this standard should be applied to ALARP using a whole-life cost approach for their consideration.
| Asset | Any item, entity, or property owned by Network Rail and regarded as having actual or potential value or function to the operation of the rail network, to other Network Rail business activities, or to other stakeholders.
| AMP | Asset Management Plan
| Best practicable means (BPM) | Measures taken to reduce the impacts of noise and vibration caused by works.
| Biodiversity | The variety and variability among all forms of life
| Building research establishment environmental assessment method (BREEAM) | An international scheme that provides third-party certification for the assessment of sustainability performance for projects, infrastructure and buildings.
| Capital Carbon | Includes all carbon dioxide and other greenhouse gas emissions associated with the creation, construction, refurbishment and end-of- life decommissioning and treatment of an asset.
| Circular Economy | A circular economy is a sustainable alternative to the traditional linear economy of make, use and dispose. The aim of a circular economy is to extract fewer virgin resources from the planet and to keep existing resources in use for as long as possible. Resources, products and materials should be re-used, repaired and regenerated in order to extend their useful lifespan and extract their maximum environmental, social and financial value. This approach reduces embodied carbon, water and social impacts and keeps waste to a minimum.
| Civil engineering environmental quality assessment & awards scheme (CEEQUAL) | A sustainability assessment for engineering, infrastructure, landscaping and public realm projects.
| Contaminated Land | Land that has legally been defined as 'contaminated land’ where substances are causing or has the potential to cause significant harm to people, property or protected species, significant pollution of surface waters (e.g. lakes and rivers) or groundwater, air pollution, and/or harm to people as a result of radioactivity. Land can become contaminated with: • hazardous and/or non-hazardous materials from human activity (e.g. previous land uses, fuel spillages, fly tipping); • invasive non-native species; • naturally occurring hazardous substances like radon gas.
| Contractor | Any person or organisation, including a non-domestic client, who carries out, manages or controls works (as defined above).
| Design | Design includes any production of drawings, design details, specifications and bills of quantities (including specification of articles or substances) relating to a structure, and calculations prepared for the purpose of design.
| Designer | Any person or organisation, including a client, contractor or other person, who: • prepares or modifies a design • arranges for, or instructs, any person under their control to do so, relating to a structure, or a product or mechanical or electrical system intended for a particular structure. A person is deemed to prepare a design where a design is prepared by a person under their control.
| Drinking Water Protection Zone | Designated areas in which the use of certain substances must be carefully management to prevent the pollution of raw water sources that are used to provide drinking water.
| Emergency works | Works that must be undertaken immediately, without delay and with involvement from emergency services. The event is unexpected and serious, such that it presents a significant risk to human life, health and/or property, or the natural environment, and involves the need for immediate action to manage the risk.
| Employer's representative | Any role within Network Rail responsible for managing and delivering the contracted project or works activity at a given stage in the project/works life-cycle. This could be, without limitation, the Contract Manager, Development Manager, Project Manager, or Asset Manager.
| Environmental product declaration (EPD) | An independently verified and registered document that communicates transparent and comparable information about the life-cycle environmental impact of products
| Forest products | Any material derived from forestry, including timber, composite timber products, paper, card, etc.
| Geo-RIMN | Geo-RINM Viewer provides a map-based view of Network Rail's geographic data, as well as tools to query and analyse asset information.
| Ground investigation (GI) | A process to determine the condition (particularly in relation to contamination) of the ground, ideally before beginning construction works.
| Health & Safety File (HSF) | A file prepared to satisfy regulation 12(5) of the Construction (Design and Management) Regulations. The purpose of the HSF is to confirm that, at the end of a project, the client has information that anyone carrying out subsequent construction work on the same site or structure would need to be aware of in order to plan and carry out work safely and without risk to health.
| Indicators | Indications of performance and/ or the likelihood of meeting targets. The most significant of these, for a business, are key performance indicators.
| Non-construction works | Works outside the scope of construction works might include non-intrusive surveys and inspections carried out as part of the pre-construction phase, vegetation clearance that is not associated with the construction phase, and structures examinations.
| Potable water | Water that is safe to drink.
| Preliminary ecological appraisal (PEA) | A rapid assessment of the habitats and ecological features, present or potentially present, within a site and within the wider zone of influence of a project or work site. A PEA normally comprises a desktop study and a site walkover survey such as an Extended Phase 1 Habitat Survey. The PEA will determine the need for further Phase 2 surveys. PEAs need to be conducted in accordance with the most current edition of Chartered Institute of Ecology and Environmental Management (CIEEM) Guidelines for Preliminary Ecological Appraisal.
| Preliminary risk assessment (PRA) | The Preliminary Risk Assessment (Phase 1 desktop study) is the first stage of the contaminated land assessment process. This involves analysing historical and environmental information for the site and within a 250 m radius around the site as detailed in the Environment Agency’s Land Contamination Risk Management (LCRM) guidance. A risk assessment report with conceptual site modelling will be undertaken. If this demonstrates no risk from contamination, the planning will be released, subject to local authority agreement.
| Ramsar | Ramsar sites are wetlands of international importance that have been designated under the criteria of the Ramsar Convention on Wetlands for containing representative, rare or unique wetland types or for their importance in conserving biological diversity.
| Safety Central | Safety Central is a Network Rail managed website to promote best practice health, safety and sustainability within the rail industry. Network Rail environment and social guidance notes can be found on this website: https://safety.networkrail.co.uk/.
| Site Management Statement (SMS) | Site Management Statements are produced by Network Rail to give notice under section 28H of the Wildlife and Countryside Act 1981 (as amended) of its intention to carry out routine maintenance operations on the land under its control which lies directly adjacent to particular SSSIs. If Natural England agrees with the SMS, they will issue a Letter of Assent to confirm the arrangement.
| Site of Special Scientific Interest (SSSI) | A SSSI can be designated to give higher levels of protection than other designations (e.g. Areas of Outstanding Natural Beauty). SSSIs must be managed by the land owners appropriately to conserve its special features.
| SKA rating | SKA rating is an environmental assessment method, benchmark and standard for non-domestic fitouts, led and owned by the Royal Institute of Chartered Surveyors (RICS).
| Special Area of Conservation (SAC) | Sites that have been formally designated by the government of each country in whose territory the site lies.
| Social performance | The extent to which Network Rail's operations, activities and decisions impact people- including passengers, employees, suppliers, communities or other groups affected by Network Rail's physical and socio-economic presence.
| Social value | Defined by Social Value UK as "the quantification of the relative importance that people place on the changes they experience in their lives. Some, but not all of this value is captured in market prices." The term 'social value' is used sometimes interchangeably with the term 'social performance.'
| Source-Pathway-Receptor Conceptual Model | Pollution model that maps out potential pollution sources and pathways to vulnerable receptors.
| Source Protection Zone (SPZ) | These are defined zones which show the level of risk to the source of groundwater supply from contamination.
| Structure | a) Any building, timber, masonry, metal or reinforced concrete structure, railway line or siding, tramway line, dock, harbour, inland navigation, tunnel, shaft, bridge, viaduct, waterworks, reservoir, pipe or pipeline, cable, aqueduct, sewer, sewage works, gasholder, road, airfield, sea defence works, river works, drainage works, earthworks, lagoon, dam, wall, caisson, mast, tower, pylon, underground tank, earth retaining structure or structure designed to preserve or alter any natural feature, and fixed plant; or similar, b) Any formwork, falsework, scaffold or other structure designed or used to provide support or means of access during construction work.
| Supplier | The term used within Network Rail contracting to refer to a Designer and/or contractor.
| Traction energy | The energy used to move trains.
| Tree Preservation Order | A Tree Preservation Order is an order made by a local planning authority to protect specific trees, groups of trees or woodlands in the interests of amenity. The order prohibits activities such as cutting down, uprooting, and wilful damage of trees without the local planning authority’s written consent. If consent is given, it can be subject to conditions which have to be followed.
| Tree Root Protection Zone | A calculated area of ground that lies immediately under a tree and just beyond the extent of its crown. It is intended to help avoid damage to the tree’s rooting system.
| Urgent reactive works / Non-emergency unplanned works | Works that were not planned but must be undertaken urgently when a rail asset has failed due to a sudden and unforeseen event, fault or defect. There is not involvement from emergency services, but the work is deemed urgent in order to restore the rail network to a safe operating condition.
| Weather resilience and climate change adaptation (WRCCA) | Weather resilience is the ability of assets, networks and systems to anticipate, absorb, adapt to, and/or recover from disruptive weather events. Climate change adaptation is action taken to improve the resilience of assets, networks and systems to future weather conditions, avoiding, minimising or mitigating the impact of more severe or frequent adverse and extreme weather events and gradual or erratic changes in weather patterns due to climate change.
| Whole-life carbon | The sum of greenhouse gas emissions from all stages in the life cycle of an asset, including embodied carbon emissions of materials and products; capital carbon emissions from construction activities, major maintenance/ refurbishment/ replacement and end of life decommissioning and treatment; and operational carbon emissions from utilities consumption, minor servicing and maintenance

## Revision History
Revision History
Produced by: | Name: | Signed:
Job Title:
Date:
Reviewed by: | Name: | Signed:
Job Title:
Date:
Accepted by: | Name: | Signed:
Job Title:
Date:
Version | Change history | Document Number
P01
Reference Documents (PACE Products) |  | Document Number
Diversity Impact Assessment
Stakeholders & Customer Engagement Plan
Land & Consents Strategy
Land & Consents Commitments Register

## 1. Project Info
Project Information
Please enter the project information that relates to this appraisal. Once complete, please proceed to the 'Project Scope' tab.
1. Project control
Project Name: *
Project Number:
| Client Organisation: * |  | Select from drop down list…
Client Sponsor:
Client Project Manager:
| PACE Stage (or equivalent for non-PACE projects): * |  | Select from drop down list...
| Estimated Project Value (Development, Design and Construction): * |  | Select from drop down list…
Level of Control (LoC):
2. Project Location
| Network Rail Region and Route: * |  | Select from drop down list...
Does the project involve delivering the same scope of works at multiple locations (repeat/portfolio works)?
Does the project involve delivering the same scope of works over a large project area (e.g. re-signalling)?
Does the project involve delivering a multi-discipline scope of works at multiple locations or over a large project area?
Overview of project location(s): More details to be provided within Desktop Study
3. Project Description (Refer to Client Remit/Sponsor Instruction)
| 4. Useful Network Rail Contacts for this Project (Optional) |  | Search by 'Position_Name' on |  |  |  | OrgPlus
| Role |  | Name |  |  |  | Contact details
NR Environment & Sustainability Representative (Specialist or Manager)
NR Ecologist
NR Consents Manager
NR Town Planning Representative (Property)
NR Communications Manager
NR Community Relations Manager
NR Maintenance Protection Co-ordinator (MPC)
NR Section Manager (Off Track)
NR Project Interface Co-ordinator (PIC)
NR Community Safety Manager
NR Level Crossing Manager
* mandatory
Q | S21 | The project will involve design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). | 0 | Yes | 0 | No |  | {P4}="Route Services"
Q | S22 | The project will involve decommissioning of the existing asset. | 0 | Yes | 0 | No |  | {P4}="Route Services"

## 2. Project Scope
Project Scope
To set the scope for the project, confirm which of the activities are appropriate. Once your scope of work is set, review what has been included/excluded to ensure this accurately reflects your works programme. You should do this before starting your appraisal, as the project information you provide will determine which questions and actions you need to consider going forward. Proceed by clicking the 'Start Appraisal' button.
Template | Group Header
| WBS1.1 | Question | c |  | c |  | c |  | 0
| WBS1.1 | Questions with freeform answer | 0
| 0% | [8 empty] | 20 | 0
| Enabling Activities | [8 empty] | Y
Q101 | S1 | The project involves vegetation management and/or land take. | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q102 | S2 | The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s). | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q103 | S3 | The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
| Buildings & Civils | [8 empty] | Y
Q104 | S4 | The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q105 | S5 | The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q106 | S6 | The project involves other civils work (e.g. foundations, fencing, walkway, etc.). | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
| Geotechnical & Drainage | [8 empty] | Y
Q107 | S7 | The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q108 | S8 | The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
| Track | [8 empty] | Y
Q109 | S9 | The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q110 | S10 | The project involves plain line extension (e.g. new track line, new loop, grade separation) | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q111 | S11 | The project involves new or modified sidings | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
| Electrical & Power | [8 empty] | Y
Q112 | S12 | The project involves replacing or installing new OLE | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q113 | S13 | The project involves replacing or installing new feeder station or sub-station | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q114 | S19 | The project involves replacing or installing new lineside E&P assets (e.g. DNO, lighting, etc.) | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q115 | S20 | The project involves replacing and/or installing new E&P cable route | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
| Signalling & Telecoms | [8 empty] | Y
Q116 | S15 | The project involves replacing and/or installing Under Track Crossing (UTX)/Under Road Crossing (URX). | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q117 | S14 | The project involves replacing and/or installing new lineside S&T assets (e.g. signal, signal box, signage, REB, location cabinet, GSM mast, etc.) | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q118 | S16 | The project involves replacing and/or installing new S&T cable route | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
| Level Crossing (LX) | [8 empty] | Y
Q119 | S17 | The project involves renewing and/or modifying a Level Crossing | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
Q120 | S18 | The project involves closing a Level Crossing | 0 | Yes | 0 | Maybe | 0 | No | 0 | Y
| On Track Machine (OTM) Design/Build/Refurbishment | [8 empty] | Y
Q121 | S21 | The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). | 0 | Yes | 0 | No |  |  | 0 | {P4}="Route Services"
Q122 | S22 | As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments? | 0 | Yes | 0 | No |  |  | 0 | {P4}="Route Services"
Start Appraisal

## 3. Project Activities
Project Activities
Based on the scope of the assessment set out in the 'Project Info & Scope' tab, you will be asked to provide answers to a series of questions on environmental and social risks. Where appropriate, provide additional information. Please provide an answer to each question and then proceed by clicking the 'Move to Desktop Study' button.
| WBS1.1 | Questions with freeform answer | 0
Template | Group Header
Template | WBS1.1 | Question | c |  | c |  | c |  | c | c | 0
Template | WBS1.1.1 | Question | c |  | c |  | c |  | c | c | 0
Template | WBS1.1 | Question Heading
Template | 0% | [10 empty] | 100% | 0%
| Ref. | Question | Response | [7 empty] | Additional Information
| Biodiversity | [10 empty] | Y
Q58 | A1 | Will vegetation management and/or land take impact an area >1,500m2? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S1}="Yes"
Q59 | A35 | Will land take impact third party land? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S1}="Yes"
| Pollution of land /water | [10 empty] | Y
Q60 | A2 | Will the project require handling >200L of oil and/or fuel during construction (e.g. diesel generator, refuelling tank, oil-filled High Voltage cable) and/or operation (e.g. transformer, refuelling depot)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q61 | A3 | Will the project require substances hazardous to the environment (other than oil and fuel) during construction and/or operation (e.g. solvent, herbicide, etc.)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q62 | A4 | Will the project require delivery of anti-icer treated rail ballast (based on programme of works)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S9¦S10¦S11}="Yes"
| Emissions to Air | [10 empty] | Y
Q63 | A5 | Will the project contribute to local air pollution from diesel rolling stock during operation (e.g. passenger train idling at new depot or expanded sidings, freight train idling at new signal location, etc.)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S5¦S9¦S10¦S11¦S14}="Yes"
Q64 | A6 | Will the project contribute to local air pollution (including dust and fumes) during construction (from earthworks, plant and equipment as well as vehicles for the transport of materials, etc.)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
| Pollution of land /water | [10 empty] | Y
Q65 | A12 | Will the project require temporary or permanent water discharge to surface water or sewerage system? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q66 | A13 | Will the project require piling, boring or drilling? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S4¦S5¦S6¦S7¦S12¦S14¦S14}="Yes"
| Noise & Vibration | [10 empty] | Y
Q67 | A7 | Will the project contribute to an increase local noise & vibration levels during operation (e.g. new or increased maintenance depot activities, additional rolling stock, rolling stock idling at new signal location, etc.)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S5¦S9¦S10¦S11¦S15}="Yes"
Q68 | A8 | Will the project contribute to an increase local noise & vibration levels during construction (excavation/demolition works, tamping, piling, cutting, drilling, etc.)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q69 | A9 | Will the project require the installation of a Public Address (PA) system? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S5}="Yes"
Q70 | A10 | Will the project require the installation of an Automatic Track Warning System? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S14¦S17}="Yes"
| Dust, Odour & Lighting | [10 empty] | Y
Q71 | A11 | Could the project require installation of temporary (i.e. construction) and/or permanent (i.e. operation) outdoor artificial lighting? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q72 | A44 | Is there a risk of dust or odour emissions? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
| Energy | [10 empty] | Y
Q73 | A14 | Will the project involve modifying, replacing and/or providing new operational power supply to lineside equipment? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S11¦S13¦S14¦S17¦S19}="Yes"
Q74 | A15 | Will the project require access to a power supply during construction? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q75 | A43 | Have you identified opportunities to reduce energy and fuel usage? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
| Materials | [10 empty] | Y
Q76 | A16 | Will construction (including site compounds) require import of large volumes of engineering fill and/or aggregates (>100t), including track bed material? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q77 | A17 | Will construction require significant quantities of concrete and/or steel (>100t), including track material? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q78 | A18 | Will construction require timber or other forest products for temporary (e.g. hoarding, formwork) or permanent use (e.g. structural frame, cladding) other than rail sleepers? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
| Waste | [10 empty] | Y
Q79 | A19 | Will existing building, structure or equipment need to be decommissioned, demounted, demolished or stripped-out as part of the project? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q80 | A20 | Are the construction works likely to generate significant volumes of demolition and/or excavation material (>100 tonnes)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q81 | A21 | Are the works likely to generate significant volumes of construction waste (>100 tonnes) other than demolition and/or excavation material (e.g. plastic, timber or cardboard packaging; steel, timber, plastic off cuts; food or office waste, grit blasting waste; silt or sludge from drainage works; excess concrete)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
| Water | [10 empty] | Y
Q82 | A23 | Are the works likely to require large quantities of water (>100m3 or 100,000L) during construction (e.g. dust suppression including control of ballast dust, welfare facilities, grouting)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q83 | A24 | Will the project increase water consumption during operation? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S5}="Yes"
Q84 | A25 | Will the project require water abstraction (from surface water or groundwater) during construction and/or operation? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
| Weather Resilience & Climate Change Adaptation (WRCCA) | [10 empty] | Y
Q85 | A27 | Will the project increase the area requiring surface water drainage (e.g. car park, roof, new track, new sidings, feeder station containment, etc.)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S2¦S4¦S5¦S7¦S8¦S10¦S11¦S13}="Yes"
Q86 | A28 | Does the project include new or existing railway assets (including earthworks) vulnerable to higher temperature (e.g. rail buckling, signalling failure), heavier rainfall (e.g. land slip, power cut due to flooding) and/or more extreme coastal events (e.g. erosion, sea level rise)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S2¦S4¦S5¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S17¦S19}="Yes"
| Sustainable Travel | [10 empty] | Y
Q87 | A29 | Will the project offer an interface with other modes of transport (e.g. at station, depot, etc.) during operation? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S5}="Yes"
Q88 | A30 | Will the project involve a large workforce (>50) that will be travelling to a single location for a long period of time (>6 months) during construction? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
| Respecting cultural heritage and rail history (visual impact) | [10 empty] | Y
Q89 | A31 | Will the project involve erecting prominent structures or assets (e.g. OLE masts and wires, GSM mast, LX equipment inc. radars and lighting, signal gantries, fencing, etc.)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S4¦S5¦S6¦S12¦S13¦S14¦S17}="Yes"
| Making travel accessible and inclusive | [10 empty] | Y
Q90 | A32 | Will the project involve changing the permanent or temporary access to buildings, stations or bridges? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S4¦S5}="Yes"
Q91 | A33 | Could public access (including footpath, cycle path, rights of way, level crossing) require temporary closure and/or diversion during project delivery? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
Q92 | A42 | Will the project impact people (e.g. passengers, employees, or lineside neighbours), including temporary works, temporary conditions, and staging works? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {N1}="No"&&{S21&S22}<>"Yes"
| Connecting communities with the environment | [10 empty] | Y
Q93 | A34 | Will the project affect the station and/or platform environment? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S4¦S5¦S6}="Yes"
Q94 | A40 | Will visually prominent structures be erected in the project area? | 0 | Yes | 0 | No |  |  |  |  | 0 | {S4¦S9}="Yes"
| Inspiring tomorrow's workforce | [10 empty] | Y
Q95 | A41 | Are there any schools within 200m of the project area? | 0 | Yes | 0 | No |  |  |  |  | 0 | {P2}=">£50m"
Q96 | A45 | Does the project have any section 106 requirements set by a planning authority? | 0 | Yes | 0 | No |  |  |  |  | 0 | Y
| OTM Design/Build/Refurbishment | [10 empty] | Y
Q97 | A36 | Is the OTM powered by fossil fuels (includes primary engine power source as well as auxiliary power e.g. onboard generators)? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S21}="Yes"
Q98 | A37 | Does the OTM require hydrocarbon based lubricants to operate? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S21}="Yes"
Q99 | A38 | Does the OTM use large quantities of water as part of its operational activities (e.g. water to treat the track bed or onboard dust suppression), excluding engine cooling? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S21}="Yes"
Q100 | A39 | Is the OTM likely to be operated near lineside neighbours? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {S21}="Yes"
Move to Desktop Study

## 4. Desktop Study
Desktop Study
You will be asked to respond to a series of 'Desktop Study' questions based on environmental and social risks. Use the provided links to relevant data sources and guidance to help answer the questions. Where appropriate, provide additional information. Please provide an answer to each question and then proceed by clicking the 'Move to Action Plan' button.
| WBS1.1 | Questions with freeform answer | 0
Template | Group Header
Template | WBS1.1 | Question | c |  | c |  | c |  | c | c | 0
Template | WBS1.1.1 | Question | c |  | c |  | c |  | c | c | 0
Template | WBS1.1 | Question Heading
| 28.57% | [10 empty] | 28 | 8
| Ref. | Question | Response | [7 empty] | Additional Information |  |  |  |  | Links to relevant data sources
| Project Location | [10 empty] | Y
Q6 | D0.1 | ELRs and mileages (from/to): | 0 | [8 empty] | Y | No
Q7 | D0.2 | Asset ID (if applicable): | 0 | [8 empty] | Y | No
Q8 | D0.3 | Nearest Town/City and/or Postcode: | 0 | [8 empty] | Y | No
Q9 | D0.4 | Local Planning Authority (District, Borough or City Council): | 0 | [8 empty] | Y | No |  |  | Magic
Q10 | D0.5 | Parish, Community or Town Council: | 0 | [8 empty] | Y | No |  |  | Magic
Q11 | D0.6 | Local Member of Parliament: | 0 | [8 empty] | Y | No |  |  | Find my MP
Q12 | D0.7 | Is access to third party land required? | 0 | Yes | 0 | No |  |  |  |  | 0 | Y
| Biodiversity | [10 empty] | Y
Q13 | D1 | Are there records of ecology survey(s) covering the project area on Geo-RINM? ! Absence of records on Geo-RINM does not confirm absence of previous surveys recorded locally! ! Preliminary Ecological Appraisals require re-validation after 24 months ! | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Geo-RINM
Q14 | D2 | Are there records of protected species within 1km of the project area? ! Absence of records does not confirm absence of protected species ! | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  | H[22] | S[22] | National Hazard Directory | Geo-RINM | Magic
Q15 | D2.1 | If No, within 2km? | 0 | Yes | 0 | No |  |  |  |  | 0
| D3 | Are any of the following statutory designated sites within 2km of the project area? | [9 empty] | Y |  |  |  | Geo-RINM | Magic
G1 | D4.1 | Site of Special Scientific Interest (SSSI) | 0 | Applicable | [6 empty] | 0 | Y |  | S[25] | H[25,26]
Q18 | D4.1.1 | Is NR land included within the SSSI designation? | 0 | Yes | 0 | No |  |  |  |  | 0 |  |  | S[26] | H[26] | Register of SSSIs on NR land
Q19 | D4.1.1.1 | Is there an up to date Site Management Statement (SMS) in place? Note: there is no SMS in Wales and Scotland: Answer 'No' by default | 0 | Yes | 0 | No |  |  |  |  | 0 |  |  |  |  | Site Management Statements (England only)
G1 | D4.2 | Special Area of Conservation (SAC) | 0 | Applicable | [6 empty] | 0 | Y
G1 | D4.3 | Special Protection Area (SPA) | 0 | Applicable | [6 empty] | 0 | Y
G1 | D4.4 | Ramsar | 0 | Applicable | [6 empty] | 0 | Y
G1 | D4.5 | Area of Outstanding Natural Beauty (AONB) | 0 | Applicable | [6 empty] | 0 | Y
G1 | D4.6 | National Park | 0 | Applicable | [6 empty] | 0 | Y
G1 | D4.7 | National Nature Reserve | 0 | Applicable | [6 empty] | 0 | Y
G1 | D4.8 | Local Nature Reserve | 0 | Applicable | [6 empty] | 0 | Y |  |  |  | find a LERC map | Planning Portal
G1 | D4.9 | Provide details of any other designations (non-statutory) identified: | 0 | [8 empty] | Y | No
G1 | D4.10 | None of the above | 0 | Applicable | [6 empty] | 0 | Y
Q29 | D5 | Is there an Ancient Woodland Site near (<50m) or within the project area? | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Magic (England) | Lle Map (Wales) | Scotland's Environment Maps
Q30 | D6 | Are there records of Tree Preservation Order (TPO) near (<50m) or within the project area? ! Absence of records does not confirm absence of TPO ! | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Geo-RINM | National Hazard Directory | find a LERC map | Planning Portal
Q31 | D7 | Are there records of Japanese Knotweed, Giant Hogweed or Himalayan Balsam (Invasive Non-Native Species - INNS) near (<50m) or within the project area? ! Absence of records does not confirm absence of INNS ! Note: Other non-native invasive plant species (e.g. Cotoneaster, Rhododendron) must be considered as part of a Preliminary Ecological Appraisal (PEA) | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Geo-RINM | National Hazard Directory
| Contaminated Land | [10 empty] | Y
Q32 | D8 | Are there records of contaminated land and/or historic landfill (including landfill gases and past mining activities) near (<250m) or within the project area? ! Absence of records does not confirm absence of contaminated land ! | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Geo-RINM | National Hazard Directory | Groundsure Enviro Data Viewer
| Hydrology and hydrogeology | [10 empty] | Y
Q33 | D9 | Is the project area within 10m of a sea, estuary, watercourse (main river or ordinary watercourse such as open drainage, brook, etc.) or other surface water body (pond, canal, lake, loch, reservoir, etc.)? | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Geo-RINM | Google Map
Q34 | D13 | Is the project area within or near a fluvial, coastal (i.e. Flood Zone 3) and/or surface water high flood risk area? | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | England & Wales (Coastal & River Flooding) | England & Wales (Surface Water Flooding) | Scotland (Coastal, River & Surface Water Flooding)
Q35 | D10 | In the project area within a Source Protection Zone (SPZ) in England & Wales or Drinking Water Protection Area (Scotland)? Note: Answer 'Yes' by default if project area in Scotland as the whole country is covered by Drinking Water Protection Areas for its Groundwater. | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Magic (England) | Groundsure Enviro Data Viewer (England) | Lle Map (Wales) | Scotland
| Emissions to Air | [10 empty] | Y
Q36 | D11 | Is the project area within an Air Quality Management Area (AQMA)? | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Noise & Air Quality Viewer (England) | Noise & Air Quality Viewer (Wales) | Air Quality in Scotland
| Noise & Vibration | [10 empty] | Y
Q37 | D12 | Is the project area within a Noise Management Area (Important Area or Priority Area) for Roads and/or Railways (England & Wales)? Note: Answer 'No' by default if project area in Scotland as Noise Management Areas have not yet been defined. | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Noise & Air Quality Viewer (England) | Noise & Air Quality Viewer (Wales)
| Respecting cultural heritage and rail history | [10 empty] | Y
Q38 | D27 | Will the project area include scheduled monuments, archaeological sites and deposits, or buildings of historical and architectural interest? | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Geo-RINM | Historic England | Lle Map (Wales) | Scotland's Environment Maps
| D15 | Is the project area within 150m of any of the following? | [9 empty] | Y |  |  |  | Geo-RINM | Historic England | Lle Map (Wales) | Scotland's Environment Maps
G2 | D15.1 | Grade I and II Listed buildings | 0 | Applicable | [6 empty] | 0 | Y
G2 | D15.2 | Scheduled ancient monuments | 0 | Applicable | [6 empty] | 0 | Y
G2 | D15.3 | Conservation areas | 0 | Applicable | [6 empty] | 0 | Y
G2 | D15.4 | World heritage sites | 0 | Applicable | [6 empty] | 0 | Y
G2 | D15.5 | Other (e.g. registered parks and gardens, registered battlefields, Area of Archaeological Interest, war memorial, designated items) | 0 | [8 empty] | Y | No
G2 | D15.6 | None of the above | 0 | Applicable | [6 empty] | 0 | Y
Q46 | D16 | Is there a heritage railway near (<10km) the project area? | 0 | Yes | 0 | No |  |  |  |  | 0 | VLOOKUP({P2},tblProjectValues,2,False)>=6 |  |  |  | Heritage Railways (UK)
| Being a caring neighbour | [10 empty] | Y
Q47 | D17 | Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  | H[61] | S[61] | Google Map | Social Value Framework
Q48 | D17.1 | If No, within 250m? | 0 | Yes | 0 | No |  |  |  |  | 0
Q49 | D18 | Are there sensitive/vulnerable receptors (e.g. hospital, care home) near (<200m) the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Google Map | Social Value Framework
Q50 | D19 | Are there schools and/or universities within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value | 0 | Yes | 0 | No |  |  |  |  | 0 | VLOOKUP({P2},tblProjectValues,2,False)>=6 |  |  |  | Google Map | Social Value Framework
Q51 | D20 | Is there employment a correctional facility or rehabilitation centre within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value | 0 | Yes | 0 | No |  |  |  |  | 0 | {P2}=">£50m" |  |  |  | Google Map | Social Value Framework
Q52 | D21 | Is there a homelessness service or centre within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value | 0 | Yes | 0 | No |  |  |  |  | 0 | {P2}=">£50m" |  |  |  | Homeless England | Social Value Framework
Q53 | D22 | Is there a place of worship (e.g. church, mosque, temple, etc.) within 1km of the project area? Note: Please see the Social Value Framework for opportunities around social value | 0 | Yes | 0 | No |  |  |  |  | 0 | {P2}=">£50m" |  |  |  | Google Map | Social Value Framework
Q54 | D23 | Is the project area located where a large number of complaints (>10) has been received over the past 2 years? Username: NR.user Password: NRUser2019# | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Complaints Map
| Keeping communities safe | [10 empty] | Y
Q55 | D25 | Is the project area affected by route crime (e.g. trespass) or suicide (i.e. Amber or Red Status)? Note: Use the Route Crime Excel Register | 0 | Yes | 0 | No |  |  |  |  | 0 | Y |  |  |  | Route Crime
| Supporting Britain's economic development | [10 empty] | Y
Q56 | D26 | Does the project area include neighbourhood(s) affected by social deprivation (i.e. amongst the 10% most deprived neighbourhoods in the country)? | 0 | Yes | 0 | No |  |  |  |  | 0 | {P2}=">£50m" |  |  |  | Index of Multiple Deprivation (England) | Welsh Index of Multiple Deprivation | Scottish Index of Multiple Deprivation
Q57 | D29 | Are there opportunities available to (i) share contract opportunities with SME, local and/or VCSE business groups (ii) job opportunities with local communities? | 0 | Yes | 0 | No | 0 | Don't Know |  |  | 0 | {P2}=">£50m"
| General | [10 empty] | Y
Q123 | D30 | Have objective, targets and key performance indicators been identified? | 0 | Yes | 0 | No |  |  |  |  | 0 | Y
| Energy and Carbon | [10 empty] | Y
Q124 | D31 | Have opportunities been identified to support carbon reduction commitments and the decarbonisation programme? | 0 | Yes | 0 | No |  |  |  |  | 0 | Y
| General | [10 empty] | Y
Q125 | D32 | As part of the response to the relevant invitation to tender, did the designer/ contractor make environmental and or social commitments? | 0 | Yes | 0 | No |  |  |  |  | 0 | Y
Move to Action Plan

## Heat Map (hidden)
Being a caring neighbour | Biodiversity | Circular economy | Connecting communities with the environment | Contaminated Land | Creating engaged employees and positive industry partnerships
Dust, odour and lighting | Emissions to Air | Energy & Carbon | Inspiring tomorrow’s workforce | Keeping Communities safe | Making rail a great experience
Making travel accessible and inclusive | Materials - Responsible Sourcing | Noise and vibration | Pollution of land / water | Respecting cultural heritage and rail history | Supporting Britain’s economic development
Sustainable Travel | Waste | Water | Weather Resilience & Climate Change Adaptation (WRCCA)

## Definitions (hidden)
Definitions
ASSET | Any item, entity or property owned by Network Rail and regarded as having actual or potential value or function to the operation of the rail network, to other Network Rail business activities, or to other stakeholders.
CONSTRUCTION | Any physical building, civil engineering or engineering construction work that results in new, modified, renewed, refurbished, decommissioned, demolished or otherwise changed assets, regardless of the Network Rail business division that awarded the contract. Other activities that enable planning and mobilisation for construction are also included, but excluding design work (see Design). See also extended definition as per Construction (Design and Management) Regulations 2015, Regulation 2.
DESIGN | Any work to ‘design’ new, modified, renewed, refurbished, decommissioned, demolished or otherwise changed assets. Design activity comprises the production of any plans, drawings, calculations, specifications or bills of quantities that define the appearance, structure, function or performance of an asset before or while it is being constructed. Other desk top activities such as planning or data gathering to support the design process are also included in design. Where physical or mechanised activities are undertaken on site to enable and support design, such as vegetation clearance, exploration or investigation, these shall be treated as Construction.
MAINTENANCE | Any physical works aimed at sustaining or restoring the condition, function or performance of an existing asset, including component replacement but without resorting to full renewal/asset replacement.
WORK SITE | The primary development site and any associated temporary work sites to be used for compounds, satellite construction sites, storage / stock-piling, haul roads, service diversions, access/egress, etc. This includes both Network Rail land and any third party land that will be impacted.

## 5. Action Plan
Action Plan
The Action Plan provides a summary of the specific risks and opportunities associated with your project, and actions you will need to take to respond to them.
Indicative Level of Risk & Opportunities
| Social | Low
| Environmental | Low
Level 1 Template | General
Template | Sub section | Vegetation management activities to be planned and delivered under a Method Statement reviewed and approved by an Ecologist. | S1, S2, S5 | GRIP 2-4 | Adam Hill
Template
Template
[8 empty] | Action Owner |  | Employer's Representative |  |  | Automation
Macro | Environmental & Social Themes | Action (1) | Trigger (Double click question references for more information) |  |  | Due by (PACE stage or Date) | Action Owner (Organisation or Individual) | Action Accepted (Yes/No) | Action Owner's Response (Please provide evidence here if you believe this action is not applicable) | Response Accepted (Yes/No) | Employer's Comments | Action Status (Open / Closed / N/A) | Sort Referenced | Risk Level | Visibility Logic | ESR Type
Level 1 Template | General | [11 empty] | 1000 | 4¦GeneralAtTop | ;; | N/A
T1;127;0 | Appraisal Completeness | One or more Project Activities questions were answered as 'Don't know': Provide update at the next project development stage. i | DK1 | ALL | [8 empty] | 1001 | 4¦GeneralAtTop | {DK1}="Yes"
T154;117;0 | Appraisal Completeness | One or more Project Scope questions were answered as 'Maybe': Provide update at the next project development stage. i | M1 | ALL | [8 empty] | 1002 | 4¦GeneralAtTop | {M1}="Yes"
T2;261;0 | External Benchmarking | Identify suitable Sustainability Certification Scheme (CEEQUAL, BREEAM or equivalent) and integrate associated Assessment with expected level of achievement/rating (e.g. Very Good or Excellent) into Client/Route Requirement Document and Contract Requirements. i | S4, S5, S12 | Phase 1 | Client | [7 empty] | 1003 | 4¦GeneralAtTop | [{S4¦S5¦S12}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)=7
T3;201;0 | 3rd party Land Take | Liaise with Town Planning representative to trigger negotiation with land owner and identify planning requirements (e.g. TWAO). Update Land & Consents Strategy and associated Commitments accordingly. i | A35 | Phase 2 | Client | [7 empty] | 1004 | 4¦GeneralAtTop | {A35}="Yes"
T4;228;0 | Compound / Haul Road / Access Point | Undertake site-specific Desktop Study for the proposed Compound/Haul Road/Access Point and select location with the least environmental and social impacts (e.g. least biodiversity loss and/or least nuisance to local community) i | S2, S2 | Phase 3 | Client | [7 empty] | 1005 | 4¦GeneralAtTop | {S2}="Yes"¦¦{S2}="Maybe"
T5;286;0 | Compound / Haul Road / Access Point | Provide findings of site-specific Desktop Study to Contractor for associated environmental and social risks (e.g. ecology, noise & vibration, pollution, invasive species, etc.) to be addressed as part of the Work Package Plan (WPP) and/or Environment & Social Management Plan (ESMP). i | S2, S2 | Phase 3 | Client | [7 empty] | 1006 | 4¦GeneralAtTop | {S2}="Yes"¦¦{S2}="Maybe"
T163;53;0 | Third Party Land | Obtain appropriate landowner consent prior to works i | D0.7 | [9 empty] | 1007 | 4¦GeneralAtTop | {D0.7}="Yes"
T7;217;0 | Site Investigation | Undertake site-specific Desktop Study for the proposed Site Investigation and select locations with the least environmental and social impacts (e.g. least biodiversity loss and/or least nuisance to local community) i | S3, S3 | Phase 2-3 | Client | [7 empty] | 1008 | 4¦GeneralAtTop | {S3}="Yes"¦¦{S3}="Maybe"
T8;305;0 | Site Investigation | Provide findings of site-specific Desktop Study to Contractor for environmental and social risks associated with this activity (e.g. ecology, noise & vibration, pollution, invasive species, etc.) to be addressed as part of the Work Package Plan (WPP) and/or Environment & Social Management Plan (ESMP). i | S3, S3 | Phase 2-3 | Survey Contractor / Principal Contractor | [7 empty] | 1009 | 4¦GeneralAtTop | {S3}="Yes"¦¦{S3}="Maybe"
T10;131;133 | Environmental Resources | Principal Contractor to provide Safety, Health & Environment Advisor with environmental competence and experience in Construction i ! This is a requirement under the Principal Contractor Licensing Scheme (NR/L2/INI/CP0070) ! | P2, S21, S22 | Phase 3 | Principal Contractor | [7 empty] | 1010 | 4¦GeneralAtTop | VLOOKUP({P2},tblProjectValues,2,False)<=3&&{S21&S22}<>"Yes"
T11;132;134 | Environmental Resources | Principal Contractor to have an Environmental Professional with IEMA Associate membership (or equivalent) available to the Project i ! This is a requirement under the Principal Contractor Licensing Scheme (NR/L2/INI/CP0070) ! | P2, S21, S22 | Phase 3 | Principal Contractor | [7 empty] | 1011 | 4¦GeneralAtTop | VLOOKUP({P2},tblProjectValues,2,False)=4&&{S21&S22}<>"Yes"
T12;134;136 | Environmental Resources | Principal Contractor to have an Environmental Professional with IEMA Practitioner membership (or equivalent) embedded in the Project i ! This is a requirement under the Principal Contractor Licensing Scheme (NR/L2/INI/CP0070) ! | P2, S21, S22 | Phase 3 | Principal Contractor | [7 empty] | 1012 | 4¦GeneralAtTop | VLOOKUP({P2},tblProjectValues,2,False)=5&&{S21&S22}<>"Yes"
T13;178;180 | Environmental Resources | Principal Contractor to provide Full time Environment Advisor (or equivalent) with IEMA Practitioner membership (or equivalent) and at least 5 years experience in Construction i ! This is a requirement under the Principal Contractor Licensing Scheme (NR/L2/INI/CP0070) ! | P2, S21, S22 | Phase 3 | Principal Contractor | [7 empty] | 1013 | 4¦GeneralAtTop | VLOOKUP({P2},tblProjectValues,2,False)=6&&{S21&S22}<>"Yes"
T14;169;171 | Environmental Resources | Principal Contractor to provide Full time Environment Manager (or equivalent) with Full IEMA membership (or equivalent) and at least 5 years experience in Construction i ! This is a requirement under the Principal Contractor Licensing Scheme (NR/L2/INI/CP0070) ! | P2, S21, S22 | Phase 3 | Principal Contractor | [7 empty] | 1014 | 4¦GeneralAtTop | VLOOKUP({P2},tblProjectValues,2,False)=7&&{S21&S22}<>"Yes"
T155;90;92 | ESMP | Develop a Design Environment & Social Management Plan (ESMP) using Network Rail template i ! Mandated under NR/L2/ENV/015, Section 4.2 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | N1, S21, S22 | Phase 3 | Designer | [7 empty] | 1015 | 4¦GeneralAtTop | {N1}="No"&&{S21&S22}<>"Yes"
T156;96;98 | ESMP | Develop a Construction Environment & Social Management Plan (ESMP) using Network Rail template i ! Mandated under NR/L2/ENV/015, Section 4.2 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | N1, S21, S22 | Phase 3 | Principal Contractor | [7 empty] | 1016 | 4¦GeneralAtTop | {N1}="No"&&{S21&S22}<>"Yes"
T157;95;97 | ESMP | Review Design ESMP using the Environmental & Social Contract Review and Acceptance Form (EN3) i ! Mandated as a PACE Product ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | N1, S21, S22 | Phase 2 | Client | [7 empty] | 1017 | 4¦GeneralAtTop | {N1}="No"&&{S21&S22}<>"Yes"
T158;92;94 | ESMP | Review Construction ESMP using the Environmental & Social Review and Acceptance Form (EN3) i ! Mandated as a PACE Product ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | N1, S21, S22 | Phase 2-3 | Client | [7 empty] | 1018 | 4¦GeneralAtTop | {N1}="No"&&{S21&S22}<>"Yes"
T159;183;0 | Records, documents and knowledge transfer | Handover any medium to long term permit, licence or consent conditions and requirements (e.g. maintenance and monitoring) to the Route with associated budget through the AMP process i | D2, D2.1, D4.1, D4.2, D4.3, D4.4, D4.5, D4.6, D4.7, D4.8, D5, D9, D13, D15.1, D15.2, D15.3, D15.4, S8, A12, A25 | Phase 4 | [8 empty] | 1019 | 4¦GeneralAtTop | {D2¦D2.1¦D4.1¦D4.2¦D4.3¦D4.4¦D4.5¦D4.6¦D4.7¦D4.8¦D5¦D9¦D13¦D15.1¦D15.2¦D15.3¦D15.4¦S8¦A12¦A25}="Yes"
T172;87;0 |  | Refer to Environment and Sustainability Strategy for key strategy areas for inclusion i | D30 | [9 empty] | 1020 | 4¦GeneralAtTop | {D30}="No"
T173;56;0 |  | Progress environment and/or social commitments to ESMP i | D32 | [9 empty] | 1021 | 4¦GeneralAtTop | {D32}="Yes"
Level 1 Template | Biodiversity | [11 empty] | 2000 | 1¦Low | [{D2¦D2.1¦D4.1¦D4.2¦D4.3¦D4.4¦D4.5¦D4.6¦D4.7¦D4.8¦D5¦D6¦D7}="Yes"]&&[{S1}="Yes"¦¦{S1}="Maybe"];[{D2¦D2.1¦D4.1¦D4.2¦D4.3¦D4.4¦D4.5¦D4.6¦D4.7¦D4.8¦D5¦D6¦D7}="Yes"¦¦{S1}="Yes"¦¦{S1}="Maybe"];True | Env
T15;168;170 | Surveying | Liaise with the project Environment & Sustainability Representative (Ecologist, Specialist, Manager) for local records of ecology surveys (not published on Geo-RINM) i Note: Consult an Ecologist to confirm validity and suitability of any existing survey report for this project | N1, S21, S22 | Phase 1 | Client / Designer | [7 empty] | 2001 | 1¦Low | {N1}="No"&&{S21&S22}<>"Yes"
T16;67;69 | Surveying | Request and review ecology survey report identified on Geo-RINM. i Note: Consult an Ecologist to confirm validity and suitability of the survey report for this project | D1 | Phase 1 | Client / Designer | [7 empty] | 2002 | 1¦Low | {D1}="Yes"
T17;122;124 | Surveying | Commission Preliminary Ecological Appraisal (PEA) including Phase 1 Habitat survey (unless valid PEA already available) i ! Mandated under NR/L2/ENV/015, Section 6.1 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! Note: Provide information gathered from Geo-RINM and NHD to the ecology services provider as part of the scope of works | N1, S21, S22 | Phase 1 | Client / Designer | [7 empty] | 2003 | 1¦Low | {N1}="No"&&{S21&S22}<>"Yes"
T18;141;0 | Surveying | Commission further surveys if required (i.e. Phase 2 Species absence/presence survey) based on findings and recommendations from PEA report i | N1, S21, S22 | Phase 2 | Client / Principal Contractor | [7 empty] | 2004 | 1¦Low | {N1}="No"&&{S21&S22}<>"Yes"
T21;195;0 | Planning & Control | Develop and implement Invasive Non-Native Species (INNS) Management Plan including bio-security control measures to prevent spreading (Japanese Knotweed, Giant Hogweed, Himalayan Balsam, etc.) i | D7 | Phase 2 | Survey Contractor / Principal Contractor | [7 empty] | 2005 | 1¦Low | {D7}="Yes"
T22;195;0 | Planning & Control | Plan works outside sensitive periods for wildlife (e.g. bird nesting, GCN hibernation, bat maternity and hibernation, badger winter sleep, etc.) when there is a risk to affect protected species i | N1, S21, S22 | Phase 2-3 | Client / Designer / Survey Contractor / Principal Contractor | [7 empty] | 2006 | 1¦Low | {N1}="No"&&{S21&S22}<>"Yes"
T23;125;0 | Planning & Control | Implement and maintain exclusion zone around protected trees based on Tree Root Protection Zone to prevent adverse impact. i | D5, D6 | Phase 2-3 | Principal Contractor | [7 empty] | 2007 | 1¦Low | {D5¦D6}="Yes"
T25;141;0 | Risk assessment | If transformer oil containment e.g. bunding is required (as per NR/L1/ELP/27000), integrate design solutions to prevent wildlife entrapment i | S13 | Phase 2-3 | Designer | [7 empty] | 2008 | 1¦Low | {S13}="Yes"
T26;101;0 | Risk assessment | Undertake OLE bird flight collision risk assessment and include diverter into design if recommended i | S12, S12 | Phase 2-3 | Designer / Principal Contractor | [7 empty] | 2009 | 1¦Low | {S12}="Yes"¦¦{S12}="Maybe"
T27;99;101 | Risk assessment | Undertake bird nesting inspection if undertaking vegetation management between March and October. i ! Only SAFETY CRITICAL vegetation management can be carried out between March and October (bird nesting season) ! | S1, S1 | Phase 2-3 | Survey Contractor / Principal Contractor | [7 empty] | 2010 | 1¦Low | {S1}="Yes"¦¦{S1}="Maybe"
T28;183;0 | Risk assessment | Undertake vegetation management activity under a method statement reviewed and approved by an ecologist, including watching brief by an ecologist or by an ecological clerk of works i | S1, S1 | Phase 2-3 | Survey Contractor / Principal Contractor | [7 empty] | 2011 | 1¦Low | {S1}="Yes"¦¦{S1}="Maybe"
T29;160;0 | Local knowledge | Liaise with the project Environment & Sustainability Representative regarding SSSI Site Management Statement (SMS) and activities allowed under this agreement i | D4.1.1.1 | Phase 2-3 | Client | [7 empty] | 2012 | 1¦Low | {D4.1.1.1}="Yes"
T30;178;0 | Local knowledge | Liaise with Section Manager (Off Track) regarding existing treatment schedule to control Invasive Non-Native Species (Japanese Knotweed, Giant Hogweed, Himalayan Balsam, etc.) i | D7 | Phase 2-3 | Client | [7 empty] | 2013 | 1¦Low | {D7}="Yes"
T146;64;0 | Local knowledge | Liaise with Section Manager (Off Track) regarding tagged trees i | S1, S1 | Phase 2-3 | Client | [7 empty] | 2014 | 1¦Low | {S1}="Yes"¦¦{S1}="Maybe"
T31;134;0 | Local knowledge | Liaise with Local Authority for latest Tree Preservation Order (TPO) locations (if not provided by Preliminary Ecological Appraisal) i | S1, S1 | Phase 2-3 | Client / Designer / Survey Contractor / Principal Contractor | [7 empty] | 2015 | 1¦Low | {S1}="Yes"¦¦{S1}="Maybe"
T32;182;0 | Consenting | Liaise with Ecologist and/or Regulator (Natural England, Natural Resources Wales, Scottish Natural Heritage) and apply for Protected Species Licence and/or SSSI Assent if required. i | D2, D2.1, D4.1 | Phase 2-3 | Client / Principal Contractor | [7 empty] | 2016 | 1¦Low | {D2¦D2.1¦D4.1}="Yes"
T33;138;0 | Consenting | Liaise with Local Authority and apply for Consent if works on protected trees (or within their Tree Root Protection Zone) is unavoidable i | S1, S1, D6, D15.3 | Phase 2-3 | Principal Contractor | [7 empty] | 2017 | 1¦Low | [{S1}="Yes"¦¦{S1}="Maybe"]&&[{D6¦D15.3}="Yes"]
T34;144;0 | Consenting | Liaise with Local Authority and apply for hedgerow Licence if vegetation management activities are affecting an important countryside hedgerow i | S1, S1 | Phase 2-3 | Principal Contractor | [7 empty] | 2018 | 1¦Low | {S1}="Yes"¦¦{S1}="Maybe"
T35;151;0 | Consenting | Liaise with Forestry Commission and apply for tree felling Licence if planning to fell large volume of trees outside the operational railway envelope i | S1, S1, A1 | Phase 2-3 | Principal Contractor | [7 empty] | 2019 | 1¦Low | [{S1}="Yes"¦¦{S1}="Maybe"]&&[{A1}="Yes"]
T36;150;0 | Consenting | Update Land & Consents Strategy and associated Commitments to consider consultation with National Park Authority due to potential impact on the Park i | D4.6 | Phase 2-3 | Client | [7 empty] | 2020 | 1¦Low | {D4.6}="Yes"
T37;167;0 | Consenting | Update Land & Consents Strategy and associated Commitments to consider consultation with National Nature Reserve Managing Body due to potential impact on the Reserve i | D4.7 | Phase 2-3 | Client | [7 empty] | 2021 | 1¦Low | {D4.7}="Yes"
T38;150;0 | Consenting | Update Land & Consents Strategy and associated Commitments to consider consultation with AONB Conservation Board due to potential impact on the AONB i | D4.5 | Phase 2-3 | Client | [7 empty] | 2022 | 1¦Low | {D4.5}="Yes"
T39;167;0 | Consenting | Update Land & Consents Strategy and associated Commitments to consider Habitats Regulations Assessment (HRA Screening) due to potential impact on SAC/SPA/Ramsar site i | D4.2, D4.3, D4.4 | Phase 2-3 | Client | [7 empty] | 2023 | 1¦Low | {D4.2¦D4.3¦D4.4}="Yes"
T40;154;0 | Consenting | Update Land & Consents Strategy and associated Commitments to consider consultation with Local Authority due to potential impact on Local Nature Reserve i | D4.8 | Phase 2-3 | Client | [7 empty] | 2024 | 1¦Low | {D4.8}="Yes"
T41;150;0 | Consenting | Update Land & Consents Strategy and associated Commitments to consider consultation with Local Authority due to potential impact on Ancient Woodland i | D5 | Phase 2-3 | Client | [7 empty] | 2025 | 1¦Low | {D5}="Yes"
T43;168;170 | Net Gain | Demonstrate a positive impact on biodiversity (this may be through the biodiversity metric) as part of the PEA scope of works (preferable) or as a standalone activity i ! Mandated under NR/L2/ENV/015, Section 6.1 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | A1, P2, S1, S2, S3, S4, S5, S6, S7, S8, S9, S10, S11, S12, S13, S14, S15, S16, S17, S18, S19, S20, S1, S2, S3, S4, S5, S6, S7, S8, S9, S10, S11, S12, S13, S14, S15, S16, S17, S18, S19, S20 | Phase 2-3 | Client / Designer | [7 empty] | 2026 | 1¦Low | [{A1}="Yes"¦¦VLOOKUP({P2},tblProjectValues,2,False)>1]&&[{S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Yes"¦¦{S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Maybe"]
T44;191;0 | Net Gain | Assess opportunity to integrate green/blue infrastructure principles into design options (e.g. green wall, green roof, vegetated retaining wall and other nature-based engineering solutions) i | S1, S2, S3, S4, S5, S6, S7, S8, S9, S10, S11, S12, S13, S14, S15, S16, S17, S18, S19, S20, S1, S2, S3, S4, S5, S6, S7, S8, S9, S10, S11, S12, S13, S14, S15, S16, S17, S18, S19, S20 | Phase 2-3 | Designer / Principal Contractor | [7 empty] | 2027 | 1¦Low | {S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Yes"¦¦{S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Maybe"
T45;102;104 | Net Gain | Secure budget and resources to deliver Biodiversity Net Gain, including long term habitat management i ! Apply the Biodiversity Mitigation Strategy ! | S1, S2, S3, S4, S5, S6, S7, S8, S9, S10, S11, S12, S13, S14, S15, S16, S17, S18, S19, S20, S1, S2, S3, S4, S5, S6, S7, S8, S9, S10, S11, S12, S13, S14, S15, S16, S17, S18, S19, S20 | Phase 2-3 | Client | [7 empty] | 2028 | 1¦Low | [{S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Yes"¦¦{S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Maybe"]
Level 1 Template | Contaminated Land | [11 empty] | 3000 | 1¦Low | {D8}="Yes"&&[{D9¦D10}="Yes"];{D8¦D10}="Yes";True | Env
T46;143;145 |  | Commission Preliminary Risk Assessment (PRA) based on a desktop study and site walkover to develop a Source-Pathway-Receptor Conceptual Model i ! Mandated under NR/L2/ENV/015, Section 6.2 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | S4, S5, S6, S7, S8, S11, S12, S13, S16, S4, S5, S6, S7, S8, S11, S12, S13, S16 | Phase 2-3 | Client / Designer | [7 empty] | 3001 | 1¦Low | {S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Yes"¦¦{S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Maybe"
T47;117;119 |  | Include adequate sampling and chemical testing into Ground Investigation (GI) scope of works based on PRA findings. i ! Waste Acceptance Criteria (WAC) Testing not suitable for land contamination assessment ! | S3, S3, S4, S5, S6, S7, S8, S11, S12, S13, S16, S4, S5, S6, S7, S8, S11, S12, S13, S16 | Phase 2-3 | Client / Designer | [7 empty] | 3002 | 1¦Low | [{S3}="Yes"¦¦{S3}="Maybe"]&&[{S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Yes"¦¦{S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Maybe"]
T48;224;226 |  | Apply Network Rail Standard NR/L3/ENV/044 to assess risk of track bed contamination (including desktop study and site walkover) and determine the need for sampling and chemical testing during track bed investigation (TBI). i ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | S9, S10, S9, S10 | Phase 2-3 | Designer / Principal Contractor | [7 empty] | 3003 | 1¦Low | {S9¦S10}="Yes"¦¦{S9¦S10}="Maybe"
T50;99;0 |  | Commission further site investigations if required based on findings and recommendations from PRA i | S4, S5, S6, S7, S8, S11, S12, S13, S16, S4, S5, S6, S7, S8, S11, S12, S13, S16 | Phase 2-3 | Client / Principal Contractor | [7 empty] | 3004 | 1¦Low | {S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Yes"¦¦{S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Maybe"
T51;97;0 |  | Commission a Piling Risk Assessment to prevent opening a pollution pathway into the groundwater i | A13 | Phase 2-3 | Principal Contractor | [7 empty] | 3005 | 1¦Low | {A13}="Yes"
Level 1 Template | Emissions to Air | [11 empty] | 4000 | 1¦Low | [{D11}="Yes"]&&[{A5¦A6}="Yes"];{D11¦A5¦A6}="Yes";True | Env
T52;79;81 |  | Commission Operational Air Quality Assessment and liaise with Local Authority i ! Mandated under NR/L2/ENV/015, Section 6.3 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | D11, A5 | Phase 2-3 | Client | [7 empty] | 4001 | 1¦Low | {D11&A5}="Yes"
T53;47;49 |  | Undertake Construction Air Quality Assessment i ! Mandated under NR/L2/ENV/015, Section 6.3 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | D11, A6 | Phase 2-3 | Principal Contractor | [7 empty] | 4002 | 1¦Low | {D11&A6}="Yes"
T54;190;0 |  | Specify low emissions vehicles, plant and equipment (Euro 6 engine, hybrid/solar generator, Non-Road Mobile Machinery (NRMM) requirements in London, etc.) as part of Contract & Procurement i | A6 | Phase 2-3 | Client / Principal Contractor | [7 empty] | 4003 | 1¦Low | {A6}="Yes"
T56;92;0 |  | Consider air insulated or non-SF6 gas insulated transformer into business case development i | S13, S13 | Phase 1 | Client / Designer | [7 empty] | 4004 | 1¦Low | {S13}="Yes"¦¦{S13}="Maybe"
Level 1 Template | Noise and Vibration | [11 empty] | 5000 | 1¦Low | [{D12¦D17}="Yes"]&&[{A7¦A8¦A9¦A10}="Yes"];{D12¦D17¦A7¦A8¦A9¦A10}="Yes";True | Env
T57;134;136 |  | Commission Operational Noise & Vibration Impact Assessment for compliance with Noise Insulation Regs and Railway Act (due diligence) i ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | S10, S11, S10, S11, A7, D17 | Phase 2-3 | Client | [7 empty] | 5001 | 1¦Low | [{S10¦S11}="Yes"¦¦{S10¦S11}="Maybe"]¦¦[{A7&D17}="Yes"]
T58;181;0 |  | Liaise with Local Authority as well as TOC/FOC to identify and agree mitigation measures based on findings and recommendations from Operational Noise & Vibration Impact Assessment i | S10, S11, S10, S11, A7, D17 | Phase 2 | Client | [7 empty] | 5002 | 1¦Low | [{S10¦S11}="Yes"¦¦{S10¦S11}="Maybe"]¦¦[{A7&D17}="Yes"]
T59;130;0 |  | Assess potential adverse Noise Impact of Public Address and/or Warning system on nearby residents and design mitigation measures i | A9, A10, D17, D17.1 | Phase 2 | Designer | [7 empty] | 5003 | 1¦Low | [{A9¦A10}="Yes"]&&[{D17¦D17.1}="Yes"]
T60;81;83 |  | Undertake Construction Noise & Vibration Impact Assessment as per NR/L2/ENV/121 i ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | A8, D17, D17.1 | Phase 2 | Principal Contractor | [7 empty] | 5004 | 1¦Low | [{A8}="Yes"]&&[{D17¦D17.1}="Yes"]
T61;209;211 |  | Liaise with Local Authority and apply for Section 61 Consent based on Construction Noise & Vibration Impact Assessment findings and recommendations (e.g. when noisy works at unsociable hours are unavoidable) i ! Mandated under NR/L2/ENV/015, Section 6.6 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | A8, D17, D17.1 | Phase 2 | Principal Contractor | [7 empty] | 5005 | 1¦Low | [{A8}="Yes"]&&[{D17¦D17.1}="Yes"]
T63;229;0 |  | Identify Best Practicable Means (BPM) such as white noise reversing alarms, battery-powered plant and equipment, planning noisy works outside inconsiderate hours, etc. to minimise impact As Low as Reasonably Practicable (ALARP) i | A8, D17, D17.1 | Phase 2-3 | Principal Contractor | [7 empty] | 5006 | 1¦Low | [{A8}="Yes"]&&[{D17¦D17.1}="Yes"]
Level 1 Template | Dust, odour and lighting | [11 empty] | 6000 | 1¦Low | ;{A11}="Yes";True | Env
T64;225;0 |  | Undertake lighting impact assessment in line with NR guidance note 'Minimising impact of artificial lighting on people and wildlife' and include adequate mitigation measures into design based on findings and recommendations i | A11, S19, D17, D2 | Phase 2-3 | Designer | [7 empty] | 6001 | 1¦Low | [{A11¦S19}="Yes"]&&[{D17¦D2}="Yes"]
T162;102;0 |  | Ensure design includes measures to reduce dust and odour to As Low as Reasonably Practicable (ALARP) i | A44, A44 | [9 empty] | 6002 | 1¦Low | {A44}="Yes"¦¦{A44}="Don't Know"
Level 1 Template | Pollution of land / water | [11 empty] | 7000 | 1¦Low | [{D9¦D10}="Yes"]&&[{A2¦A3¦A4¦A12}="Yes"];{D9¦D10¦A2¦A3¦A4¦A12}="Yes";True | Env
T65;133;0 |  | Provide containment in accordance with The Control of Pollution (Oil Storage) Regulations 2001, or equivalent in Wales and Scotland i | A2 | Phase 2-3 | Designer/Principal Contractor | [7 empty] | 7001 | 1¦Low | {A2}="Yes"
T66;140;0 |  | Apply hierarchy of control for hazardous substances through elimination and substitution for less hazardous to health and the environment i | A3 | Phase 3 | Principal Contractor | [7 empty] | 7002 | 1¦Low | {A3}="Yes"
T67;38;0 |  | Develop Incident Response Plan (IRP) i | N1, S21, S22 | Phase 2-3 | Designer / Principal Contractor | [7 empty] | 7003 | 1¦Low | {N1}="No"&&{S21&S22}<>"Yes"
T68;106;0 |  | Avoid spraying of herbicide near watercourses and apply for permission from the Regulator if unavoidable i | S1, S1, D9, A3, A3 | Phase 3 | Principal Contractor | [7 empty] | 7004 | 1¦Low | {S1}="Yes"¦¦{S1}="Maybe"&&{D9}="Yes"&&{A3}="Yes"¦¦{A3}="Don’t' Know"
T69;50;0 |  | Complete ballast de-icer risk assessment process i | A4 | Phase 3 | Principal Contractor | [7 empty] | 7005 | 1¦Low | {A4}="Yes"
T70;73;0 |  | Interrogate the Asbestos Risk Management System (ARMS) and PCB Register i | A19 | Phase 1 - 2 | Client | [7 empty] | 7006 | 1¦Low | {A19}="Yes"
T71;176;0 |  | Update Land & Consents Strategy and associated Commitments to consider water discharge permit, land drainage consent for discharge and and/or trade effluent discharge consent i | S8, S8, A12 | Phase 2 -3 | Client | [7 empty] | 7007 | 1¦Low | [{S8}="Yes"¦¦{S8}="Maybe"]¦¦[{A12}="Yes"]
Level 1 Template | Energy and Carbon | [11 empty] | 8000 | 1¦Low | {A17¦S4¦S5}="Yes";{A14¦A15}="Yes";True | Env
T72;68;70 | Whole life carbon | Undertake Whole Life Carbon Assessment using the Rail Carbon Tool i ! Mandated under NR/L2/ENV/015, Section 6.4.2 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | N1, S21, S22 | Phase 2-3 | Designer / Principal Contractor | [7 empty] | 8001 | 1¦Low | [{N1}="No"&&{S21&S22}<>"Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>3
T73;156;158 | Energy and operational carbon | Undertake Operational Energy Assessment using an industry approved methodology such as the Chartered Institute of Building Services Engineers (CIBSE) TM54 i ! Mandated under NR/L2/ENV/015, Section 6.4.3 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | S5, A43 | Phase 1-2 | Designer | [7 empty] | 8002 | 1¦Low | [{S5}="Yes"¦¦{A43}="No"]&&VLOOKUP({P2},tblProjectValues,2,False)>3
T76;59;0 | Low environmental impact products | Specify low carbon troughing products and/or power cables i | S16, S20 | Phase 2-3 | Designer / Principal Contractor | [7 empty] | 8003 | 1¦Low | {S16¦S20}="Yes"
T78;106;0 | Energy and operational carbon | Integrate energy-efficient solutions into buildings and structures' design (PV, LED lighting, GHP, etc.) i | S4, S5, S4, S5 | Phase 2-3 | Designer | [7 empty] | 8004 | 1¦Low | {S4¦S5}="Yes"¦¦{S4¦S5}="Maybe"
T79;156;0 | Energy and operational carbon | Integrate energy-efficient solutions (e.g. solar panel, forced-air temperature control instead of Air Con, LED lighting, etc.) to power lineside equipment i | A14 | Phase 2 | Designer | [7 empty] | 8005 | 1¦Low | {A14}="Yes"
T80;82;0 | Energy and operational carbon | Investigate DNO supply and electricity meters installation ahead of construction i | A15 | Phase 2 | Client / Principal Contractor | [7 empty] | 8006 | 1¦Low | {A15}="Yes"
T81;201;0 | Energy and operational carbon | Specify renewable energy power and energy efficient technologies where technologies exist (e.g. battery power, solar power LED technology, etc.) as part of Contract & Procurement to reduce emissions. i | A15 | Phase 2 | Client / Principal Contractor | [7 empty] | 8007 | 1¦Low | {A15}="Yes"
T171;58;0 | Energy and operational carbon | Contact local Energy and Carbon team for further support i | D31 | [9 empty] | 8008 | 1¦Low | {D31}="No"
Level 1 Template | Materials - Responsible Sourcing | [11 empty] | 9000 | 1¦Low | {A16¦A17}="Yes";{S2¦A18}="Yes";True | Env
T85;113;115 | Concrete and aggregates | Specify responsibly sourced concrete and/or aggregates (e.g. BES6001 certification) into Contract & Procurement i ! Mandated under NR/L2/ENV/015, Section 6.5.2 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | A16, A17 | Phase 2 | Client / Principal Contractor | [7 empty] | 9001 | 1¦Low | [{A16¦A17}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>3
T86;94;96 | Responsibly sourced timber | Specify responsibly sourced timber (e.g. FSC/PEFC certification) into Contract & Procurement i ! Mandated under NR/L2/ENV/015, Section 6.5.2.3 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | A18 | Phase 2 | Client / Principal Contractor | [7 empty] | 9002 | 1¦Low | {A18}="Yes"
T87;89;0 |  | Specify no single use plastic (e.g. plastic-free packaging) into Contract & Procurement i | N1, S21, S22 | Phase 2 | Client / Principal Contractor | [7 empty] | 9003 | 1¦Low | {N1}="No"&&{S21&S22}<>"Yes"
T88;103;0 |  | Consider rail and river networks as alternatives to road transport for large quantities of materials i | A16, A17 | Phase 2 | Client / Principal Contractor | [7 empty] | 9004 | 1¦Low | [{A16¦A17}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>3
Level 1 Template | Circular economy | [11 empty] | 10000 | 1¦Low | ;;True | Env
T90;155;157 |  | Undertake Resource Efficiency Assessment/ Workshop to minimise materials need, prevent waste and maximise reuse through LEAN design and value engineering i ! Mandated under NR/L2/ENV/015, Section 6.5.1 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | A19, A20, A21 | Phase 1-2 | Designer / Principal Contractor | [7 empty] | 10001 | 1¦Low | [{A19¦A20¦A21}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>=6
Level 1 Template | Waste | [11 empty] | 11000 | 1¦Low | {A20¦A21}="Yes";{A19}="Yes";True | Env
T92;113;115 |  | Apply Network Rail Standard NR/L3/ENV/044 for track bed waste classification by Route Services Environment Team i ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | S9, S10, S9, S10 | Phase 2-3 | Designer / Principal Contractor | [7 empty] | 11001 | 1¦Low | {S9¦S10}="Yes"¦¦{S9¦S10}="Maybe"
T93;206;208 |  | Undertake waste classification prior disposal in accordance with the EA technical guidance WM3 (including representative sampling and chemical testing for mirror haz/non haz waste e.g. excavated material) i ! Waste Acceptance Criteria (WAC) testing is NOT suitable for waste classification ! | N1, S21, S22 | Phase 3 | Principal Contractor | [7 empty] | 11002 | 1¦Low | {N1}="No"&&{S21&S22}<>"Yes"
T94;330;0 |  | Maximise waste avoidance and reuse using: - SurPlus - Obtain or transfer railway assets - Quality Protocol - Produce aggregates from inert waste - CLAIRE Register of Materials - Look for Donor and/or Receiver Sites - Waste Exemptions - Consult the EA Public Register for sites with U1 Exemption (Reuse of Waste in Construction) i | A19, A20, A21 | Phase 2-3 | Designer / Principal Contractor | [7 empty] | 11003 | 1¦Low | {A19¦A20¦A21}="Yes"
T95;168;0 |  | Consider including the local heritage railway into the redundant asset process to give them the opportunity to bid for assets that could benefit their infrastructure. i | S9, A19, D16 | Phase 2-3 | Client / Principal Contractor | [7 empty] | 11004 | 1¦Low | {S9&A19&D16}="Yes"
T96;196;0 |  | Consider alternative Invasive Non-Native Species (e.g. Japanese Knotweed) soil treatment methods allowing reuse of excavated material on site or off-site disposal at the lower landfill tax rate. i | A20, D7 | Phase 2-3 | Designer / Principal Contractor | [7 empty] | 11005 | 1¦Low | {A20&D7}="Yes"
T97;111;0 | Polychlorinated bi-phenols | Manage insulating oil with potential traces of PCB in accordance with NR guidance note and disposal checklist i | S13, S13, A2, A19 | Phase 3 | Principal Contractor | [7 empty] | 11006 | 1¦Low | [{S13}="Yes"¦¦{S13}="Maybe"]&&[{A2¦A19}="Yes"]
T98;148;150 |  | Develop Site Waste Management Plan (SWMP) including waste avoidance and reduction measures as well as details of waste carriers and disposal sites i ! Mandated under NR/L2/ENV/015, Section 6.5.3.1 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | N1, S21, S22 | Phase 2-3 | Designer / Principal Contractor | [7 empty] | 11007 | 1¦Low | {N1}="No"&&{S21&S22}<>"Yes"
Level 1 Template | Weather Resilience & Climate Change Adaptation (WRCCA) | [11 empty] | 12000 | 1¦Low | [{D13¦D9}="Yes"]&&[{A28}="Yes"];{A28¦D13¦D9}="Yes";True | Env
T99;66;68 |  | Commission Weather Resilience & Climate Change Impact Assessment i ! Mandated under NR/L2/ENV/015, Section 6.11 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | D13, A28 | Phase 1--2 | Designer | [7 empty] | 12001 | 1¦Low | [{D13¦A28}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>3
T100;34;0 |  | Commission Flood Risk Assessment i | D13 | Phase 1-2 | Designer | [7 empty] | 12002 | 1¦Low | {D13}="Yes"
T102;204;0 |  | Update Land & Consents Strategy and associated Commitments to consider flood risk permit, land drainage consent and/or marine licence and/or Code of Practice for Works Affecting the Canal & River Trust. i | D9, D13 | Phase 2-3 | Client | [7 empty] | 12003 | 1¦Low | {D9¦D13}="Yes"
T103;110;0 |  | Integrate Sustainable Drainage Systems (SuDS) principles and climate change predictions into drainage design i | S8, S8, A27 | Phase 2-3 | Designer | [7 empty] | 12004 | 1¦Low | [{S8}="Yes"¦¦{S8}="Maybe"]¦¦[{A27}="Yes"]
Level 1 Template | Water | [11 empty] | 13000 | 1¦Low | {A25}="Yes";{A23¦A24}="Yes";True | Env
T104;107;0 |  | Update Land & Consents Strategy and associated Commitments to consider abstraction or impoundment licence i | A25 | Phase 2-3 | Client | [7 empty] | 13001 | 1¦Low | {A25}="Yes"
T105;49;0 |  | Integrate water-efficient solutions into design i | A24 | Phase 2-3 | Designer | [7 empty] | 13002 | 1¦Low | {A24}="Yes"
Level 1 Template | Sustainable Travel | [11 empty] | 14000 | 1¦Low | {A29}="Yes";{A30}="Yes";True | Env
T107;103;0 |  | Integrate multi-modal transport connections into Business Case (EV charging points, bike racks, etc.) i | A29 | Phase 1 | Client | [7 empty] | 14001 | 1¦Low | {A29}="Yes"
T108;183;0 |  | Liaise with Local Authority, local transport companies and local transport action groups (including cycling) for better transport integration as part of Stakeholders Engagement Plan i | A29 | Phase 1 | Client | [7 empty] | 14002 | 1¦Low | {A29}="Yes"
T109;200;0 |  | Develop Green Travel Plan for the workforce (e.g. park & ride, car sharing platform, etc.) to minimise carbon emissions, air pollution and nuisance to the local community (traffic, road noise, etc.) i | A30 | Phase 3 | Principal Contractor | [7 empty] | 14003 | 1¦Low | {A30}="Yes"
Level 1 Template | Being a caring neighbour | [11 empty] | 15000 | 1¦Low | {D17¦D23}="Yes";{D17.1}="Yes";True | Soc
T111;238;0 |  | Liaise with Maintenance Protection Coordinator and Communications Manager for obtaining local knowledge on Network Rail relationship with local stakeholders (including Member of Parliament) and inclusion into Stakeholder Engagement Plan i | D17, D17.1, D23 | Phase 1 | Client | [7 empty] | 15001 | 1¦Low | {D17¦D17.1¦D23}="Yes"
T112;74;0 |  | Include sensitive/vulnerable receptors into Stakeholders Engagement Plan i | D18 | Phase 1 | Client | [7 empty] | 15002 | 1¦Low | {D18}="Yes"
T113;69;0 |  | Assess visual impact of planned asset/structure on nearby residents i | S12, S12, D17 | Phase 2 | Designer | [7 empty] | 15003 | 1¦Low | [[{S12}="Yes"¦¦{S12}="Maybe"]¦¦{A31}="Yes"]&&[{D17}="Yes"]
T114;133;0 |  | Notify the public in advance of planned noisy works and/or vegetation management activities (e.g. letter drop, drop-in event, etc.) i | A8, S1, D17, D17.1 | Phase 2 | Client / Principal Contractor | [7 empty] | 15004 | 1¦Low | [{A8¦S1}="Yes"]&&[{D17¦D17.1}="Yes"]
Level 1 Template | Connecting communities with the environment | [11 empty] | 16000 | 1¦Low | {S1}="Yes"&&{D19¦D17}="Yes";{S1}="Yes"&&{D17¦D17.1¦A34}="Yes";True | Soc
T116;261;0 |  | Engage with local communities through nature conservation initiatives (e.g. creating bug hotels with local school, building planters on platform with the Friends of the station, supporting local nature conservation group with volunteering or donations, etc.) i | A1, A35, S1, A34, D19, D17, S1, A34, D19, D17 | Phase 2-3 | Designer/Principal Contractor | [7 empty] | 16001 | 1¦Low | [{A1¦A35}="Yes"]¦¦[{S1}="Yes"&&{A34¦D19¦D17}="Yes"]¦¦[{S1}="Maybe"&&{A34¦D19¦D17}="Yes"]
T164;61;0 |  | Consider the design impact of visually prominent structures i | A40 | [9 empty] | 16002 | 1¦Low | {A40}="Yes"
Level 1 Template | Making rail a great experience | [11 empty] | 17000 | 1¦Low | {D17&A34}="Yes";{D17¦A34}="Yes";True | Soc
T149;175;0 |  | Integrate Network Rail Principles of Good Design into project development, supported by the local Design Champion nominated by Technical Authority (Buildings & Architecture) i | A34 | Phase 1 - 2 | Client | [7 empty] | 17001 | 1¦Low | {A34}="Yes"
T117;106;0 |  | Liaise with station management (TOC or NR) and local users group as part of Stakeholders Engagement Plan i | A34 | Phase 2-3 | Client | [7 empty] | 17002 | 1¦Low | {A34}="Yes"
T118;140;0 |  | Engage with Community Rail Partnership/Station adoption group as part of Stakeholders Engagement Plan when modifying platforms or stations i | A34, D17 | Phase 2-3 | Client | [7 empty] | 17003 | 1¦Low | {A34&D17}="Yes"
T119;80;0 |  | Support Community Rail Partnership/Station adoption group through volunteering i | D17 | Phase 3 | Client / Principal Contractor | [7 empty] | 17004 | 1¦Low | {D17}="Yes"
Level 1 Template | Creating engaged employees and positive industry partnerships | [11 empty] | 18000 | 1¦Low | {D20¦D21¦D22¦D26}="Yes";{D16¦D19¦D17}="Yes";True | Soc
T120;86;0 |  | Undertake Social Value Workshop based on the Common Social Industry Framework (CSIF) i | D16, D19, D20, D21, D22, D17, D26, P2 | Phase 2-3 | Client | [7 empty] | 18001 | 1¦Low | [{D16¦D19¦D20¦D21¦D22¦D17¦D26}="Yes"]&&[{P2}=">£50m"]
T121;292;0 |  | Build partnerships with local parish/community/town council, local charities and/or local schools through volunteering and community engagement activities (e.g. STEM) in collaboration with industry partners (e.g. TOC, NR suppliers, NR business units) as part of Stakeholders Engagement Plan i | D16, D19, D20, D21, D22, D17, D26, P2 | Phase 2--3 | Client | [7 empty] | 18002 | 1¦Low | [{D16¦D19¦D20¦D21¦D22¦D17¦D26}="Yes"]&&[{P2}=">£50m"]
Level 1 Template | Inspiring tomorrow’s workforce | [11 empty] | 19000 | 1¦Low | [{D19}="Yes"]&&[{P2}=">£50m"];[{D19}="Yes"]&&[{P2}="£20m-£50m"];True | Soc
T122;157;0 |  | Stakeholder Engagement Plan to include promoting careers in the rail industry through schools visits, careers fairs, work placements and/or apprenticeships i | D19 | Phase 2--3 | Client | [7 empty] | 19001 | 1¦Low | {D19}="Yes"
T165;61;0 |  | Document the requirements and any associated plans/controls i | A45 | [9 empty] | 19002 | 1¦Low | {A45}="Yes"
T166;99;0 |  | Consider providing safety messaging and early engagement (e.g. STEM, careers talks) interventions i | A41 | [9 empty] | 19003 | 1¦Low | {A41}="Yes"
Level 1 Template | Keeping Communities safe | [11 empty] | 20000 | 1¦Low | {D25¦S12¦S17}="Yes";{S18}="Yes";True | Soc
T147;153;0 |  | Liaise with Community Safety Manager (for Route Insight Assessment) and the Suicide Prevention Programme (for Priority Areas) to gather local knowledge i | D25, S12, S17, S18, S12, S17, S18 | Phase 102 | Client | [7 empty] | 20001 | 1¦Low | {D25¦S12¦S17¦S18}="Yes"¦¦{S12¦S17¦S18}="Maybe"
T148;62;0 |  | Liaise with Level Crossing Manager to gather local knowledge i | S17, S18 | Phase 1-2 | Client | [7 empty] | 20002 | 1¦Low | {S17¦S18}="Yes"
T123;37;0 |  | Minimise risk of trespass by design i | D25, S12, S17, S18, S12, S17, S18 | Phase 2 | Designer | [7 empty] | 20003 | 1¦Low | [{D25}="Yes"]¦¦[{S12¦S17¦S18}="Yes"¦¦{S12¦S17¦S18}="Maybe"]
T124;34;0 |  | Launch Community Safety campaign i | D25, S12, S17, S18, S12, S17, S18 | Phase 2--3 | Client | [7 empty] | 20004 | 1¦Low | [{D25}="Yes"]¦¦[{S12¦S17¦S18}="Yes"¦¦{S12¦S17¦S18}="Maybe"]
Level 1 Template | Making travel accessible and inclusive | [11 empty] | 21000 | 1¦Low | {A32¦A33}="Yes";{D17¦A34}="Yes";True | Soc
T125;121;123 |  | Undertake and update Diversity Impact Assessment (DIA) at each PACE stage and take actions to mitigate negative impacts i ! Mandated as a PACE Product ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | S5, S17, S18, A32, A33, A42, A42 | Phase 1-4 | Client | [7 empty] | 21001 | 1¦Low | [{S5¦S17¦S18¦A32¦A33¦A42}="Yes"¦¦{A42}="Don't Know"]
Level 1 Template | Respecting cultural heritage and rail history | [11 empty] | 22000 | 1¦Low | {D15.1¦D15.2¦D15.3¦D15.4}="Yes";{D16}="Yes";True | Soc
T126;48;0 |  | Minimise impact on cultural heritage by design i | D15.1, D15.2, D15.3, D15.4 | Phase 2 | Designer | [7 empty] | 22001 | 1¦Low | {D15.1¦D15.2¦D15.3¦D15.4}="Yes"
T127;146;148 |  | Update Land & Consents Strategy and associated Commitments to consider Cultural Heritage Impact Assessment and consultation with Local Authority i ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | D15.1, D15.2, D15.3, D15.4 | Phase 2 | Client | [7 empty] | 22002 | 1¦Low | {D15.1¦D15.2¦D15.3¦D15.4}="Yes"
T128;72;74 |  | Undertake Landscape & Visual Impact Assessment (AONB or National Park) i ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | S12, S12, D4.5, D4.6 | Phase 2 | Client / Designer | [7 empty] | 22003 | 1¦Low | [[{S12}="Yes"¦¦{S12}="Maybe"]¦¦{A31}="Yes"]&&[{D4.5¦D4.6}="Yes"]
T129;192;0 |  | Contribute to local heritage railway through volunteering, by providing technical support (e.g. design, project management, etc.) and/or offering the opportunity to bid for redundant assets. i | D16 | Phase 3 | Client / Principal Contractor | [7 empty] | 22004 | 1¦Low | {D16}="Yes"
T167;33;0 |  | Undertake a heritage assessment i | D27 | [9 empty] | 22005 | 1¦Low | {D27}="Yes"
Level 1 Template | Supporting Britain’s economic development | [11 empty] | 23000 | 1¦Low | {D26}="Yes";{A30}="Yes";True | Soc
T130;107;0 |  | Consider socio-economic landscape into Project Business Case development and Stakeholders Engagement Plan i | D26 | Phase 1 | Client | [7 empty] | 23001 | 1¦Low | {D26}="Yes"
T131;42;0 |  | Recruit workforce locally where possible i | A30, D26 | Phase 3 | Principal Contractor | [7 empty] | 23002 | 1¦Low | [{A30¦D26}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>=4
T132;79;0 |  | Procure goods, materials and services locally and/or from SMEs where possible i | A17, D26 | Phase 3 | Principal Contractor | [7 empty] | 23003 | 1¦Low | [{A17¦D26}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>=4
T169;134;0 |  | Consider opportunities to utilise NR procurement processes that support SMEs, local, VCSE business groups, and/or local communities. i | D29, D29 | Phase 3 | [8 empty] | 23004 | 1¦Low | {D29}="Yes"¦¦{D29}="Don't Know"
Level 1 Template | OTM Design / Build / Refurbishment | [11 empty] | 24000 | 0¦N/A | ;; | N/A
T133;159;0 |  | Undertake Resource Efficiency Workshop taking into consideration the whole life of the asset including construction, maintenance, repairs and decommissioning i | S21 | Phase 1-2 | Supplier | [7 empty] | 24001 | 0¦N/A | {S21}="Yes"
T134;233;0 |  | Integrate findings and recommendations from circular economy workshop into Business Case/Option Selection/Outline Design/Detailed Design/Construction e.g. reusability and recyclability of parts and components across a range of OTMs i | S21 | Phase 1-2 | Client / Supplier | [7 empty] | 24002 | 0¦N/A | {S21}="Yes"
T135;68;0 |  | Undertake Whole Life Carbon Assessment using the Rail Carbon Tool i | S21 | Phase 1-2 | Supplier | [7 empty] | 24003 | 0¦N/A | {S21}="Yes"
T136;246;0 |  | Integrate findings and recommendations from capital carbon assessment into Business Case/Option Selection/Outline Design/Detailed Design/Construction e.g. alternative low carbon materials, materials with high recycled content, LEAN design, etc. i | S21 | Phase 2-3 | Client / Supplier | [7 empty] | 24004 | 0¦N/A | {S21}="Yes"
T137;50;0 |  | Undertake 'in-use' Operational Energy assessment i | A36 | Phase 2 | Supplier | [7 empty] | 24005 | 0¦N/A | {A36}="Yes"
T138;331;0 |  | Integrate findings and recommendations from 'in-use' operational energy assessment into Business Case/Option Selection/Outline Design/Detailed Design/Construction e.g. alternative renewable power sources, 'best in class' diesel engine technology, energy efficiency solutions such as reduced weight and improved aerodynamics, etc. i | A36 | Phase 2 | Client / Supplier | [7 empty] | 24006 | 0¦N/A | {A36}="Yes"
T139;102;0 |  | Design for high reliability to prevent pollution incidents with a focus on hydraulic and fuels lines i | S21 | Phase 2 | Supplier | [7 empty] | 24007 | 0¦N/A | {S21}="Yes"
T140;102;0 |  | Investigate alternatives to hydrocarbon-based hydraulic or lubricating systems (e.g. compressed air) i | A37 | Phase 2 | Supplier | [7 empty] | 24008 | 0¦N/A | {A37}="Yes"
T141;69;0 |  | Develop Decommissioning plan in accordance with the waste hierarchy i | S22 | Phase 2 | Supplier | [7 empty] | 24009 | 0¦N/A | {S22}="Yes"
T142;39;0 |  | Undertake Water Efficiency assessment i | A38 | Phase 2 | Supplier | [7 empty] | 24010 | 0¦N/A | {A38}="Yes"
T143;240;0 |  | Integrate findings and recommendations from water efficiency assessment into Business Case/Option Selection/Outline Design/Detailed Design/Construction e.g. alternative waterless solutions, water reuse, water-efficient technologies, etc. i | A38 | Phase 2 | Client / Supplier | [7 empty] | 24011 | 0¦N/A | {A38}="Yes"
T144;40;0 |  | Undertake Operational Noise assessment i | A39 | Phase 2 | Supplier | [7 empty] | 24012 | 0¦N/A | {A39}="Yes"
T145;227;0 |  | Integrate findings and recommendations from operational noise assessment into Business Case/Option Selection/Outline Design/Detailed Design/Construction e.g. start-stop technology to present idling, acoustic containment, etc. i | A39 | Phase 1-2 | Client / Supplier | [7 empty] | 24013 | 0¦N/A | {A39}="Yes"
Compact View ON
Refresh Action List

## Initial Questions (hidden)
Evaluate Cell for long formulae (DO NOT DELETE):
FALSE
| Include action count on Action Plan? |  | Yes
| Dev Mode |  | No
| Ref | Sheet | Cell | Response | Previous Response | Question text
| P2 | 1. Project Info | E10 | Select from drop down list… |  | Estimated Project Value (Development, Design and Construction)
P-NEW1 | P4 | 1. Project Info | E6 | Select from drop down list… |  | Client Organisation
P-NEW2 | P5 | 1. Project Info | E13 | Select from drop down list... |  | Network Rail Region and Route
Rebuild Core Structures

## Framework (hidden)
|  | N1 | [Automated] No to ALL Project Scope activities = Non-Intrusive project | [22 empty] | Yes
|  | DK1 | [Automated] 'Don't Know' answers are present on the Project Activities tab | [22 empty] | No
|  | M1 | [Automated] 'Maybe' answers are present on the Project Scope tab | [22 empty] | No
|  | REFERENCING |  |  | QUESTIONS |  |  | [title];#[url];#[guidance] |  |  |  |  | ANSWER OPTIONS | [7 empty] | WHAT HAPPENS IF… S[{ref},{ref}]to show a question(s);H[{ref},{ref}]to hide a question;SET[{ref}]to set another question to the same value |  |  |  |  | Responses
| Old Ref | Ref | Section | Include/Filter | Question | Warning | Additional information | Data Source 1 | Data Source 2 | Data Source 3 | Data Source 4 | Data Source 5 | Type | Group | Default Option | Option 1 | Option 2 | Option 3 | Option 4 | Option 5 | Option 1 is selected? | Option 2 is selected? | Option 3 is selected? | Option 4 is selected? | Option 5 is selected?
|  | D0.1 | Project Location | Y | ELRs and mileages (from/to): | [7 empty] | Free text | [12 empty] | No
|  | D0.2 | Project Location | Y | Asset ID (if applicable): | [7 empty] | Free text | [12 empty] | No
|  | D0.3 | Project Location | Y | Nearest Town/City and/or Postcode: | [7 empty] | Free text | [12 empty] | No
|  | D0.4 | Project Location | Y | Local Planning Authority (District, Borough or City Council): |  |  | Magic;#http://magic.defra.gov.uk/MagicMap.aspx;#- Open Magic <br>- Expand 'Administrative Geographies' layer (without ticking the box) <br>- Expand 'Other Administrative Boundaries' layer (without ticking the box) <br>- Select 'Counties, Metropolitan Districts and Unitary Authorities (GB)' <br>- Identify area on the map using the 'i' button |  |  |  |  | Free text | [12 empty] | No
|  | D0.5 | Project Location | Y | Parish, Community or Town Council: |  |  | Magic;#http://magic.defra.gov.uk/MagicMap.aspx;#- Open Magic <br>- Expand 'Administrative Geographies' layer (without ticking the box) <br>- Expand 'Other Administrative Boundaries' layer (without ticking the box) <br>- Select 'Parishes' <br>- Identify area on the map using the 'i' button |  |  |  |  | Free text | [12 empty] | No
|  | D0.6 | Project Location | Y | Local Member of Parliament: |  |  | Find my MP;#https://members.parliament.uk/FindYourMP;#- Open UK Parliament webpage <br>- Search project location by postcode or location <br>- If unsure, use Magic to identify ' Parliamentary Constituencies' within 'Administrative Geographies' -> 'Other Administrative Boundaries' |  |  |  |  | Free text | [12 empty] | No
| NewQ | D0.7 | Project Location | Y | Is access to third party land required? | [7 empty] | Choice |  |  | Yes | No | [8 empty] | 0
| D1 | D1 | Biodiversity | Y | Are there records of ecology survey(s) covering the project area on Geo-RINM? | ! Absence of records on Geo-RINM does not confirm absence of previous surveys recorded locally! ! Preliminary Ecological Appraisals require re-validation after 24 months ! |  | Geo-RINM;#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28/#;#- Open Geo-RINM <br>- Select 'Sustainability' layer (Expand) <br>- Select 'Biodiversity' layer (Expand) <br>- Select 'Ecological Surveys Point' and 'Ecological Surveys Line' <br>- To obtain more details (if a record appears), right-click and select 'Find data on the map'. Results will appear on the left hand-side. |  |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D2a | D2 | Biodiversity | Y | Are there records of protected species within 1km of the project area? | ! Absence of records does not confirm absence of protected species ! |  | National Hazard Directory;#https://networkrail.sharepoint.com/sites/myconnect/ToolsandSites/Pages/ToolsandSites.aspx;#- Search for 'National Hazard Directory' on MyConnect <br>- Open National Hazard Directory <br>- Accept Terms and Conditions <br>- Select 'Custom Search' <br>- Enter ELR and mileages <br>- Select 'Advanced Custom Report (Optional)' <br>- Accept T&C's <br>- Select the following Hazards Codes: EE (Ecology & Landscape), ESH (Protected Animal Species), EST (Protected Plant Species) <br>- Select 'Check All' within 'Custom Report Columns' <br>- Run Report... | Geo-RINM;#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28/#;#- Open Geo-RINM <br>- Select 'Sustainability' layer (Expand) <br>- Select 'Biodiversity' layer (Expand) <br>- Select 'Protected Species Plant', 'Protected Species Animal', 'Protected Species Licences Point' and Protected Species Licences Line' <br>- To obtain more details (if a record appears), right-click and select 'Find data on the map'. Results will appear on the left hand-side. <br>- Measure distance using function available in the Tools ('Identify and Measure' tab) <br> <br><i><u>Note</u>: If the weblink is not working, go to MyConnect -> Key Links -> Tools & Sites -> Search for 'Geo-RINM' | Magic;#http://magic.defra.gov.uk/MagicMap.aspx;#- Open Magic <br>- Expand 'Habitat & Species' layer (without ticking the box) <br>- Expand 'Species' layer (without ticking the box) <br>- Select 'European Protected Species Licensing' and 'Great Crested Newts Pond Surveys 2017-2019' <br>- Identify features using the 'i' button <br>- Measure distances using the 'ruler' button <br> <br><i><u>Note</u>: European Protected Species Licensing data is only visible at 1:25000 scale or above |  |  | Choice |  |  | Yes | No |  |  |  | H[{D2.1}] | S[{D2.1}] |  |  |  | 0
Remove in the future? | D2b | D2.1 | Biodiversity |  | If No, within 2km? | [7 empty] | Choice |  |  | Yes | No | [8 empty] | 0
| D37a | D3 | Biodiversity | Y | Are any of the following statutory designated sites within 2km of the project area? |  |  | Geo-RINM;#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28/#;#- Open Geo-RINM <br>- Select 'Sustainability' layer (Expand) <br>- Select 'Biodiversity' layer (Expand) <br>- Select 'National Parks', 'Special Protection Areas', 'National Nature Reserves', 'Ramsar', 'Special Areas of Conservation' and 'SSSI' <br>- Identify features with a right-click and selecting 'Find data on the map'. Results will appear on the left hand-side. <br>- Measure distance using function available in the Tools ('Identify and Measure' tab) <br> <br>For Area of Outstanding Natural Beauty: <br>- Select 'Land Information' and 'Heritage' | Magic;#http://magic.defra.gov.uk/MagicMap.aspx;#- Open Magic <br>- Expand 'Designations' layer (without ticking the box) <br>- Expand 'Land-based Designations' layer (without ticking the box) <br>- Expand 'Statutory' (without ticking the box) <br>- Select 'Local Nature Reserves' as the only designation missing from Geo-RINM <br>- Identify features using the 'i' button <br>- Measure distances using the 'ruler' button |  |  |  | Heading | [7 empty] | S[{D4},{D4.1},{D4.2},{D4.3},{D4.4},{D4.5},{D4.6},{D4.7},{D4.8}];H[{D3.1}] | S[{D3.1}];H[{D4},{D4.1},{D4.1.1},{D4.1.1.1},{D4.2},{D4.3},{D4.4},{D4.5},{D4.6},{D4.7},{D4.8}] |  |  |  | 0
| D3 | D4.1 | Biodiversity | Y | Site of Special Scientific Interest (SSSI) | [7 empty] | Double Click | 1 | [6 empty] | S[{D4.1.1}] | H[{D4.1.1},{D4.1.1.1}] |  |  |  | 0
| D3a | D4.1.1 | Biodiversity |  | Is NR land included within the SSSI designation? |  |  | Register of SSSIs on NR land;#http://connectdocs/NetworkRail/Documents/Delivery/NetworkOperations/Infrastructure_Maintenance_Services/Environment/SSSIRegisterJan2013.xls;#- After identifying a SSSI near the project area using Geo-RINM, open the 'Register of SSSIs on NR Land' to confirm if the designation includes NR land. |  |  |  |  | Choice |  |  | Yes | No |  |  |  | S[{D4.1.1.1}] | H[{D4.1.1.1}] |  |  |  | 0
| D3b | D4.1.1.1 | Biodiversity |  | Is there an up to date Site Management Statement (SMS) in place? | Note: there is no SMS in Wales and Scotland: Answer 'No' by default |  | Site Management Statements (England only);#https://sddata.hub.networkrail.co.uk/Enviroment/Forms/AllItems.aspx?RootFolder=%2FEnviroment%2FSite%20Management%20Statements&FolderCTID=0x012000FB9F7BACE3C81643A83B95403574EB51&View=%7B4860448E%2D5285%2D40C4%2D97DB%2D1F16E4BF0E62%7D;#- If the SSSI designation includes NR land, look for the associated Site Management Statement |  |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D4 | D4.2 | Biodiversity | Y | Special Area of Conservation (SAC) | [7 empty] | Double Click | 1 | [11 empty] | 0
| D5 | D4.3 | Biodiversity | Y | Special Protection Area (SPA) | [7 empty] | Double Click | 1 | [11 empty] | 0
| D6 | D4.4 | Biodiversity | Y | Ramsar | [7 empty] | Double Click | 1 | [11 empty] | 0
| D7 | D4.5 | Biodiversity | Y | Area of Outstanding Natural Beauty (AONB) | [7 empty] | Double Click | 1 | [11 empty] | 0
| D8 | D4.6 | Biodiversity | Y | National Park | [7 empty] | Double Click | 1 | [11 empty] | 0
| D9 | D4.7 | Biodiversity | Y | National Nature Reserve | [7 empty] | Double Click | 1 | [11 empty] | 0
| D10 | D4.8 | Biodiversity | Y | Local Nature Reserve |  |  | find a LERC map;#https://www.alerc.org.uk/find-an-lerc-map.html | Planning Portal;#https://www.planningportal.co.uk/ |  |  |  | Double Click | 1 | [11 empty] | 0
| NewQ | D4.9 | Biodiversity | Y | Provide details of any other designations (non-statutory) identified: | [7 empty] | Free text | 1 | [11 empty] | No
| NewQ | D4.10 | Biodiversity | Y | None of the above | [7 empty] | Double Click | 1 | [11 empty] | 0
| D11 | D5 | Biodiversity | Y | Is there an Ancient Woodland Site near (<50m) or within the project area? |  |  | Magic (England);#http://magic.defra.gov.uk/MagicMap.aspx;#- Open Magic <br>- Expand 'Habitats and Species' layer (without ticking the box) <br>- Expand 'Woodland' layer (without ticking the box) <br>- Select 'Ancient Woodland' <br>- Identify features using the 'i' button <br>- Measure distances using the 'ruler' button | Lle Map (Wales);#http://lle.gov.wales/map;#- Open Lle Map <br>- Add 'Ancient Woodland Inventory 2011' layer <br>- Zoom in towards project area <br>- Select 'Legend' to identify feature <br>- Select 'Tools' to measure distances | Scotland's Environment Maps;#https://map.environment.gov.scot/sewebmap/;#- Open Scotland's environment Map <br>- Select 'Add Map Data Layers' <br>- Search for 'Ancient Woodland Inventory Scotland' <br>- Select 'Apply to Map' and close window <br>- Zoom in towards project area <br>- Display Legend to visualise the type of Ancient Woodland <br>- Click on the map to identify the feature <br>- Estimate distance using the map's scale |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D12 | D6 | Biodiversity | Y | Are there records of Tree Preservation Order (TPO) near (<50m) or within the project area? | ! Absence of records does not confirm absence of TPO ! |  | Geo-RINM;#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28/#;#- Open Geo-RINM <br>- Select 'Sustainability' layer (Expand) <br>- Select 'Biodiversity' layer (Expand) <br>- Select 'Tree Protection Orders' <br>- To obtain more details (if a record appears), right-click and select 'Find data on the map'. Results will appear on the left hand-side. <br>- Measure distance using function available in the Tools ('Identify and Measure' tab) <br> <br><i><u>Note</u>: Data is not exhaustive and up to date. The Local Authority TPO database (and Tree Officer) is the only reliable source of information. | National Hazard Directory;#https://networkrail.sharepoint.com/sites/myconnect/ToolsandSites/Pages/ToolsandSites.aspx;#- Search for 'National Hazard Directory' on MyConnect <br>- Open National Hazard Directory <br>- Accept Terms and Conditions <br>- Select 'Custom Search' <br>- Enter ELR and mileages <br>- Select 'Advanced Custom Report (Optional)' <br>- Accept T&C's <br>- Select the following Hazards Codes: EP (Preservation Order), EPR (Preserved Tree (TPO)) <br>- Select 'Check All' within 'Custom Report Columns' <br>- Run Report... <br> <br><i><u>Note</u>: Data is not exhaustive and up to date. The Local Authority TPO database (and Tree Officer) is the only reliable source of information. | find a LERC map;#https://www.alerc.org.uk/find-an-lerc-map.html | Planning Portal;#https://www.planningportal.co.uk/ |  | Choice |  |  | Yes | No | [8 empty] | 0
| D13 | D7 | Biodiversity | Y | Are there records of Japanese Knotweed, Giant Hogweed or Himalayan Balsam (Invasive Non-Native Species - INNS) near (<50m) or within the project area? | ! Absence of records does not confirm absence of INNS ! Note: Other non-native invasive plant species (e.g. Cotoneaster, Rhododendron) must be considered as part of a Preliminary Ecological Appraisal (PEA) |  | Geo-RINM;#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28/#;#- Open Geo-RINM <br>- Select 'Sustainability' layer (Expand) <br>- Select 'Biodiversity' layer (Expand) <br>- Select 'Invasive Non-Native Species (INNS) Plants' and 'Invasive Non-Native Species (INNS) Animals' <br>- To obtain more details (if a record appears), right-click and select 'Find data on the map'. Results will appear on the left hand-side. <br>- Measure distance using function available in the Tools ('Identify and Measure' tab) <br> <br><i>(u>Note</u>: Geo-RINM only provides records of Japanese Knotweed, Giant Hogweed and Himalayan Balsam as INNS plant species (gathered from the NBN Atlas database). The scope of the Preliminary Ecological Appraisal (PEA) should include the full list of INNS. | National Hazard Directory;#https://networkrail.sharepoint.com/sites/myconnect/ToolsandSites/Pages/ToolsandSites.aspx;#- Search for 'National Hazard Directory' on MyConnect <br>- Open National Hazard Directory <br>- Accept Terms and Conditions <br>- Select 'Custom Search' <br>- Enter ELR and mileages <br>- Select 'Advanced Custom Report (Optional)' <br>- Accept T&C's <br>- Select the following Hazards Codes: EKU (Invasive/Injurious Plants) <br>- Select 'Check All' within 'Custom Report Columns' <br>- Run Report... <br> <br><i><u>Note</u>: Data is not exhaustive. The scope of the Preliminary Ecological Appraisal (PEA) should include the full list of INNS. |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D14 | D8 | Contaminated Land | Y | Are there records of contaminated land and/or historic landfill (including landfill gases and past mining activities) near (<250m) or within the project area? | ! Absence of records does not confirm absence of contaminated land ! |  | Geo-RINM;#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28/#;#- Open Geo-RINM <br>- Select 'Sustainability' layer (Expand) <br>- Select 'Environment' layer (Expand) <br>- Select 'Contaminated Land' <br>- To obtain more details (if a record appears), right-click and select 'Find data on the map'. Results will appear on the left hand-side. <br>- Measure distance using function available in the Tools ('Identify and Measure' tab) <br> <br>- Run a similar search using the 'Mining' layer -> 'Mining Referral Layer' -> 'Mining Risk National', considering areas identified as potentially contaminated by historic mining activities and associated waste deposits | National Hazard Directory;#https://networkrail.sharepoint.com/sites/myconnect/ToolsandSites/Pages/ToolsandSites.aspx;#- Search for 'National Hazard Directory' on MyConnect <br>- Open National Hazard Directory <br>- Accept Terms and Conditions <br>- Select 'Custom Search' <br>- Enter ELR and mileages <br>- Select 'Advanced Custom Report (Optional)' <br>- Accept T&C's <br>- Select the following Hazards Codes: EK (Site Contamination), EKB (Asbestos Hazard), EKC (CIMAH Site), EKF (Landfill Gases), EKL (LPG Contamination), EKN (NIHHS Site), EKO (Other Contamination), EKS (Contaminated Track Bed - Toilet Waste) and EKW (Waste Disposal / Tipping) <br>- Select 'Check All' within 'Custom Report Columns' <br>- Run Report... | Groundsure Enviro Data Viewer;#https://groundsure.io/;#- Open Groundsure Enviro Data Viewer <br>- Search project location <br>- Open layers using symbol on the left hand side <br>- In the 'Mining' layer, select 'Mining Waste' and display 'Inventory of closed mining waste facilities' <br>- In the 'Landfill and waste' layer, select 'Landfill' and display both 'Authorised landfill' and 'Historic landfill' <br>- Click on the feature to obtain information <br>- Open measuring tool using symbol on the left hand side to obtain distance |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D15 | D9 | Hydrology and hydrogeology | Y | Is the project area within 10m of a sea, estuary, watercourse (main river or ordinary watercourse such as open drainage, brook, etc.) or other surface water body (pond, canal, lake, loch, reservoir, etc.)? |  |  | Geo-RINM;#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28/#;#- Open Geo-RINM <br>- Identify waterbodies and measure distance to project area using function available in the Tools ('Identify and Measure' tab) | Google Map;#https://www.google.com/maps;#- Open Google Map <br>- Identify waterbodies and measure distance to project area using function available through a right click on the map |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
Moved | D19 | D13 | Hydrology and hydrogeology | Y | Is the project area within or near a fluvial, coastal (i.e. Flood Zone 3) and/or surface water high flood risk area? |  |  | England & Wales (Coastal & River Flooding);#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28/;#- Open Geo-RINM <br>- Select 'Sustainability' layer (Expand) <br>- Select 'Environment Agency Flood Data' layer (Expand) <br>- Select 'Environment Agency Online Data Feed' layer <br>- Select 'Flood_Map_for_Planning_Rivers_and_Sea_Flood_Zone_3' <br>- Untick all the other layers under 'Environment Agency Flood Data' layer <br>- Identify if project area is affected by a Food Zone 3 | England & Wales (Surface Water Flooding);#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28#;#- Open Geo-RINM <br>- Select 'Sustainability' layer (Expand) <br>- Select 'Flood Risk' layer (Expand) <br>- Select 'Surface Water Flood Risk' layer <br>- Select 'Risk_of_Flooding_from_Surface_Water_Extent_3_3_percent_annual_chance' <br>- Untick all the other layers under 'Flood Risk' layer <br>- Identify if project area is affected by a High Risk of surface water flooding | Scotland (Coastal, River & Surface Water Flooding);#http://map.sepa.org.uk/floodmap/map.htm;#- Open SEPA Flood Maps <br>- Accept terms and conditions <br>- Hide Menu <br>- Identify if project area is affected by High Risk of flooding |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D16 | D10 | Hydrology and hydrogeology | Y | In the project area within a Source Protection Zone (SPZ) in England & Wales or Drinking Water Protection Area (Scotland)? | Note: Answer 'Yes' by default if project area in Scotland as the whole country is covered by Drinking Water Protection Areas for its Groundwater. |  | Magic (England);#http://magic.defra.gov.uk/MagicMap.aspx;#- Open Magic <br>- Expand 'Designations' layer (without ticking the box) <br>- Expand 'Land-based Designations' layer (without ticking the box) <br>- Expand 'Non-Statutory' (without ticking the box) <br>- Select 'Source Protection Zones merged (England)' | Groundsure Enviro Data Viewer (England);#https://groundsure.io/;#'- Open Groundsure Enviro Data Viewer <br>- Search project location <br>- Open layers using symbol on the left hand side <br>- In the 'Geology/Hydrogeology' layer, select 'Hydrogeology' and display 'Source Protection Zones (Merged)' | Lle Map (Wales);#http://lle.gov.wales/map;#- Open Lle Map <br>- Add 'Source Protection Zones (SPZ) merged' layer <br>- Zoom in towards project area | Scotland;#https://www.webarchive.org.uk/wayback/archive/20150221042820/http:/www.gov.scot/Topics/Environment/Water/17670/maps/gwsummary;#- Open Scottish Government website <br>- Select 'Drinking Water Protected Areas - Scotland River Basin District - Groundwater - summary map' showing that most of the country is covered by 'Groundwater Bodies Drinking Water Protected Areas' |  | Choice |  |  | Yes | No | [8 empty] | 0
| D17 | D11 | Emissions to Air | Y | Is the project area within an Air Quality Management Area (AQMA)? |  |  | Noise & Air Quality Viewer (England);#http://www.extrium.co.uk/noiseviewer.html;#- Open England Noise and Air Quality Viewer and 'Continue' <br>- Search project location <br>- Select 'AQMAs' and untick 'Lden' | Noise & Air Quality Viewer (Wales);#http://extrium.co.uk/walesnoiseviewer.html;#- Open Wales Noise and Air Quality Viewer and 'Continue' <br>- Search project location <br>- Select 'AQMAs' and untick 'Lden' | Air Quality in Scotland;#http://www.scottishairquality.scot/laqm/aqma;#- Open 'Air Quality in Scotland' website <br>- Select Local Authority(ies) associated with project area <br>- View Maps of AQMAs |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D18 | D12 | Noise & Vibration | Y | Is the project area within a Noise Management Area (Important Area or Priority Area) for Roads and/or Railways (England & Wales)? | Note: Answer 'No' by default if project area in Scotland as Noise Management Areas have not yet been defined. |  | Noise & Air Quality Viewer (England);#http://www.extrium.co.uk/noiseviewer.html;#- Open England Noise and Air Quality Viewer and 'Continue' <br>- Search project location <br>- Select 'IAs (Roads)' and 'IAs (Railways)' and untick 'Lden' | Noise & Air Quality Viewer (Wales);#http://extrium.co.uk/walesnoiseviewer.html;#- Open Wales Noise and Air Quality Viewer and 'Continue' <br>- Search project location <br>- Select 'Priority Area (Road)' and 'Priority Area (Railway)' and untick 'Lden' |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
|  | D27 | Respecting cultural heritage and rail history | Y | Will the project area include scheduled monuments, archaeological sites and deposits, or buildings of historical and architectural interest? |  |  | Geo-RINM;#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28#;#- Open Geo-RINM <br>- Select 'Land Information' layer (Expand) <br>- Select 'Heritage' layer (Expand) <br>- Search project area <br>- Identify features with a right-click and selecting 'Find data on the map'. Results will appear on the left hand-side. <br>- Measure distance using function available in the Tools ('Identify and Measure' tab) <br> <br><i><u>Note</u>: World Heritage Site, Registered Parks & Gardens and Registered Battlefields are not available on Geo-RINM. Consult Historic England/Wales/Scotland for these statutory designations. | Historic England;#https://historicengland.org.uk/listing/the-list/map-search?clearresults=True;#- Open Historic England Map <br>- Search project area <br>- Click on the feature to obtain information | Lle Map (Wales);#http://lle.gov.wales/map;#- Open Lle Map <br>- Add 'World Heritage Sites' layers <br>- Zoom in towards project area | Scotland's Environment Maps;#https://map.environment.gov.scot/sewebmap/;#- Open Scotland's environment Map <br>- Select 'Add Map Data Layers' <br>- Search for 'World Heritage Sites' <br>- Select 'Apply to Map' and close window <br>- Zoom in towards project area <br>- Display Legend <br>- Click on the map to identify the feature <br>- Estimate distance using the map's scale |  | Choice |  |  | Yes | No | [8 empty] | 0
|  | D15 | Respecting cultural heritage and rail history | Y | Is the project area within 150m of any of the following? |  |  | Geo-RINM;#http://grv.corp.ukrail.net/Html5Viewer/Index.html?viewer=GeoRINM_Viewer.GeoRINM_Viewer_html5_v28#;#- Open Geo-RINM <br>- Select 'Land Information' layer (Expand) <br>- Select 'Heritage' layer (Expand) <br>- Search project area <br>- Identify features with a right-click and selecting 'Find data on the map'. Results will appear on the left hand-side. <br>- Measure distance using function available in the Tools ('Identify and Measure' tab) <br> <br><i><u>Note</u>: World Heritage Site, Registered Parks & Gardens and Registered Battlefields are not available on Geo-RINM. Consult Historic England/Wales/Scotland for these statutory designations. | Historic England;#https://historicengland.org.uk/listing/the-list/map-search?clearresults=True;#- Open Historic England Map <br>- Search project area <br>- Click on the feature to obtain information | Lle Map (Wales);#http://lle.gov.wales/map;#- Open Lle Map <br>- Add 'World Heritage Sites' layers <br>- Zoom in towards project area | Scotland's Environment Maps;#https://map.environment.gov.scot/sewebmap/;#- Open Scotland's environment Map <br>- Select 'Add Map Data Layers' <br>- Search for 'World Heritage Sites' <br>- Select 'Apply to Map' and close window <br>- Zoom in towards project area <br>- Display Legend <br>- Click on the map to identify the feature <br>- Estimate distance using the map's scale |  | Heading | [12 empty] | 0
| D21 | D15.1 | Respecting cultural heritage and rail history | Y | Grade I and II Listed buildings | [7 empty] | Double Click | 2 | [11 empty] | 0
| D22 | D15.2 | Respecting cultural heritage and rail history | Y | Scheduled ancient monuments | [7 empty] | Double Click | 2 | [11 empty] | 0
| D23 | D15.3 | Respecting cultural heritage and rail history | Y | Conservation areas | [7 empty] | Double Click | 2 | [11 empty] | 0
| D24 | D15.4 | Respecting cultural heritage and rail history | Y | World heritage sites | [7 empty] | Double Click | 2 | [11 empty] | 0
| D25 | D15.5 | Respecting cultural heritage and rail history | Y | Other (e.g. registered parks and gardens, registered battlefields, Area of Archaeological Interest, war memorial, designated items) | [7 empty] | Free text | 2 | [11 empty] | No
|  | D15.6 | Respecting cultural heritage and rail history | Y | None of the above | [7 empty] | Double Click | 2 | [11 empty] | 0
| D26 | D16 | Respecting cultural heritage and rail history | VLOOKUP({P2},tblProjectValues,2,False)>=6 | Is there a heritage railway near (<10km) the project area? |  |  | Heritage Railways (UK);#http://www.heritage-railways.com/map.php;#- Open UK & Ireland Heritage Railways Map <br>- Search project area <br>- Identify if Heritage Railway within 10km using the map scale |  |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D27a | D17 | Being a caring neighbour | Y | Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? | Note: Please see the Social Value Framework for opportunities around social value |  | Google Map;#https://www.google.com/maps;#- Open Google Map <br>- Identify nearby properties and measure distance to project area using function available through a right click on the map | Social Value Framework;#https://safety.networkrail.co.uk/wp-content/uploads/2021/08/78092_NETRAIL_Social_Framework_doc_v3.pdf;#- Open Social Value Framework <br>- Identify opportunities |  |  |  | Choice |  |  | Yes | No |  |  |  | H[{D17.1}] | S[{D17.1}] |  |  |  | 0
| D27b | D17.1 | Being a caring neighbour |  | If No, within 250m? | [7 empty] | Choice |  |  | Yes | No | [8 empty] | 0
| D28 | D18 | Being a caring neighbour | Y | Are there sensitive/vulnerable receptors (e.g. hospital, care home) near (<200m) the project area? Or for noisier works, within 500m? | Note: Please see the Social Value Framework for opportunities around social value |  | Google Map;#https://www.google.com/maps;#- Open Google Map <br>- Identify vulnerable receptors and measure distance to project area using function available through a right click on the map | Social Value Framework;#https://safety.networkrail.co.uk/wp-content/uploads/2021/08/78092_NETRAIL_Social_Framework_doc_v3.pdf;#- Open Social Value Framework <br>- Identify opportunities |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D29 | D19 | Being a caring neighbour | VLOOKUP({P2},tblProjectValues,2,False)>=6 | Are there schools and/or universities within 20 miles of the project area? | Note: Please see the Social Value Framework for opportunities around social value |  | Google Map;#https://www.google.com/maps;#'- Open Google Map <br>- Identify schools and universities and measure distance to project area using function available through a right click on the map | Social Value Framework;#https://safety.networkrail.co.uk/wp-content/uploads/2021/08/78092_NETRAIL_Social_Framework_doc_v3.pdf;#- Open Social Value Framework <br>- Identify opportunities |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D30 | D20 | Being a caring neighbour | {P2}=">£50m" | Is there employment a correctional facility or rehabilitation centre within 20 miles of the project area? | Note: Please see the Social Value Framework for opportunities around social value |  | Google Map;#https://www.google.com/maps;#- Open Google Map <br>- Identify correctional facilities and measure distance to project area using function available through a right click on the map | Social Value Framework;#https://safety.networkrail.co.uk/wp-content/uploads/2021/08/78092_NETRAIL_Social_Framework_doc_v3.pdf;#- Open Social Value Framework <br>- Identify opportunities |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D31 | D21 | Being a caring neighbour | {P2}=">£50m" | Is there a homelessness service or centre within 20 miles of the project area? | Note: Please see the Social Value Framework for opportunities around social value |  | Homeless England;#https://www.homeless.org.uk/homeless-england/search-near-me;#'- Open Homeless Link website <br>- Enter nearest postcode, town or city from the project area <br>- Choose a distance of 20 miles and 'Go' <br>- Identify charities that the project could support/partner with | Social Value Framework;#https://safety.networkrail.co.uk/wp-content/uploads/2021/08/78092_NETRAIL_Social_Framework_doc_v3.pdf;#- Open Social Value Framework <br>- Identify opportunities |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D32 | D22 | Being a caring neighbour | {P2}=">£50m" | Is there a place of worship (e.g. church, mosque, temple, etc.) within 1km of the project area? | Note: Please see the Social Value Framework for opportunities around social value |  | Google Map;#https://www.google.com/maps;#- Open Google Map <br>- Identify places of worship and measure distance to project area using function available through a right click on the map | Social Value Framework;#https://safety.networkrail.co.uk/wp-content/uploads/2021/08/78092_NETRAIL_Social_Framework_doc_v3.pdf;#- Open Social Value Framework <br>- Identify opportunities |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D33 | D23 | Being a caring neighbour | Y | Is the project area located where a large number of complaints (>10) has been received over the past 2 years? | Username: NR.user Password: NRUser2019# |  | Complaints Map;#https://networkrail.yonderdatasolutions.com/;#- Open Complaints Map <br>- Enter the following login details: <br>Username: NR.user <br>Password: NRUser2019# <br>- Zoom towards project area <br>- Identify if >10 service requests were received by the Network Rail Helpline since the 1st of April 2018 |  |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D35 | D25 | Keeping communities safe | Y | Is the project area affected by route crime (e.g. trespass) or suicide (i.e. Amber or Red Status)? | Note: Use the Route Crime Excel Register |  | Route Crime;#https://safety.networkrail.co.uk/wp-content/uploads/2018/06/Working-in-a-Trespass-Hotspot-National-v1.xlsm;#'- Open Route Crime Excel Register <br>- Select the type of location information to use for this search <br>- Select the Route <br>- Provide the location information (previously selected) <br>- Press 'Enter' <br>- Identify Red and Amber issues within or near the project area <br> <br><i><u>Note</u>: Grid references can be obtained from Geo-RINM by hovering over project location and taking note of the references appearing at the bottom of the map |  |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| D36 | D26 | Supporting Britain's economic development | {P2}=">£50m" | Does the project area include neighbourhood(s) affected by social deprivation (i.e. amongst the 10% most deprived neighbourhoods in the country)? |  |  | Index of Multiple Deprivation (England);#http://dclgapps.communities.gov.uk/imd/iod_index.html;#- Open IMD Maps with Google Chrome or equivalent alternative to Internet Explorer <br>- Hide 2015 map <br>- Select 'IMD' <br>- Show Map legend <br>- Search project area <br>- Identify presence of neighbourhoods amongst the 10% most deprived within the project area | Welsh Index of Multiple Deprivation;#https://wimd.gov.wales/explore?lang=en#domain=overall&&z=8&lat=52.4137&lng=-4.2000;#- Open WIMD Map <br>- Search project area <br>- Identify presence of neighbourhoods amongst the 10% most deprived within the project area | Scottish Index of Multiple Deprivation;#https://simd.scot/#/simd2016/BTTTFTT/9/-4.0000/55.9000/;#- Open SIMD Map <br>- In 'Map Chooser', select '2020' and 'Most deprived 10%' <br>- Search project area <br>- Identify presence of neighbourhoods amongst the 10% most deprived within the project area |  |  | Choice |  |  | Yes | No | [8 empty] | 0
|  | D29 | Supporting Britain's economic development | {P2}=">£50m" | Are there opportunities available to (i) share contract opportunities with SME, local and/or VCSE business groups (ii) job opportunities with local communities? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A1 | A1 | Biodiversity | {S1}="Yes" | Will vegetation management and/or land take impact an area >1,500m2? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A-NEW5? | A35 | Biodiversity | {S1}="Yes" | Will land take impact third party land? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A2 | A2 | Pollution of land /water | {N1}="No"&&{S21&S22}<>"Yes" | Will the project require handling >200L of oil and/or fuel during construction (e.g. diesel generator, refuelling tank, oil-filled High Voltage cable) and/or operation (e.g. transformer, refuelling depot)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A3 | A3 | Pollution of land /water | {N1}="No"&&{S21&S22}<>"Yes" | Will the project require substances hazardous to the environment (other than oil and fuel) during construction and/or operation (e.g. solvent, herbicide, etc.)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A4 | A4 | Pollution of land /water | {S9¦S10¦S11}="Yes" | Will the project require delivery of anti-icer treated rail ballast (based on programme of works)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A5 | A5 | Emissions to Air | {S5¦S9¦S10¦S11¦S14}="Yes" | Will the project contribute to local air pollution from diesel rolling stock during operation (e.g. passenger train idling at new depot or expanded sidings, freight train idling at new signal location, etc.)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A6 | A6 | Emissions to Air | {N1}="No"&&{S21&S22}<>"Yes" | Will the project contribute to local air pollution (including dust and fumes) during construction (from earthworks, plant and equipment as well as vehicles for the transport of materials, etc.)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A12 | A12 | Pollution of land /water | {N1}="No"&&{S21&S22}<>"Yes" | Will the project require temporary or permanent water discharge to surface water or sewerage system? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A13 | A13 | Pollution of land /water | {S4¦S5¦S6¦S7¦S12¦S14¦S14}="Yes" | Will the project require piling, boring or drilling? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A7 | A7 | Noise & Vibration | {S5¦S9¦S10¦S11¦S15}="Yes" | Will the project contribute to an increase local noise & vibration levels during operation (e.g. new or increased maintenance depot activities, additional rolling stock, rolling stock idling at new signal location, etc.)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A8 | A8 | Noise & Vibration | {N1}="No"&&{S21&S22}<>"Yes" | Will the project contribute to an increase local noise & vibration levels during construction (excavation/demolition works, tamping, piling, cutting, drilling, etc.)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A9 | A9 | Noise & Vibration | {S5}="Yes" | Will the project require the installation of a Public Address (PA) system? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A10 | A10 | Noise & Vibration | {S14¦S17}="Yes" | Will the project require the installation of an Automatic Track Warning System? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A11 | A11 | Dust, Odour & Lighting | {N1}="No"&&{S21&S22}<>"Yes" | Could the project require installation of temporary (i.e. construction) and/or permanent (i.e. operation) outdoor artificial lighting? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| NewQ | A44 | Dust, Odour & Lighting | {N1}="No"&&{S21&S22}<>"Yes" | Is there a risk of dust or odour emissions? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A14 | A14 | Energy | {S11¦S13¦S14¦S17¦S19}="Yes" | Will the project involve modifying, replacing and/or providing new operational power supply to lineside equipment? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A15 | A15 | Energy | {N1}="No"&&{S21&S22}<>"Yes" | Will the project require access to a power supply during construction? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| NewQ | A43 | Energy | {N1}="No"&&{S21&S22}<>"Yes" | Have you identified opportunities to reduce energy and fuel usage? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A16 | A16 | Materials | {N1}="No"&&{S21&S22}<>"Yes" | Will construction (including site compounds) require import of large volumes of engineering fill and/or aggregates (>100t), including track bed material? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A17 | A17 | Materials | {N1}="No"&&{S21&S22}<>"Yes" | Will construction require significant quantities of concrete and/or steel (>100t), including track material? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A18 | A18 | Materials | {N1}="No"&&{S21&S22}<>"Yes" | Will construction require timber or other forest products for temporary (e.g. hoarding, formwork) or permanent use (e.g. structural frame, cladding) other than rail sleepers? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A19 | A19 | Waste | {N1}="No"&&{S21&S22}<>"Yes" | Will existing building, structure or equipment need to be decommissioned, demounted, demolished or stripped-out as part of the project? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A20 | A20 | Waste | {N1}="No"&&{S21&S22}<>"Yes" | Are the construction works likely to generate significant volumes of demolition and/or excavation material (>100 tonnes)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A21 | A21 | Waste | {N1}="No"&&{S21&S22}<>"Yes" | Are the works likely to generate significant volumes of construction waste (>100 tonnes) other than demolition and/or excavation material (e.g. plastic, timber or cardboard packaging; steel, timber, plastic off cuts; food or office waste, grit blasting waste; silt or sludge from drainage works; excess concrete)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A23 | A23 | Water | {N1}="No"&&{S21&S22}<>"Yes" | Are the works likely to require large quantities of water (>100m3 or 100,000L) during construction (e.g. dust suppression including control of ballast dust, welfare facilities, grouting)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A24 | A24 | Water | {S5}="Yes" | Will the project increase water consumption during operation? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A25 | A25 | Water | {N1}="No"&&{S21&S22}<>"Yes" | Will the project require water abstraction (from surface water or groundwater) during construction and/or operation? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A27 | A27 | Weather Resilience & Climate Change Adaptation (WRCCA) | {S2¦S4¦S5¦S7¦S8¦S10¦S11¦S13}="Yes" | Will the project increase the area requiring surface water drainage (e.g. car park, roof, new track, new sidings, feeder station containment, etc.)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A28 | A28 | Weather Resilience & Climate Change Adaptation (WRCCA) | {S2¦S4¦S5¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S17¦S19}="Yes" | Does the project include new or existing railway assets (including earthworks) vulnerable to higher temperature (e.g. rail buckling, signalling failure), heavier rainfall (e.g. land slip, power cut due to flooding) and/or more extreme coastal events (e.g. erosion, sea level rise)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A29 | A29 | Sustainable Travel | {S5}="Yes" | Will the project offer an interface with other modes of transport (e.g. at station, depot, etc.) during operation? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A30 | A30 | Sustainable Travel | {N1}="No"&&{S21&S22}<>"Yes" | Will the project involve a large workforce (>50) that will be travelling to a single location for a long period of time (>6 months) during construction? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A31 | A31 | Respecting cultural heritage and rail history (visual impact) | {S4¦S5¦S6¦S12¦S13¦S14¦S17}="Yes" | Will the project involve erecting prominent structures or assets (e.g. OLE masts and wires, GSM mast, LX equipment inc. radars and lighting, signal gantries, fencing, etc.)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A32 | A32 | Making travel accessible and inclusive | {S4¦S5}="Yes" | Will the project involve changing the permanent or temporary access to buildings, stations or bridges? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A33 | A33 | Making travel accessible and inclusive | {N1}="No"&&{S21&S22}<>"Yes" | Could public access (including footpath, cycle path, rights of way, level crossing) require temporary closure and/or diversion during project delivery? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| NewQ | A42 | Making travel accessible and inclusive | {N1}="No"&&{S21&S22}<>"Yes" | Will the project impact people (e.g. passengers, employees, or lineside neighbours), including temporary works, temporary conditions, and staging works? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A34 | A34 | Connecting communities with the environment | {S4¦S5¦S6}="Yes" | Will the project affect the station and/or platform environment? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
|  | A40 | Connecting communities with the environment | {S4¦S9}="Yes" | Will visually prominent structures be erected in the project area? | [7 empty] | Choice |  |  | Yes | No | [8 empty] | 0
| NewQ | A41 | Inspiring tomorrow's workforce | {P2}=">£50m" | Are there any schools within 200m of the project area? |  |  | Google Map;#https://www.google.com/maps;#- Open Google Map <br>- Identify places of worship and measure distance to project area using function available through a right click on the map |  |  |  |  | Choice |  |  | Yes | No | [8 empty] | 0
| NewQ | A45 | Inspiring tomorrow's workforce | Y | Does the project have any section 106 requirements set by a planning authority? | [7 empty] | Choice |  |  | Yes | No | [8 empty] | 0
| A-NEW1 | A36 | OTM Design/Build/Refurbishment | {S21}="Yes" | Is the OTM powered by fossil fuels (includes primary engine power source as well as auxiliary power e.g. onboard generators)? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A-NEW2 | A37 | OTM Design/Build/Refurbishment | {S21}="Yes" | Does the OTM require hydrocarbon based lubricants to operate? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A-NEW3 | A38 | OTM Design/Build/Refurbishment | {S21}="Yes" | Does the OTM use large quantities of water as part of its operational activities (e.g. water to treat the track bed or onboard dust suppression), excluding engine cooling? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
| A-NEW4 | A39 | OTM Design/Build/Refurbishment | {S21}="Yes" | Is the OTM likely to be operated near lineside neighbours? | [7 empty] | Choice |  |  | Yes | No | Don't Know | [7 empty] | 0
|  | S1 | Enabling Activities | Y | The project involves vegetation management and/or land take. | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S2 | Enabling Activities | Y | The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s). | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S3 | Enabling Activities | Y | The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S4 | Buildings & Civils | Y | The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S5 | Buildings & Civils | Y | The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S6 | Buildings & Civils | Y | The project involves other civils work (e.g. foundations, fencing, walkway, etc.). | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S7 | Geotechnical & Drainage | Y | The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S8 | Geotechnical & Drainage | Y | The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S9 | Track | Y | The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S10 | Track | Y | The project involves plain line extension (e.g. new track line, new loop, grade separation) | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S11 | Track | Y | The project involves new or modified sidings | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S12 | Electrical & Power | Y | The project involves replacing or installing new OLE | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S13 | Electrical & Power | Y | The project involves replacing or installing new feeder station or sub-station | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
| S-NEW3 | S19 | Electrical & Power | Y | The project involves replacing or installing new lineside E&P assets (e.g. DNO, lighting, etc.) | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
| S-NEW4 | S20 | Electrical & Power | Y | The project involves replacing and/or installing new E&P cable route | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S15 | Signalling & Telecoms | Y | The project involves replacing and/or installing Under Track Crossing (UTX)/Under Road Crossing (URX). | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S14 | Signalling & Telecoms | Y | The project involves replacing and/or installing new lineside S&T assets (e.g. signal, signal box, signage, REB, location cabinet, GSM mast, etc.) | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S16 | Signalling & Telecoms | Y | The project involves replacing and/or installing new S&T cable route | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S17 | Level Crossing (LX) | Y | The project involves renewing and/or modifying a Level Crossing | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
|  | S18 | Level Crossing (LX) | Y | The project involves closing a Level Crossing | [7 empty] | Choice |  |  | Yes | Maybe | No | [7 empty] | 0
| S-NEW1 | S21 | On Track Machine (OTM) Design/Build/Refurbishment | {P4}="Route Services" | The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). | [7 empty] | Choice |  |  | Yes | No | [8 empty] | 0
| S-NEW2 | S22 | On Track Machine (OTM) Design/Build/Refurbishment | {P4}="Route Services" | As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments? | [7 empty] | Choice |  |  | Yes | No | [8 empty] | 0
| NewQ | D30 | General | Y | Have objective, targets and key performance indicators been identified? | [7 empty] | Choice |  |  | Yes | No | [8 empty] | 0
| NewQ | D31 | Energy and Carbon | Y | Have opportunities been identified to support carbon reduction commitments and the decarbonisation programme? | [7 empty] | Choice |  |  | Yes | No | [8 empty] | 0
| NewQ | D32 | General | Y | As part of the response to the relevant invitation to tender, did the designer/ contractor make environmental and or social commitments? | [7 empty] | Choice |  |  | Yes | No | [8 empty] | 0

## Actions Framework (hidden)
[5 empty] | Next No. | 174
Heading | High Logic | Medium Logic | Low Logic | Soc/Env | Ref | Section | Sub-Section | Action | Guidance | Warning | Logic | Suggested Phase for this Action | Suggested Action Owner(s) for this Action | Logic Result | Resolved Logic with references | Resolved Logic with values | Associated Questions
General |  |  |  | N/A | T1 | General | Appraisal Completeness | One or more Project Activities questions were answered as 'Don't know': Provide update at the next project development stage. |  |  | {DK1}="Yes" | ALL |  | FALSE | DK1="Yes" | "No"="Yes" | DK1 = "No" [Automated] 'Don't Know' answers are present on the Project Activities tab
Being a caring neighbour | {D17¦D23}="Yes" | {D17.1}="Yes" | TRUE | Soc | T154 | General | Appraisal Completeness | One or more Project Scope questions were answered as 'Maybe': Provide update at the next project development stage. |  |  | {M1}="Yes" | ALL |  | FALSE | M1="Yes" | "No"="Yes" | M1 = "No" [Automated] 'Maybe' answers are present on the Project Scope tab
Biodiversity | [{D2¦D2.1¦D4.1¦D4.2¦D4.3¦D4.4¦D4.5¦D4.6¦D4.7¦D4.8¦D5¦D6¦D7}="Yes"]&&[{S1}="Yes"¦¦{S1}="Maybe"] | [{D2¦D2.1¦D4.1¦D4.2¦D4.3¦D4.4¦D4.5¦D4.6¦D4.7¦D4.8¦D5¦D6¦D7}="Yes"¦¦{S1}="Yes"¦¦{S1}="Maybe"] | TRUE | Env | T2 | General | External Benchmarking | Identify suitable Sustainability Certification Scheme (CEEQUAL, BREEAM or equivalent) and integrate associated Assessment with expected level of achievement/rating (e.g. Very Good or Excellent) into Client/Route Requirement Document and Contract Requirements. | BREEAM to be considered for new or refurbished buildings with significant areas of thermal space and some permanently occupied spaces (e.g. large workplace office, large stations - Category A to C) <br> <br>CEEQUAL to be considered for large infrastructure projects. |  | [{S4¦S5¦S12}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)=7 | Phase 1 | Client | FALSE | AND(OR(S4="Yes",S5="Yes",S12="Yes"),VLOOKUP(P2,tblProjectValues,2,False)=7) | AND(OR(""="Yes",""="Yes",""="Yes"),VLOOKUP("Select from drop down list…",tblProjectValues,2,False)=7) | S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S12 = "" The project involves replacing or installing new OLE
Connecting communities with the environment | {S1}="Yes"&&{D19¦D17}="Yes" | {S1}="Yes"&&{D17¦D17.1¦A34}="Yes" | TRUE | Soc | T3 | General | 3rd party Land Take | Liaise with Town Planning representative to trigger negotiation with land owner and identify planning requirements (e.g. TWAO). Update Land & Consents Strategy and associated Commitments accordingly. |  |  | {A35}="Yes" | Phase 2 | Client | FALSE | A35="Yes" | ""="Yes" | A35 = "" Will land take impact third party land?
Contaminated Land | {D8}="Yes"&&[{D9¦D10}="Yes"] | {D8¦D10}="Yes" | TRUE | Env | T4 | General | Compound / Haul Road / Access Point | Undertake site-specific Desktop Study for the proposed Compound/Haul Road/Access Point and select location with the least environmental and social impacts (e.g. least biodiversity loss and/or least nuisance to local community) |  |  | {S2}="Yes"¦¦{S2}="Maybe" | Phase 3 | Client | FALSE | OR(S2="Yes",S2="Maybe") | OR(""="Yes",""="Maybe") | S2 = "" The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s). S2 = "" The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s).
Creating engaged employees and positive industry partnerships | {D20¦D21¦D22¦D26}="Yes" | {D16¦D19¦D17}="Yes" | TRUE | Soc | T5 | General | Compound / Haul Road / Access Point | Provide findings of site-specific Desktop Study to Contractor for associated environmental and social risks (e.g. ecology, noise & vibration, pollution, invasive species, etc.) to be addressed as part of the Work Package Plan (WPP) and/or Environment & Social Management Plan (ESMP). |  |  | {S2}="Yes"¦¦{S2}="Maybe" | Phase 3 | Client | FALSE | OR(S2="Yes",S2="Maybe") | OR(""="Yes",""="Maybe") | S2 = "" The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s). S2 = "" The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s).
Emissions to Air | [{D11}="Yes"]&&[{A5¦A6}="Yes"] | {D11¦A5¦A6}="Yes" | TRUE | Env | T163 | General | Third Party Land | Obtain appropriate landowner consent prior to works |  |  | {D0.7}="Yes" |  |  | FALSE | D0.7="Yes" | ""="Yes" | D0.7 = "" Is access to third party land required?
Energy and Carbon | {A17¦S4¦S5}="Yes" | {A14¦A15}="Yes" | TRUE | Env | T7 | General | Site Investigation | Undertake site-specific Desktop Study for the proposed Site Investigation and select locations with the least environmental and social impacts (e.g. least biodiversity loss and/or least nuisance to local community) |  |  | {S3}="Yes"¦¦{S3}="Maybe" | Phase 2-3 | Client | FALSE | OR(S3="Yes",S3="Maybe") | OR(""="Yes",""="Maybe") | S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.)
Inspiring tomorrow’s workforce | [{D19}="Yes"]&&[{P2}=">£50m"] | [{D19}="Yes"]&&[{P2}="£20m-£50m"] | TRUE | Soc | T8 | General | Site Investigation | Provide findings of site-specific Desktop Study to Contractor for environmental and social risks associated with this activity (e.g. ecology, noise & vibration, pollution, invasive species, etc.) to be addressed as part of the Work Package Plan (WPP) and/or Environment & Social Management Plan (ESMP). |  |  | {S3}="Yes"¦¦{S3}="Maybe" | Phase 2-3 | Survey Contractor / Principal Contractor | FALSE | OR(S3="Yes",S3="Maybe") | OR(""="Yes",""="Maybe") | S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.)
Keeping Communities safe | {D25¦S12¦S17}="Yes" | {S18}="Yes" | TRUE | Soc | T10 | General | Environmental Resources | Principal Contractor to provide Safety, Health & Environment Advisor with environmental competence and experience in Construction | <a href="http://networkrailstandards/StandardHeaderView.aspx?id=27303" target="_blank">NR/L2/INI/CP0070 Principal Contractor Licensing Scheme</a> (Appendix E) | ! This is a requirement under the Principal Contractor Licensing Scheme (NR/L2/INI/CP0070) ! | VLOOKUP({P2},tblProjectValues,2,False)<=3&&{S21&S22}<>"Yes" | Phase 3 | Principal Contractor | TRUE | AND(VLOOKUP(P2,tblProjectValues,2,False)<=3,AND(S21<>"Yes",S22<>"Yes")) | AND(VLOOKUP("Select from drop down list…",tblProjectValues,2,False)<=3,AND(""<>"Yes",""<>"Yes")) | P2 = "Select from drop down list…" Estimated Project Value (Development, Design and Construction) S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
Making rail a great experience | {D17&A34}="Yes" | {D17¦A34}="Yes" | TRUE | Soc | T11 | General | Environmental Resources | Principal Contractor to have an Environmental Professional with IEMA Associate membership (or equivalent) available to the Project | <a href="http://networkrailstandards/StandardHeaderView.aspx?id=27303" target="_blank">NR/L2/INI/CP0070 Principal Contractor Licensing Scheme</a> (Appendix E) | ! This is a requirement under the Principal Contractor Licensing Scheme (NR/L2/INI/CP0070) ! | VLOOKUP({P2},tblProjectValues,2,False)=4&&{S21&S22}<>"Yes" | Phase 3 | Principal Contractor | FALSE | AND(VLOOKUP(P2,tblProjectValues,2,False)=4,AND(S21<>"Yes",S22<>"Yes")) | AND(VLOOKUP("Select from drop down list…",tblProjectValues,2,False)=4,AND(""<>"Yes",""<>"Yes")) | P2 = "Select from drop down list…" Estimated Project Value (Development, Design and Construction) S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
Making travel accessible and inclusive | {A32¦A33}="Yes" | {D17¦A34}="Yes" | TRUE | Soc | T12 | General | Environmental Resources | Principal Contractor to have an Environmental Professional with IEMA Practitioner membership (or equivalent) embedded in the Project | <a href="http://networkrailstandards/StandardHeaderView.aspx?id=27303" target="_blank">NR/L2/INI/CP0070 Principal Contractor Licensing Scheme</a> (Appendix E) | ! This is a requirement under the Principal Contractor Licensing Scheme (NR/L2/INI/CP0070) ! | VLOOKUP({P2},tblProjectValues,2,False)=5&&{S21&S22}<>"Yes" | Phase 3 | Principal Contractor | FALSE | AND(VLOOKUP(P2,tblProjectValues,2,False)=5,AND(S21<>"Yes",S22<>"Yes")) | AND(VLOOKUP("Select from drop down list…",tblProjectValues,2,False)=5,AND(""<>"Yes",""<>"Yes")) | P2 = "Select from drop down list…" Estimated Project Value (Development, Design and Construction) S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
Materials - Responsible Sourcing | {A16¦A17}="Yes" | {S2¦A18}="Yes" | TRUE | Env | T13 | General | Environmental Resources | Principal Contractor to provide Full time Environment Advisor (or equivalent) with IEMA Practitioner membership (or equivalent) and at least 5 years experience in Construction | <a href="http://networkrailstandards/StandardHeaderView.aspx?id=27303" target="_blank">NR/L2/INI/CP0070 Principal Contractor Licensing Scheme</a> (Appendix E) | ! This is a requirement under the Principal Contractor Licensing Scheme (NR/L2/INI/CP0070) ! | VLOOKUP({P2},tblProjectValues,2,False)=6&&{S21&S22}<>"Yes" | Phase 3 | Principal Contractor | FALSE | AND(VLOOKUP(P2,tblProjectValues,2,False)=6,AND(S21<>"Yes",S22<>"Yes")) | AND(VLOOKUP("Select from drop down list…",tblProjectValues,2,False)=6,AND(""<>"Yes",""<>"Yes")) | P2 = "Select from drop down list…" Estimated Project Value (Development, Design and Construction) S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
Noise and Vibration | [{D12¦D17}="Yes"]&&[{A7¦A8¦A9¦A10}="Yes"] | {D12¦D17¦A7¦A8¦A9¦A10}="Yes" | TRUE | Env | T14 | General | Environmental Resources | Principal Contractor to provide Full time Environment Manager (or equivalent) with Full IEMA membership (or equivalent) and at least 5 years experience in Construction | <a href="http://networkrailstandards/StandardHeaderView.aspx?id=27303" target="_blank">NR/L2/INI/CP0070 Principal Contractor Licensing Scheme</a> (Appendix E) | ! This is a requirement under the Principal Contractor Licensing Scheme (NR/L2/INI/CP0070) ! | VLOOKUP({P2},tblProjectValues,2,False)=7&&{S21&S22}<>"Yes" | Phase 3 | Principal Contractor | FALSE | AND(VLOOKUP(P2,tblProjectValues,2,False)=7,AND(S21<>"Yes",S22<>"Yes")) | AND(VLOOKUP("Select from drop down list…",tblProjectValues,2,False)=7,AND(""<>"Yes",""<>"Yes")) | P2 = "Select from drop down list…" Estimated Project Value (Development, Design and Construction) S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
OTM Design / Build / Refurbishment |  |  |  | N/A | T155 | General | ESMP | Develop a Design Environment & Social Management Plan (ESMP) using Network Rail template | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2020/06/ESMP-FINAL-FOR-ISSUE.docx" target=_"blank">Environment and Social Management Plan (ESMP) Template</a> <br> <br><a href="https://safety.networkrail.co.uk/esd-guidance-notes/" target=_"blank">E&SD Guidance Notes<a/> | ! Mandated under NR/L2/ENV/015, Section 4.2 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {N1}="No"&&{S21&S22}<>"Yes" | Phase 3 | Designer | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
Pollution of land / water | [{D9¦D10}="Yes"]&&[{A2¦A3¦A4¦A12}="Yes"] | {D9¦D10¦A2¦A3¦A4¦A12}="Yes" | TRUE | Env | T156 | General | ESMP | Develop a Construction Environment & Social Management Plan (ESMP) using Network Rail template | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2020/06/ESMP-FINAL-FOR-ISSUE.docx" target=_"blank">Environment and Social Management Plan (ESMP) Template</a> <br> <br><a href="https://safety.networkrail.co.uk/esd-guidance-notes/" target=_"blank">E&SD Guidance Notes<a/> | ! Mandated under NR/L2/ENV/015, Section 4.2 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {N1}="No"&&{S21&S22}<>"Yes" | Phase 3 | Principal Contractor | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
Respecting cultural heritage and rail history | {D15.1¦D15.2¦D15.3¦D15.4}="Yes" | {D16}="Yes" | TRUE | Soc | T157 | General | ESMP | Review Design ESMP using the Environmental & Social Contract Review and Acceptance Form (EN3) | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2019/01/EN3-Review-and-Acceptance-Form-Template-NEW.xlsx" target=_"blank">Environmental & Social Contract Review and Acceptance Form<a/> | ! Mandated as a PACE Product ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {N1}="No"&&{S21&S22}<>"Yes" | Phase 2 | Client | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
Supporting Britain’s economic development | {D26}="Yes" | {A30}="Yes" | TRUE | Soc | T158 | General | ESMP | Review Construction ESMP using the Environmental & Social Review and Acceptance Form (EN3) | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2019/01/EN3-Review-and-Acceptance-Form-Template-NEW.xlsx" target=_"blank">Environmental & Social Contract Review and Acceptance Form<a/> | ! Mandated as a PACE Product ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {N1}="No"&&{S21&S22}<>"Yes" | Phase 2-3 | Client | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
Sustainable Travel | {A29}="Yes" | {A30}="Yes" | TRUE | Env | T159 | General | Records, documents and knowledge transfer | Handover any medium to long term permit, licence or consent conditions and requirements (e.g. maintenance and monitoring) to the Route with associated budget through the AMP process |  |  | {D2¦D2.1¦D4.1¦D4.2¦D4.3¦D4.4¦D4.5¦D4.6¦D4.7¦D4.8¦D5¦D9¦D13¦D15.1¦D15.2¦D15.3¦D15.4¦S8¦A12¦A25}="Yes" | Phase 4 |  | FALSE | OR(D2="Yes",D2.1="Yes",D4.1="Yes",D4.2="Yes",D4.3="Yes",D4.4="Yes",D4.5="Yes",D4.6="Yes",D4.7="Yes",D4.8="Yes",D5="Yes",D9="Yes",D13="Yes",D15.1="Yes",D15.2="Yes",D15.3="Yes",D15.4="Yes",S8="Yes",A12="Yes",A25="Yes") | OR(""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes") | D2 = "" Are there records of protected species within 1km of the project area? ! Absence of records does not confirm absence of protected species ! D2.1 = "" If No, within 2km? D4.1 = "" Site of Special Scientific Interest (SSSI) D4.2 = "" Special Area of Conservation (SAC) D4.3 = "" Special Protection Area (SPA) D4.4 = "" Ramsar D4.5 = "" Area of Outstanding Natural Beauty (AONB) D4.6 = "" National Park D4.7 = "" National Nature Reserve D4.8 = "" Local Nature Reserve D5 = "" Is there an Ancient Woodland Site near (<50m) or within the project area? D9 = "" Is the project area within 10m of a sea, estuary, watercourse (main river or ordinary watercourse such as open drainage, brook, etc.) or other surface water body (pond, canal, lake, loch, reservoir, etc.)? D13 = "" Is the project area within or near a fluvial, coastal (i.e. Flood Zone 3) and/or surface water high flood risk area? D15.1 = "" Grade I and II Listed buildings D15.2 = "" Scheduled ancient monuments D15.3 = "" Conservation areas D15.4 = "" World heritage sites S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) A12 = "" Will the project require temporary or permanent water discharge to surface water or sewerage system? A25 = "" Will the project require water abstraction (from surface water or groundwater) during construction and/or operation?
Waste | {A20¦A21}="Yes" | {A19}="Yes" | TRUE | Env | T172 | General |  | Refer to Environment and Sustainability Strategy for key strategy areas for inclusion | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2020/10/NR-Environmental-Strategy-FINAL-12-October-2020.pdf" target=_"blank">Environmental Sustainability Strategy</a> |  | {D30}="No" |  |  | FALSE | D30="No" | ""="No" | D30 = "" Have objective, targets and key performance indicators been identified?
Water | {A25}="Yes" | {A23¦A24}="Yes" | TRUE | Env | T173 | General |  | Progress environment and/or social commitments to ESMP |  |  | {D32}="Yes" |  |  | FALSE | D32="Yes" | ""="Yes" | D32 = "" As part of the response to the relevant invitation to tender, did the designer/ contractor make environmental and or social commitments?
Weather Resilience & Climate Change Adaptation (WRCCA) | [{D13¦D9}="Yes"]&&[{A28}="Yes"] | {A28¦D13¦D9}="Yes" | TRUE | Env | T15 | Biodiversity | Surveying | Liaise with the project Environment & Sustainability Representative (Ecologist, Specialist, Manager) for local records of ecology surveys (not published on Geo-RINM) |  | Note: Consult an Ecologist to confirm validity and suitability of any existing survey report for this project | {N1}="No"&&{S21&S22}<>"Yes" | Phase 1 | Client / Designer | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
Circular economy |  |  | TRUE | Env | T16 | Biodiversity | Surveying | Request and review ecology survey report identified on Geo-RINM. |  | Note: Consult an Ecologist to confirm validity and suitability of the survey report for this project | {D1}="Yes" | Phase 1 | Client / Designer | FALSE | D1="Yes" | ""="Yes" | D1 = "" Are there records of ecology survey(s) covering the project area on Geo-RINM? ! Absence of records on Geo-RINM does not confirm absence of previous surveys recorded locally! ! Preliminary Ecological Appraisals require re-validation after 24 months !
Dust, odour and lighting |  | {A11}="Yes" | TRUE | Env | T17 | Biodiversity | Surveying | Commission Preliminary Ecological Appraisal (PEA) including Phase 1 Habitat survey (unless valid PEA already available) | <a href=" https://safety.networkrail.co.uk/wp-content/uploads/2018/06/Biodiversity-planning-and-managing-Guidance-Note.pdf" target="_blank">Biodiversity planning and managing – Guidance Note</a> <br> <br>Integrate PEA findings and recommendations into Option Selection/Outline Design/Detailed Design/Construction | ! Mandated under NR/L2/ENV/015, Section 6.1 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! Note: Provide information gathered from Geo-RINM and NHD to the ecology services provider as part of the scope of works | {N1}="No"&&{S21&S22}<>"Yes" | Phase 1 | Client / Designer | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
[5 empty] | T18 | Biodiversity | Surveying | Commission further surveys if required (i.e. Phase 2 Species absence/presence survey) based on findings and recommendations from PEA report |  |  | {N1}="No"&&{S21&S22}<>"Yes" | Phase 2 | Client / Principal Contractor | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
[5 empty] | T21 | Biodiversity | Planning & Control | Develop and implement Invasive Non-Native Species (INNS) Management Plan including bio-security control measures to prevent spreading (Japanese Knotweed, Giant Hogweed, Himalayan Balsam, etc.) |  |  | {D7}="Yes" | Phase 2 | Survey Contractor / Principal Contractor | FALSE | D7="Yes" | ""="Yes" | D7 = "" Are there records of Japanese Knotweed, Giant Hogweed or Himalayan Balsam (Invasive Non-Native Species - INNS) near (<50m) or within the project area? ! Absence of records does not confirm absence of INNS ! Note: Other non-native invasive plant species (e.g. Cotoneaster, Rhododendron) must be considered as part of a Preliminary Ecological Appraisal (PEA)
[5 empty] | T22 | Biodiversity | Planning & Control | Plan works outside sensitive periods for wildlife (e.g. bird nesting, GCN hibernation, bat maternity and hibernation, badger winter sleep, etc.) when there is a risk to affect protected species |  |  | {N1}="No"&&{S21&S22}<>"Yes" | Phase 2-3 | Client / Designer / Survey Contractor / Principal Contractor | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
[5 empty] | T23 | Biodiversity | Planning & Control | Implement and maintain exclusion zone around protected trees based on Tree Root Protection Zone to prevent adverse impact. | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2017/09/Shared-Learning-Tree-Root-Preservation-Zone-management_August-2017.pdf" target=_"blank">Tree Root Protection Shared Learning</a> |  | {D5¦D6}="Yes" | Phase 2-3 | Principal Contractor | FALSE | OR(D5="Yes",D6="Yes") | OR(""="Yes",""="Yes") | D5 = "" Is there an Ancient Woodland Site near (<50m) or within the project area? D6 = "" Are there records of Tree Preservation Order (TPO) near (<50m) or within the project area? ! Absence of records does not confirm absence of TPO !
[5 empty] | T25 | Biodiversity | Risk assessment | If transformer oil containment e.g. bunding is required (as per NR/L1/ELP/27000), integrate design solutions to prevent wildlife entrapment | <a href="https://networkrail.sharepoint.com/sites/LessonsLearned/Lists/Lessons%20Learnt%20Database/DispForm.aspx?ID=813&e=zcnh4m" target=_"blank"> Shared Learning - Great Crested Newt trapped in Transformer Sump</a> <br> <br><a href="http://networkrailstandards/StandardHeaderView.aspx?id=27116" target=_"blank">NR/L1/ELP/27000 Policy Requirements for Electrical Power Assets</a> (See Policy Number EP-115 with regards to Bunding) <br> <br><a href="http://networkrailstandards/StandardHeaderView.aspx?id=27211" target=_"blank">NR/L1/ELP/27000 - Appendices</a> (See Appendix O- Distribution Transformer Siting Risk Assessment Matrix) |  | {S13}="Yes" | Phase 2-3 | Designer | FALSE | S13="Yes" | ""="Yes" | S13 = "" The project involves replacing or installing new feeder station or sub-station
[5 empty] | T26 | Biodiversity | Risk assessment | Undertake OLE bird flight collision risk assessment and include diverter into design if recommended |  |  | {S12}="Yes"¦¦{S12}="Maybe" | Phase 2-3 | Designer / Principal Contractor | FALSE | OR(S12="Yes",S12="Maybe") | OR(""="Yes",""="Maybe") | S12 = "" The project involves replacing or installing new OLE S12 = "" The project involves replacing or installing new OLE
[5 empty] | T27 | Biodiversity | Risk assessment | Undertake bird nesting inspection if undertaking vegetation management between March and October. | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2019/02/breeding-bird-briefing-2019-v2.pdf" target=_"blank">Breeding Bird and Nest Check Briefing 2019</a> <br> <br><a href="https://safety.networkrail.co.uk/wp-content/uploads/2019/02/ESD29-Breeding-Bird-and-Nest-Check-form.pdf" target=_"blank">ESD29 - Breeding Bird and Nest Check Form</a> | ! Only SAFETY CRITICAL vegetation management can be carried out between March and October (bird nesting season) ! | {S1}="Yes"¦¦{S1}="Maybe" | Phase 2-3 | Survey Contractor / Principal Contractor | FALSE | OR(S1="Yes",S1="Maybe") | OR(""="Yes",""="Maybe") | S1 = "" The project involves vegetation management and/or land take. S1 = "" The project involves vegetation management and/or land take.
[5 empty] | T28 | Biodiversity | Risk assessment | Undertake vegetation management activity under a method statement reviewed and approved by an ecologist, including watching brief by an ecologist or by an ecological clerk of works |  |  | {S1}="Yes"¦¦{S1}="Maybe" | Phase 2-3 | Survey Contractor / Principal Contractor | FALSE | OR(S1="Yes",S1="Maybe") | OR(""="Yes",""="Maybe") | S1 = "" The project involves vegetation management and/or land take. S1 = "" The project involves vegetation management and/or land take.
[5 empty] | T29 | Biodiversity | Local knowledge | Liaise with the project Environment & Sustainability Representative regarding SSSI Site Management Statement (SMS) and activities allowed under this agreement |  |  | {D4.1.1.1}="Yes" | Phase 2-3 | Client | FALSE | D4.1.1.1="Yes" | ""="Yes" | D4.1.1.1 = "" Is there an up to date Site Management Statement (SMS) in place? Note: there is no SMS in Wales and Scotland: Answer 'No' by default
[5 empty] | T30 | Biodiversity | Local knowledge | Liaise with Section Manager (Off Track) regarding existing treatment schedule to control Invasive Non-Native Species (Japanese Knotweed, Giant Hogweed, Himalayan Balsam, etc.) |  |  | {D7}="Yes" | Phase 2-3 | Client | FALSE | D7="Yes" | ""="Yes" | D7 = "" Are there records of Japanese Knotweed, Giant Hogweed or Himalayan Balsam (Invasive Non-Native Species - INNS) near (<50m) or within the project area? ! Absence of records does not confirm absence of INNS ! Note: Other non-native invasive plant species (e.g. Cotoneaster, Rhododendron) must be considered as part of a Preliminary Ecological Appraisal (PEA)
[5 empty] | T146 | Biodiversity | Local knowledge | Liaise with Section Manager (Off Track) regarding tagged trees | Lineside trees are tagged by Network Rail for 2 reasons: 1. They represent a risk to the infrastructure and so are tagged for later pruning or removal 2. They represent a fine example of a particular tree species and are tagged because they should not be removed e.g. veteran tree Projects should contact off track section manager to find out why the tree is tagged i.e. which of the two reasons above applies before any decisions are made. Tagged tree information is recorded on the Ellipse system. |  | {S1}="Yes"¦¦{S1}="Maybe" | Phase 2-3 | Client | FALSE | OR(S1="Yes",S1="Maybe") | OR(""="Yes",""="Maybe") | S1 = "" The project involves vegetation management and/or land take. S1 = "" The project involves vegetation management and/or land take.
[5 empty] | T31 | Biodiversity | Local knowledge | Liaise with Local Authority for latest Tree Preservation Order (TPO) locations (if not provided by Preliminary Ecological Appraisal) |  |  | {S1}="Yes"¦¦{S1}="Maybe" | Phase 2-3 | Client / Designer / Survey Contractor / Principal Contractor | FALSE | OR(S1="Yes",S1="Maybe") | OR(""="Yes",""="Maybe") | S1 = "" The project involves vegetation management and/or land take. S1 = "" The project involves vegetation management and/or land take.
[5 empty] | T32 | Biodiversity | Consenting | Liaise with Ecologist and/or Regulator (Natural England, Natural Resources Wales, Scottish Natural Heritage) and apply for Protected Species Licence and/or SSSI Assent if required. |  |  | {D2¦D2.1¦D4.1}="Yes" | Phase 2-3 | Client / Principal Contractor | FALSE | OR(D2="Yes",D2.1="Yes",D4.1="Yes") | OR(""="Yes",""="Yes",""="Yes") | D2 = "" Are there records of protected species within 1km of the project area? ! Absence of records does not confirm absence of protected species ! D2.1 = "" If No, within 2km? D4.1 = "" Site of Special Scientific Interest (SSSI)
[5 empty] | T33 | Biodiversity | Consenting | Liaise with Local Authority and apply for Consent if works on protected trees (or within their Tree Root Protection Zone) is unavoidable |  |  | [{S1}="Yes"¦¦{S1}="Maybe"]&&[{D6¦D15.3}="Yes"] | Phase 2-3 | Principal Contractor | FALSE | AND(OR(S1="Yes",S1="Maybe"),OR(D6="Yes",D15.3="Yes")) | AND(OR(""="Yes",""="Maybe"),OR(""="Yes",""="Yes")) | S1 = "" The project involves vegetation management and/or land take. S1 = "" The project involves vegetation management and/or land take. D6 = "" Are there records of Tree Preservation Order (TPO) near (<50m) or within the project area? ! Absence of records does not confirm absence of TPO ! D15.3 = "" Conservation areas
[5 empty] | T34 | Biodiversity | Consenting | Liaise with Local Authority and apply for hedgerow Licence if vegetation management activities are affecting an important countryside hedgerow |  |  | {S1}="Yes"¦¦{S1}="Maybe" | Phase 2-3 | Principal Contractor | FALSE | OR(S1="Yes",S1="Maybe") | OR(""="Yes",""="Maybe") | S1 = "" The project involves vegetation management and/or land take. S1 = "" The project involves vegetation management and/or land take.
[5 empty] | T35 | Biodiversity | Consenting | Liaise with Forestry Commission and apply for tree felling Licence if planning to fell large volume of trees outside the operational railway envelope |  |  | [{S1}="Yes"¦¦{S1}="Maybe"]&&[{A1}="Yes"] | Phase 2-3 | Principal Contractor | FALSE | AND(OR(S1="Yes",S1="Maybe"),A1="Yes") | AND(OR(""="Yes",""="Maybe"),""="Yes") | S1 = "" The project involves vegetation management and/or land take. S1 = "" The project involves vegetation management and/or land take. A1 = "" Will vegetation management and/or land take impact an area >1,500m2?
[5 empty] | T36 | Biodiversity | Consenting | Update Land & Consents Strategy and associated Commitments to consider consultation with National Park Authority due to potential impact on the Park |  |  | {D4.6}="Yes" | Phase 2-3 | Client | FALSE | D4.6="Yes" | ""="Yes" | D4.6 = "" National Park
[5 empty] | T37 | Biodiversity | Consenting | Update Land & Consents Strategy and associated Commitments to consider consultation with National Nature Reserve Managing Body due to potential impact on the Reserve |  |  | {D4.7}="Yes" | Phase 2-3 | Client | FALSE | D4.7="Yes" | ""="Yes" | D4.7 = "" National Nature Reserve
[5 empty] | T38 | Biodiversity | Consenting | Update Land & Consents Strategy and associated Commitments to consider consultation with AONB Conservation Board due to potential impact on the AONB |  |  | {D4.5}="Yes" | Phase 2-3 | Client | FALSE | D4.5="Yes" | ""="Yes" | D4.5 = "" Area of Outstanding Natural Beauty (AONB)
[5 empty] | T39 | Biodiversity | Consenting | Update Land & Consents Strategy and associated Commitments to consider Habitats Regulations Assessment (HRA Screening) due to potential impact on SAC/SPA/Ramsar site |  |  | {D4.2¦D4.3¦D4.4}="Yes" | Phase 2-3 | Client | FALSE | OR(D4.2="Yes",D4.3="Yes",D4.4="Yes") | OR(""="Yes",""="Yes",""="Yes") | D4.2 = "" Special Area of Conservation (SAC) D4.3 = "" Special Protection Area (SPA) D4.4 = "" Ramsar
[5 empty] | T40 | Biodiversity | Consenting | Update Land & Consents Strategy and associated Commitments to consider consultation with Local Authority due to potential impact on Local Nature Reserve |  |  | {D4.8}="Yes" | Phase 2-3 | Client | FALSE | D4.8="Yes" | ""="Yes" | D4.8 = "" Local Nature Reserve
[5 empty] | T41 | Biodiversity | Consenting | Update Land & Consents Strategy and associated Commitments to consider consultation with Local Authority due to potential impact on Ancient Woodland |  |  | {D5}="Yes" | Phase 2-3 | Client | FALSE | D5="Yes" | ""="Yes" | D5 = "" Is there an Ancient Woodland Site near (<50m) or within the project area?
[5 empty] | T43 | Biodiversity | Net Gain | Demonstrate a positive impact on biodiversity (this may be through the biodiversity metric) as part of the PEA scope of works (preferable) or as a standalone activity | <a href="http://nepubprod.appspot.com/publication/5850908674228224" target=_"blank">The Biodiversity Metric 2.0 (JP029)</a> | ! Mandated under NR/L2/ENV/015, Section 6.1 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [{A1}="Yes"¦¦VLOOKUP({P2},tblProjectValues,2,False)>1]&&[{S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Yes"¦¦{S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Maybe"] | Phase 2-3 | Client / Designer | FALSE | AND(OR(A1="Yes",VLOOKUP(P2,tblProjectValues,2,False)>1),OR(OR(S1="Yes",S2="Yes",S3="Yes",S4="Yes",S5="Yes",S6="Yes",S7="Yes",S8="Yes",S9="Yes",S10="Yes",S11="Yes",S12="Yes",S13="Yes",S14="Yes",S15="Yes",S16="Yes",S17="Yes",S18="Yes",S19="Yes",S20="Yes"),OR(S1="Maybe",S2="Maybe",S3="Maybe",S4="Maybe",S5="Maybe",S6="Maybe",S7="Maybe",S8="Maybe",S9="Maybe",S10="Maybe",S11="Maybe",S12="Maybe",S13="Maybe",S14="Maybe",S15="Maybe",S16="Maybe",S17="Maybe",S18="Maybe",S19="Maybe",S20="Maybe"))) | AND(OR(""="Yes",VLOOKUP("Select from drop down list…",tblProjectValues,2,False)>1),OR(OR(""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes"),OR(""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe"))) | A1 = "" Will vegetation management and/or land take impact an area >1,500m2? P2 = "Select from drop down list…" Estimated Project Value (Development, Design and Construction) S1 = "" The project involves vegetation management and/or land take. S2 = "" The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s). S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S14 = "" The project involves replacing and/or installing new lineside S&T assets (e.g. signal, signal box, signage, REB, location cabinet, GSM mast, etc.) S15 = "" The project involves replacing and/or installing Under Track Crossing (UTX)/Under Road Crossing (URX). S16 = "" The project involves replacing and/or installing new S&T cable route S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing S19 = "" The project involves replacing or installing new lineside E&P assets (e.g. DNO, lighting, etc.) S20 = "" The project involves replacing and/or installing new E&P cable route S1 = "" The project involves vegetation management and/or land take. S2 = "" The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s). S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S14 = "" The project involves replacing and/or installing new lineside S&T assets (e.g. signal, signal box, signage, REB, location cabinet, GSM mast, etc.) S15 = "" The project involves replacing and/or installing Under Track Crossing (UTX)/Under Road Crossing (URX). S16 = "" The project involves replacing and/or installing new S&T cable route S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing S19 = "" The project involves replacing or installing new lineside E&P assets (e.g. DNO, lighting, etc.) S20 = "" The project involves replacing and/or installing new E&P cable route
[5 empty] | T44 | Biodiversity | Net Gain | Assess opportunity to integrate green/blue infrastructure principles into design options (e.g. green wall, green roof, vegetated retaining wall and other nature-based engineering solutions) |  |  | {S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Yes"¦¦{S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Maybe" | Phase 2-3 | Designer / Principal Contractor | FALSE | OR(OR(S1="Yes",S2="Yes",S3="Yes",S4="Yes",S5="Yes",S6="Yes",S7="Yes",S8="Yes",S9="Yes",S10="Yes",S11="Yes",S12="Yes",S13="Yes",S14="Yes",S15="Yes",S16="Yes",S17="Yes",S18="Yes",S19="Yes",S20="Yes"),OR(S1="Maybe",S2="Maybe",S3="Maybe",S4="Maybe",S5="Maybe",S6="Maybe",S7="Maybe",S8="Maybe",S9="Maybe",S10="Maybe",S11="Maybe",S12="Maybe",S13="Maybe",S14="Maybe",S15="Maybe",S16="Maybe",S17="Maybe",S18="Maybe",S19="Maybe",S20="Maybe")) | OR(OR(""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes"),OR(""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe")) | S1 = "" The project involves vegetation management and/or land take. S2 = "" The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s). S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S14 = "" The project involves replacing and/or installing new lineside S&T assets (e.g. signal, signal box, signage, REB, location cabinet, GSM mast, etc.) S15 = "" The project involves replacing and/or installing Under Track Crossing (UTX)/Under Road Crossing (URX). S16 = "" The project involves replacing and/or installing new S&T cable route S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing S19 = "" The project involves replacing or installing new lineside E&P assets (e.g. DNO, lighting, etc.) S20 = "" The project involves replacing and/or installing new E&P cable route S1 = "" The project involves vegetation management and/or land take. S2 = "" The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s). S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S14 = "" The project involves replacing and/or installing new lineside S&T assets (e.g. signal, signal box, signage, REB, location cabinet, GSM mast, etc.) S15 = "" The project involves replacing and/or installing Under Track Crossing (UTX)/Under Road Crossing (URX). S16 = "" The project involves replacing and/or installing new S&T cable route S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing S19 = "" The project involves replacing or installing new lineside E&P assets (e.g. DNO, lighting, etc.) S20 = "" The project involves replacing and/or installing new E&P cable route
[5 empty] | T45 | Biodiversity | Net Gain | Secure budget and resources to deliver Biodiversity Net Gain, including long term habitat management | <a href="http://networkrailstandards/StandardHeaderView.aspx?id=32422" target=_"blank">NR/L2/ENV/122/02 Habitat Management Plan</a> | ! Apply the Biodiversity Mitigation Strategy ! | [{S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Yes"¦¦{S1¦S2¦S3¦S4¦S5¦S6¦S7¦S8¦S9¦S10¦S11¦S12¦S13¦S14¦S15¦S16¦S17¦S18¦S19¦S20}="Maybe"] | Phase 2-3 | Client | FALSE | OR(OR(S1="Yes",S2="Yes",S3="Yes",S4="Yes",S5="Yes",S6="Yes",S7="Yes",S8="Yes",S9="Yes",S10="Yes",S11="Yes",S12="Yes",S13="Yes",S14="Yes",S15="Yes",S16="Yes",S17="Yes",S18="Yes",S19="Yes",S20="Yes"),OR(S1="Maybe",S2="Maybe",S3="Maybe",S4="Maybe",S5="Maybe",S6="Maybe",S7="Maybe",S8="Maybe",S9="Maybe",S10="Maybe",S11="Maybe",S12="Maybe",S13="Maybe",S14="Maybe",S15="Maybe",S16="Maybe",S17="Maybe",S18="Maybe",S19="Maybe",S20="Maybe")) | OR(OR(""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes"),OR(""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe")) | S1 = "" The project involves vegetation management and/or land take. S2 = "" The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s). S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S14 = "" The project involves replacing and/or installing new lineside S&T assets (e.g. signal, signal box, signage, REB, location cabinet, GSM mast, etc.) S15 = "" The project involves replacing and/or installing Under Track Crossing (UTX)/Under Road Crossing (URX). S16 = "" The project involves replacing and/or installing new S&T cable route S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing S19 = "" The project involves replacing or installing new lineside E&P assets (e.g. DNO, lighting, etc.) S20 = "" The project involves replacing and/or installing new E&P cable route S1 = "" The project involves vegetation management and/or land take. S2 = "" The project involves modifying, replacing and/or building site compound(s), haul road(s) and/or access point(s). S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S14 = "" The project involves replacing and/or installing new lineside S&T assets (e.g. signal, signal box, signage, REB, location cabinet, GSM mast, etc.) S15 = "" The project involves replacing and/or installing Under Track Crossing (UTX)/Under Road Crossing (URX). S16 = "" The project involves replacing and/or installing new S&T cable route S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing S19 = "" The project involves replacing or installing new lineside E&P assets (e.g. DNO, lighting, etc.) S20 = "" The project involves replacing and/or installing new E&P cable route
[5 empty] | T46 | Contaminated Land |  | Commission Preliminary Risk Assessment (PRA) based on a desktop study and site walkover to develop a Source-Pathway-Receptor Conceptual Model | Integrate findings and recommendations from Preliminary Risk Assessment (PRA) into Option Selection/Outline Design/Detailed Design/Construction including avoidance and/or control measures within Design & Construction ESMP <br> <br><a href="https://www.claire.co.uk/useful-government-legislation-and-guidance-by-country/198-doe-industry-profiles" target=_"blank"> Department of Environment (DoE) Industry Profiles</a> (published in 1995) provide information on the processes, materials and waste associated with individual industries with regard to land contamination. <br> <br>If Mining Risk identified, complete the <a href="https://networkrail.sharepoint.com/sites/myconnect/ste/Pages/Mining.aspx" target=_"blank">Phase 1 Mining Report Request Form</a> <br>And submit it to <a href="nation​​alminingengineer@networkrail.co.uk" target=_"blank"> | ! Mandated under NR/L2/ENV/015, Section 6.2 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Yes"¦¦{S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Maybe" | Phase 2-3 | Client / Designer | FALSE | OR(OR(S4="Yes",S5="Yes",S6="Yes",S7="Yes",S8="Yes",S11="Yes",S12="Yes",S13="Yes",S16="Yes"),OR(S4="Maybe",S5="Maybe",S6="Maybe",S7="Maybe",S8="Maybe",S11="Maybe",S12="Maybe",S13="Maybe",S16="Maybe")) | OR(OR(""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes"),OR(""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe")) | S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S16 = "" The project involves replacing and/or installing new S&T cable route S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S16 = "" The project involves replacing and/or installing new S&T cable route
[5 empty] | T47 | Contaminated Land |  | Include adequate sampling and chemical testing into Ground Investigation (GI) scope of works based on PRA findings. |  | ! Waste Acceptance Criteria (WAC) Testing not suitable for land contamination assessment ! | [{S3}="Yes"¦¦{S3}="Maybe"]&&[{S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Yes"¦¦{S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Maybe"] | Phase 2-3 | Client / Designer | FALSE | AND(OR(S3="Yes",S3="Maybe"),OR(OR(S4="Yes",S5="Yes",S6="Yes",S7="Yes",S8="Yes",S11="Yes",S12="Yes",S13="Yes",S16="Yes"),OR(S4="Maybe",S5="Maybe",S6="Maybe",S7="Maybe",S8="Maybe",S11="Maybe",S12="Maybe",S13="Maybe",S16="Maybe"))) | AND(OR(""="Yes",""="Maybe"),OR(OR(""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes"),OR(""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe"))) | S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) S3 = "" The project involves intrusive site investigation(s) (e.g. ground Investigation, track bed investigation, structural coring, etc.) S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S16 = "" The project involves replacing and/or installing new S&T cable route S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S16 = "" The project involves replacing and/or installing new S&T cable route
[5 empty] | T48 | Contaminated Land |  | Apply Network Rail Standard NR/L3/ENV/044 to assess risk of track bed contamination (including desktop study and site walkover) and determine the need for sampling and chemical testing during track bed investigation (TBI). | <a href="http://networkrailstandards/StandardHeaderView.aspx?id=28955" target=_"blank">Track Maintenance Renewal or Alteration - Used Ballast and Excavation Waste Handling</a> (NR/L3/ENV/044) | ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {S9¦S10}="Yes"¦¦{S9¦S10}="Maybe" | Phase 2-3 | Designer / Principal Contractor | FALSE | OR(OR(S9="Yes",S10="Yes"),OR(S9="Maybe",S10="Maybe")) | OR(OR(""="Yes",""="Yes"),OR(""="Maybe",""="Maybe")) | S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation)
[5 empty] | T50 | Contaminated Land |  | Commission further site investigations if required based on findings and recommendations from PRA |  |  | {S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Yes"¦¦{S4¦S5¦S6¦S7¦S8¦S11¦S12¦S13¦S16}="Maybe" | Phase 2-3 | Client / Principal Contractor | FALSE | OR(OR(S4="Yes",S5="Yes",S6="Yes",S7="Yes",S8="Yes",S11="Yes",S12="Yes",S13="Yes",S16="Yes"),OR(S4="Maybe",S5="Maybe",S6="Maybe",S7="Maybe",S8="Maybe",S11="Maybe",S12="Maybe",S13="Maybe",S16="Maybe")) | OR(OR(""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes"),OR(""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe",""="Maybe")) | S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S16 = "" The project involves replacing and/or installing new S&T cable route S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S6 = "" The project involves other civils work (e.g. foundations, fencing, walkway, etc.). S7 = "" The project involves modifying or stabilising earthworks or other geotechnical asset (e.g. embankment, cutting, scouring protection). S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S11 = "" The project involves new or modified sidings S12 = "" The project involves replacing or installing new OLE S13 = "" The project involves replacing or installing new feeder station or sub-station S16 = "" The project involves replacing and/or installing new S&T cable route
[5 empty] | T51 | Contaminated Land |  | Commission a Piling Risk Assessment to prevent opening a pollution pathway into the groundwater |  |  | {A13}="Yes" | Phase 2-3 | Principal Contractor | FALSE | A13="Yes" | ""="Yes" | A13 = "" Will the project require piling, boring or drilling?
[5 empty] | T52 | Emissions to Air |  | Commission Operational Air Quality Assessment and liaise with Local Authority |  | ! Mandated under NR/L2/ENV/015, Section 6.3 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {D11&A5}="Yes" | Phase 2-3 | Client | FALSE | AND(D11="Yes",A5="Yes") | AND(""="Yes",""="Yes") | D11 = "" Is the project area within an Air Quality Management Area (AQMA)? A5 = "" Will the project contribute to local air pollution from diesel rolling stock during operation (e.g. passenger train idling at new depot or expanded sidings, freight train idling at new signal location, etc.)?
[5 empty] | T53 | Emissions to Air |  | Undertake Construction Air Quality Assessment |  | ! Mandated under NR/L2/ENV/015, Section 6.3 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {D11&A6}="Yes" | Phase 2-3 | Principal Contractor | FALSE | AND(D11="Yes",A6="Yes") | AND(""="Yes",""="Yes") | D11 = "" Is the project area within an Air Quality Management Area (AQMA)? A6 = "" Will the project contribute to local air pollution (including dust and fumes) during construction (from earthworks, plant and equipment as well as vehicles for the transport of materials, etc.)?
[5 empty] | T54 | Emissions to Air |  | Specify low emissions vehicles, plant and equipment (Euro 6 engine, hybrid/solar generator, Non-Road Mobile Machinery (NRMM) requirements in London, etc.) as part of Contract & Procurement |  |  | {A6}="Yes" | Phase 2-3 | Client / Principal Contractor | FALSE | A6="Yes" | ""="Yes" | A6 = "" Will the project contribute to local air pollution (including dust and fumes) during construction (from earthworks, plant and equipment as well as vehicles for the transport of materials, etc.)?
[5 empty] | T56 | Emissions to Air |  | Consider air insulated or non-SF6 gas insulated transformer into business case development |  |  | {S13}="Yes"¦¦{S13}="Maybe" | Phase 1 | Client / Designer | FALSE | OR(S13="Yes",S13="Maybe") | OR(""="Yes",""="Maybe") | S13 = "" The project involves replacing or installing new feeder station or sub-station S13 = "" The project involves replacing or installing new feeder station or sub-station
[5 empty] | T57 | Noise and Vibration |  | Commission Operational Noise & Vibration Impact Assessment for compliance with Noise Insulation Regs and Railway Act (due diligence) |  | ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [{S10¦S11}="Yes"¦¦{S10¦S11}="Maybe"]¦¦[{A7&D17}="Yes"] | Phase 2-3 | Client | FALSE | OR(OR(OR(S10="Yes",S11="Yes"),OR(S10="Maybe",S11="Maybe")),AND(A7="Yes",D17="Yes")) | OR(OR(OR(""="Yes",""="Yes"),OR(""="Maybe",""="Maybe")),AND(""="Yes",""="Yes")) | S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S11 = "" The project involves new or modified sidings S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S11 = "" The project involves new or modified sidings A7 = "" Will the project contribute to an increase local noise & vibration levels during operation (e.g. new or increased maintenance depot activities, additional rolling stock, rolling stock idling at new signal location, etc.)? D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value
[5 empty] | T58 | Noise and Vibration |  | Liaise with Local Authority as well as TOC/FOC to identify and agree mitigation measures based on findings and recommendations from Operational Noise & Vibration Impact Assessment |  |  | [{S10¦S11}="Yes"¦¦{S10¦S11}="Maybe"]¦¦[{A7&D17}="Yes"] | Phase 2 | Client | FALSE | OR(OR(OR(S10="Yes",S11="Yes"),OR(S10="Maybe",S11="Maybe")),AND(A7="Yes",D17="Yes")) | OR(OR(OR(""="Yes",""="Yes"),OR(""="Maybe",""="Maybe")),AND(""="Yes",""="Yes")) | S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S11 = "" The project involves new or modified sidings S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S11 = "" The project involves new or modified sidings A7 = "" Will the project contribute to an increase local noise & vibration levels during operation (e.g. new or increased maintenance depot activities, additional rolling stock, rolling stock idling at new signal location, etc.)? D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value
[5 empty] | T59 | Noise and Vibration |  | Assess potential adverse Noise Impact of Public Address and/or Warning system on nearby residents and design mitigation measures |  |  | [{A9¦A10}="Yes"]&&[{D17¦D17.1}="Yes"] | Phase 2 | Designer | FALSE | AND(OR(A9="Yes",A10="Yes"),OR(D17="Yes",D17.1="Yes")) | AND(OR(""="Yes",""="Yes"),OR(""="Yes",""="Yes")) | A9 = "" Will the project require the installation of a Public Address (PA) system? A10 = "" Will the project require the installation of an Automatic Track Warning System? D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value D17.1 = "" If No, within 250m?
[5 empty] | T60 | Noise and Vibration |  | Undertake Construction Noise & Vibration Impact Assessment as per NR/L2/ENV/121 | <a href="http://networkrailstandards/StandardHeaderView.aspx?id=31047" target=_"blank">Managing Environmental and Social Impact of Noise and Vibration</a> (NR/L2/ENV/121 ) | ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [{A8}="Yes"]&&[{D17¦D17.1}="Yes"] | Phase 2 | Principal Contractor | FALSE | AND(A8="Yes",OR(D17="Yes",D17.1="Yes")) | AND(""="Yes",OR(""="Yes",""="Yes")) | A8 = "" Will the project contribute to an increase local noise & vibration levels during construction (excavation/demolition works, tamping, piling, cutting, drilling, etc.)? D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value D17.1 = "" If No, within 250m?
[5 empty] | T61 | Noise and Vibration |  | Liaise with Local Authority and apply for Section 61 Consent based on Construction Noise & Vibration Impact Assessment findings and recommendations (e.g. when noisy works at unsociable hours are unavoidable) |  | ! Mandated under NR/L2/ENV/015, Section 6.6 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [{A8}="Yes"]&&[{D17¦D17.1}="Yes"] | Phase 2 | Principal Contractor | FALSE | AND(A8="Yes",OR(D17="Yes",D17.1="Yes")) | AND(""="Yes",OR(""="Yes",""="Yes")) | A8 = "" Will the project contribute to an increase local noise & vibration levels during construction (excavation/demolition works, tamping, piling, cutting, drilling, etc.)? D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value D17.1 = "" If No, within 250m?
[5 empty] | T63 | Noise and Vibration |  | Identify Best Practicable Means (BPM) such as white noise reversing alarms, battery-powered plant and equipment, planning noisy works outside inconsiderate hours, etc. to minimise impact As Low as Reasonably Practicable (ALARP) | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2018/06/Noise-nuisance-and-disturbance-Guidance-Note.pdf" target=_"blank">'Noise nuisance and disturbance – Guidance Note</a> |  | [{A8}="Yes"]&&[{D17¦D17.1}="Yes"] | Phase 2-3 | Principal Contractor | FALSE | AND(A8="Yes",OR(D17="Yes",D17.1="Yes")) | AND(""="Yes",OR(""="Yes",""="Yes")) | A8 = "" Will the project contribute to an increase local noise & vibration levels during construction (excavation/demolition works, tamping, piling, cutting, drilling, etc.)? D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value D17.1 = "" If No, within 250m?
[5 empty] | T64 | Dust, odour and lighting |  | Undertake lighting impact assessment in line with NR guidance note 'Minimising impact of artificial lighting on people and wildlife' and include adequate mitigation measures into design based on findings and recommendations | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2020/02/NR_GN_ESD26-Minimising-impact-of-artificial-light-on-people-and-wildlife-v1-Feb-2020.pdf" target=_"blank">NR_GN_ESD26 – Minimising impact of artificial light on people and wildlife</a> |  | [{A11¦S19}="Yes"]&&[{D17¦D2}="Yes"] | Phase 2-3 | Designer | FALSE | AND(OR(A11="Yes",S19="Yes"),OR(D17="Yes",D2="Yes")) | AND(OR(""="Yes",""="Yes"),OR(""="Yes",""="Yes")) | A11 = "" Could the project require installation of temporary (i.e. construction) and/or permanent (i.e. operation) outdoor artificial lighting? S19 = "" The project involves replacing or installing new lineside E&P assets (e.g. DNO, lighting, etc.) D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value D2 = "" Are there records of protected species within 1km of the project area? ! Absence of records does not confirm absence of protected species !
[5 empty] | T162 | Dust, odour and lighting |  | Ensure design includes measures to reduce dust and odour to As Low as Reasonably Practicable (ALARP) |  |  | {A44}="Yes"¦¦{A44}="Don't Know" |  |  | FALSE | OR(A44="Yes",A44="Don't Know") | OR(""="Yes",""="Don't Know") | A44 = "" Is there a risk of dust or odour emissions? A44 = "" Is there a risk of dust or odour emissions?
[5 empty] | T65 | Pollution of land / water |  | Provide containment in accordance with The Control of Pollution (Oil Storage) Regulations 2001, or equivalent in Wales and Scotland | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2020/06/ESD-Briefing-Note-Transformers-Apr-18-FINAL-v-3-1.pdf" target=_"blank">ESD Briefing Note - Transformers</a> |  | {A2}="Yes" | Phase 2-3 | Designer/Principal Contractor | FALSE | A2="Yes" | ""="Yes" | A2 = "" Will the project require handling >200L of oil and/or fuel during construction (e.g. diesel generator, refuelling tank, oil-filled High Voltage cable) and/or operation (e.g. transformer, refuelling depot)?
[5 empty] | T66 | Pollution of land / water |  | Apply hierarchy of control for hazardous substances through elimination and substitution for less hazardous to health and the environment |  |  | {A3}="Yes" | Phase 3 | Principal Contractor | FALSE | A3="Yes" | ""="Yes" | A3 = "" Will the project require substances hazardous to the environment (other than oil and fuel) during construction and/or operation (e.g. solvent, herbicide, etc.)?
[5 empty] | T67 | Pollution of land / water |  | Develop Incident Response Plan (IRP) | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2018/06/Pollution-prevention-land-and-water-Guidance-Note.pdf" target=_"blank">Pollution prevention (land and water) – Guidance Note</a> |  | {N1}="No"&&{S21&S22}<>"Yes" | Phase 2-3 | Designer / Principal Contractor | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
[5 empty] | T68 | Pollution of land / water |  | Avoid spraying of herbicide near watercourses and apply for permission from the Regulator if unavoidable |  |  | {S1}="Yes"¦¦{S1}="Maybe"&&{D9}="Yes"&&{A3}="Yes"¦¦{A3}="Don’t' Know" | Phase 3 | Principal Contractor | FALSE | AND(AND(OR(OR(S1="Yes",S1="Maybe",D9="Yes",A3="Yes",A3="Don’t' Know")))) | AND(AND(OR(OR(""="Yes",""="Maybe",""="Yes",""="Yes",""="Don’t' Know")))) | S1 = "" The project involves vegetation management and/or land take. S1 = "" The project involves vegetation management and/or land take. D9 = "" Is the project area within 10m of a sea, estuary, watercourse (main river or ordinary watercourse such as open drainage, brook, etc.) or other surface water body (pond, canal, lake, loch, reservoir, etc.)? A3 = "" Will the project require substances hazardous to the environment (other than oil and fuel) during construction and/or operation (e.g. solvent, herbicide, etc.)? A3 = "" Will the project require substances hazardous to the environment (other than oil and fuel) during construction and/or operation (e.g. solvent, herbicide, etc.)?
[5 empty] | T69 | Pollution of land / water |  | Complete ballast de-icer risk assessment process | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2020/08/SCO-ENV-F001-Environmental-Site-Survey-Form-Issue-5.doc" target=_"blank">SCO Environmental Site Survey Form></a> |  | {A4}="Yes" | Phase 3 | Principal Contractor | FALSE | A4="Yes" | ""="Yes" | A4 = "" Will the project require delivery of anti-icer treated rail ballast (based on programme of works)?
[5 empty] | T70 | Pollution of land / water |  | Interrogate the Asbestos Risk Management System (ARMS) and PCB Register | <a href="https://arms.networkrail.co.uk/" target=_"blank">Asbestos Risk Management System (ARMS)</a> <br> <br><a href="https://sddata.hub.networkrail.co.uk/Enviroment/Forms/AllItems.aspx?RootFolder=%2FEnviroment%2FPCB%20Register&FolderCTID=0x012000FB9F7BACE3C81643A83B95403574EB51&View=%7B4860448E%2D5285%2D40C4%2D97DB%2D1F16E4BF0E62%7D" target=_"blank">PCB Register</a> <br> <br>PCB Register Holder: Karen Morris (karen.morris2@networkrail.co.uk) |  | {A19}="Yes" | Phase 1 - 2 | Client | FALSE | A19="Yes" | ""="Yes" | A19 = "" Will existing building, structure or equipment need to be decommissioned, demounted, demolished or stripped-out as part of the project?
[5 empty] | T71 | Pollution of land / water |  | Update Land & Consents Strategy and associated Commitments to consider water discharge permit, land drainage consent for discharge and and/or trade effluent discharge consent |  |  | [{S8}="Yes"¦¦{S8}="Maybe"]¦¦[{A12}="Yes"] | Phase 2 -3 | Client | FALSE | OR(OR(S8="Yes",S8="Maybe"),A12="Yes") | OR(OR(""="Yes",""="Maybe"),""="Yes") | S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) A12 = "" Will the project require temporary or permanent water discharge to surface water or sewerage system?
[5 empty] | T72 | Energy and Carbon | Whole life carbon | Undertake Whole Life Carbon Assessment using the Rail Carbon Tool | Integrate findings and recommendations from Capital Carbon Assessment into Option Selection/Outline Design/Detailed Design/Construction <br> <br><a href="https://safety.networkrail.co.uk/wp-content/uploads/2019/05/capital-carbon-ESD07-v.11.pdf" target=_"blank">Capital Carbon Guidance Note</a> <br> <br><a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/energy-and-carbon-management/designing-for-low-whole-life-carbon/rail-carbon-tool/" target=_"blank">Rail Carbon Tool</a> | ! Mandated under NR/L2/ENV/015, Section 6.4.2 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [{N1}="No"&&{S21&S22}<>"Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>3 | Phase 2-3 | Designer / Principal Contractor | FALSE | AND(AND(N1="No",AND(S21<>"Yes",S22<>"Yes")),VLOOKUP(P2,tblProjectValues,2,False)>3) | AND(AND("Yes"="No",AND(""<>"Yes",""<>"Yes")),VLOOKUP("Select from drop down list…",tblProjectValues,2,False)>3) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
[5 empty] | T73 | Energy and Carbon | Energy and operational carbon | Undertake Operational Energy Assessment using an industry approved methodology such as the Chartered Institute of Building Services Engineers (CIBSE) TM54 | Integrate findings and recommendations from Operational Energy Assessment into Option Selection/Outline Design/Detailed Design/Construction <br> <br>'<a href="https://safety.networkrail.co.uk/wp-content/uploads/2018/06/Operational-carbon-Guidance-Note.pdf" target=_"blank">Operational carbon – Guidance Note</a> | ! Mandated under NR/L2/ENV/015, Section 6.4.3 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [{S5}="Yes"¦¦{A43}="No"]&&VLOOKUP({P2},tblProjectValues,2,False)>3 | Phase 1-2 | Designer | FALSE | AND(OR(S5="Yes",A43="No"),VLOOKUP(P2,tblProjectValues,2,False)>3) | AND(OR(""="Yes",""="No"),VLOOKUP("Select from drop down list…",tblProjectValues,2,False)>3) | S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). A43 = "" Have you identified opportunities to reduce energy and fuel usage?
[5 empty] | T76 | Energy and Carbon | Low environmental impact products | Specify low carbon troughing products and/or power cables |  |  | {S16¦S20}="Yes" | Phase 2-3 | Designer / Principal Contractor | FALSE | OR(S16="Yes",S20="Yes") | OR(""="Yes",""="Yes") | S16 = "" The project involves replacing and/or installing new S&T cable route S20 = "" The project involves replacing and/or installing new E&P cable route
[5 empty] | T78 | Energy and Carbon | Energy and operational carbon | Integrate energy-efficient solutions into buildings and structures' design (PV, LED lighting, GHP, etc.) |  |  | {S4¦S5}="Yes"¦¦{S4¦S5}="Maybe" | Phase 2-3 | Designer | FALSE | OR(OR(S4="Yes",S5="Yes"),OR(S4="Maybe",S5="Maybe")) | OR(OR(""="Yes",""="Yes"),OR(""="Maybe",""="Maybe")) | S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S4 = "" The project involves modifying, replacing and/or installing new structure (e.g. bridge, footbridge, viaduct, tunnel, platform). S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot).
[5 empty] | T79 | Energy and Carbon | Energy and operational carbon | Integrate energy-efficient solutions (e.g. solar panel, forced-air temperature control instead of Air Con, LED lighting, etc.) to power lineside equipment |  |  | {A14}="Yes" | Phase 2 | Designer | FALSE | A14="Yes" | ""="Yes" | A14 = "" Will the project involve modifying, replacing and/or providing new operational power supply to lineside equipment?
[5 empty] | T80 | Energy and Carbon | Energy and operational carbon | Investigate DNO supply and electricity meters installation ahead of construction |  |  | {A15}="Yes" | Phase 2 | Client / Principal Contractor | FALSE | A15="Yes" | ""="Yes" | A15 = "" Will the project require access to a power supply during construction?
[5 empty] | T81 | Energy and Carbon | Energy and operational carbon | Specify renewable energy power and energy efficient technologies where technologies exist (e.g. battery power, solar power LED technology, etc.) as part of Contract & Procurement to reduce emissions. |  |  | {A15}="Yes" | Phase 2 | Client / Principal Contractor | FALSE | A15="Yes" | ""="Yes" | A15 = "" Will the project require access to a power supply during construction?
[5 empty] | T171 | Energy and Carbon | Energy and operational carbon | Contact local Energy and Carbon team for further support |  |  | {D31}="No" |  |  | FALSE | D31="No" | ""="No" | D31 = "" Have opportunities been identified to support carbon reduction commitments and the decarbonisation programme?
[5 empty] | T85 | Materials - Responsible Sourcing | Concrete and aggregates | Specify responsibly sourced concrete and/or aggregates (e.g. BES6001 certification) into Contract & Procurement |  | ! Mandated under NR/L2/ENV/015, Section 6.5.2 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [{A16¦A17}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>3 | Phase 2 | Client / Principal Contractor | FALSE | AND(OR(A16="Yes",A17="Yes"),VLOOKUP(P2,tblProjectValues,2,False)>3) | AND(OR(""="Yes",""="Yes"),VLOOKUP("Select from drop down list…",tblProjectValues,2,False)>3) | A16 = "" Will construction (including site compounds) require import of large volumes of engineering fill and/or aggregates (>100t), including track bed material? A17 = "" Will construction require significant quantities of concrete and/or steel (>100t), including track material?
[5 empty] | T86 | Materials - Responsible Sourcing | Responsibly sourced timber | Specify responsibly sourced timber (e.g. FSC/PEFC certification) into Contract & Procurement | FSC certification is required for timber products sourced from vulnerable regions such as Africa and South America whilst PEFC can also be used for timber from lower risk areas such as Europe and North America. <br> <br><a href="https://safety.networkrail.co.uk/wp-content/uploads/2015/07/Network-Rail-Responsible-Timber-Policy.pdf" target=_"blank">Network Rail Responsible Timber Policy</a> <br> <br><a href="https://safety.networkrail.co.uk/wp-content/uploads/2018/06/Responsibly-sourced-timber-Guidance-note-1.pdf" target=_"blank">Responsibly sourced timber – Guidance note</a> | ! Mandated under NR/L2/ENV/015, Section 6.5.2.3 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {A18}="Yes" | Phase 2 | Client / Principal Contractor | FALSE | A18="Yes" | ""="Yes" | A18 = "" Will construction require timber or other forest products for temporary (e.g. hoarding, formwork) or permanent use (e.g. structural frame, cladding) other than rail sleepers?
[5 empty] | T87 | Materials - Responsible Sourcing |  | Specify no single use plastic (e.g. plastic-free packaging) into Contract & Procurement |  |  | {N1}="No"&&{S21&S22}<>"Yes" | Phase 2 | Client / Principal Contractor | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
[5 empty] | T88 | Materials - Responsible Sourcing |  | Consider rail and river networks as alternatives to road transport for large quantities of materials |  |  | [{A16¦A17}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>3 | Phase 2 | Client / Principal Contractor | FALSE | AND(OR(A16="Yes",A17="Yes"),VLOOKUP(P2,tblProjectValues,2,False)>3) | AND(OR(""="Yes",""="Yes"),VLOOKUP("Select from drop down list…",tblProjectValues,2,False)>3) | A16 = "" Will construction (including site compounds) require import of large volumes of engineering fill and/or aggregates (>100t), including track bed material? A17 = "" Will construction require significant quantities of concrete and/or steel (>100t), including track material?
[5 empty] | T90 | Circular economy |  | Undertake Resource Efficiency Assessment/ Workshop to minimise materials need, prevent waste and maximise reuse through LEAN design and value engineering | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2017/07/Resource-Efficiency-Workshop-Slides.pptx" target=_"blank">Resource Efficiency Workshop</a> <br> <br><a href="https://safety.networkrail.co.uk/wp-content/uploads/2017/06/Guidance-on-Design-out-Waste-Workshop.pdf" target=_"blank">Design Out Waste Workshop</a> <br> <br>Integrate findings from Resource Efficiency & Design Out Waste Workshop into Option Selection/Outline Design/Detailed Design/Construction | ! Mandated under NR/L2/ENV/015, Section 6.5.1 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [{A19¦A20¦A21}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>=6 | Phase 1-2 | Designer / Principal Contractor | FALSE | AND(OR(A19="Yes",A20="Yes",A21="Yes"),VLOOKUP(P2,tblProjectValues,2,False)>=6) | AND(OR(""="Yes",""="Yes",""="Yes"),VLOOKUP("Select from drop down list…",tblProjectValues,2,False)>=6) | A19 = "" Will existing building, structure or equipment need to be decommissioned, demounted, demolished or stripped-out as part of the project? A20 = "" Are the construction works likely to generate significant volumes of demolition and/or excavation material (>100 tonnes)? A21 = "" Are the works likely to generate significant volumes of construction waste (>100 tonnes) other than demolition and/or excavation material (e.g. plastic, timber or cardboard packaging; steel, timber, plastic off cuts; food or office waste, grit blasting waste; silt or sludge from drainage works; excess concrete)?
[5 empty] | T92 | Waste |  | Apply Network Rail Standard NR/L3/ENV/044 for track bed waste classification by Route Services Environment Team | <a href="http://networkrailstandards/StandardHeaderView.aspx?id=28955" target=_"blank">Track Maintenance Renewal or Alteration - Used Ballast and Excavation Waste Handling</a> (NR/L3/ENV/044) | ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {S9¦S10}="Yes"¦¦{S9¦S10}="Maybe" | Phase 2-3 | Designer / Principal Contractor | FALSE | OR(OR(S9="Yes",S10="Yes"),OR(S9="Maybe",S10="Maybe")) | OR(OR(""="Yes",""="Yes"),OR(""="Maybe",""="Maybe")) | S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation) S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) S10 = "" The project involves plain line extension (e.g. new track line, new loop, grade separation)
[5 empty] | T93 | Waste |  | Undertake waste classification prior disposal in accordance with the EA technical guidance WM3 (including representative sampling and chemical testing for mirror haz/non haz waste e.g. excavated material) | <a href="https://www.gov.uk/government/publications/waste-classification-technical-guidance" target=_"blank">Technical Guidance WM3 - Guidance on the classification and assessment of waste</a> | ! Waste Acceptance Criteria (WAC) testing is NOT suitable for waste classification ! | {N1}="No"&&{S21&S22}<>"Yes" | Phase 3 | Principal Contractor | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
[5 empty] | T94 | Waste |  | Maximise waste avoidance and reuse using: - SurPlus - Obtain or transfer railway assets - Quality Protocol - Produce aggregates from inert waste - CLAIRE Register of Materials - Look for Donor and/or Receiver Sites - Waste Exemptions - Consult the EA Public Register for sites with U1 Exemption (Reuse of Waste in Construction) | <a href="https://surplus-web-app-prod.22c8.nwr-prod.openshiftapps.com/#/" target=_"blank">Surplus: NR App and/or Online</a> (using NR Active Directory login) <br> <br><a href="https://www.claire.co.uk/projects-and-initiatives/cl-aire-register-of-materials" target=_"blank">CLAIRE Register of Materials</a> <br> <br><a href="https://www.gov.uk/government/publications/quality-protocol-production-of-aggregates-from-inert-waste" target=_"blank">Quality Protocol</a> <br> <br><a href="https://environment.data.gov.uk/public-register/view/search-waste-exemptions" target=_"blank">EA public register</a> <br> <br><a href="https://www.gov.uk/guidance/register-your-waste-exemptions-environmental-permits" target=_"blank">Waste exemptions</a> |  | {A19¦A20¦A21}="Yes" | Phase 2-3 | Designer / Principal Contractor | FALSE | OR(A19="Yes",A20="Yes",A21="Yes") | OR(""="Yes",""="Yes",""="Yes") | A19 = "" Will existing building, structure or equipment need to be decommissioned, demounted, demolished or stripped-out as part of the project? A20 = "" Are the construction works likely to generate significant volumes of demolition and/or excavation material (>100 tonnes)? A21 = "" Are the works likely to generate significant volumes of construction waste (>100 tonnes) other than demolition and/or excavation material (e.g. plastic, timber or cardboard packaging; steel, timber, plastic off cuts; food or office waste, grit blasting waste; silt or sludge from drainage works; excess concrete)?
[5 empty] | T95 | Waste |  | Consider including the local heritage railway into the redundant asset process to give them the opportunity to bid for assets that could benefit their infrastructure. | <a href= "https://networkrail.sharepoint.com/sites/myconnect/routeservices/Pages/Redundant-Assets.aspx" target=_"blank">Disposal of Redundant Assets</a> (DORA) |  | {S9&A19&D16}="Yes" | Phase 2-3 | Client / Principal Contractor | FALSE | AND(S9="Yes",A19="Yes",D16="Yes") | AND(""="Yes",""="Yes",""="Yes") | S9 = "" The project involves repairing, modifying, decommissioning or renewing plain line and/or Switches & Crossings (including wet beds reballasting, timber wheel works, S&C abandonment) A19 = "" Will existing building, structure or equipment need to be decommissioned, demounted, demolished or stripped-out as part of the project? D16 = "" Is there a heritage railway near (<10km) the project area?
[5 empty] | T96 | Waste |  | Consider alternative Invasive Non-Native Species (e.g. Japanese Knotweed) soil treatment methods allowing reuse of excavated material on site or off-site disposal at the lower landfill tax rate. | INNS plant material or clean soil containing INNS plant material are not considered hazardous but must be disposed of in an authorised landfill. However if the area was treated with herbicide, excavated material could be hazardous and must be tested and classified in accordance with the EA WM3 Technical Guidance for waste classification. |  | {A20&D7}="Yes" | Phase 2-3 | Designer / Principal Contractor | FALSE | AND(A20="Yes",D7="Yes") | AND(""="Yes",""="Yes") | A20 = "" Are the construction works likely to generate significant volumes of demolition and/or excavation material (>100 tonnes)? D7 = "" Are there records of Japanese Knotweed, Giant Hogweed or Himalayan Balsam (Invasive Non-Native Species - INNS) near (<50m) or within the project area? ! Absence of records does not confirm absence of INNS ! Note: Other non-native invasive plant species (e.g. Cotoneaster, Rhododendron) must be considered as part of a Preliminary Ecological Appraisal (PEA)
[5 empty] | T97 | Waste | Polychlorinated bi-phenols | Manage insulating oil with potential traces of PCB in accordance with NR guidance note and disposal checklist | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2018/06/Polychlorinated-Biphenyls-Guidance-Note.pdf" target=_"blank">Polychlorinated Biphenyls (PCBs) – Guidance Note</a> <br> <br><a href="https://safety.networkrail.co.uk/wp-content/uploads/2018/08/PCBs-disposal-checklist-2016-1.xlsx" target=_"blank">PCB Oil and Contaminated Equipment Removal Checklist</a> |  | [{S13}="Yes"¦¦{S13}="Maybe"]&&[{A2¦A19}="Yes"] | Phase 3 | Principal Contractor | FALSE | AND(OR(S13="Yes",S13="Maybe"),OR(A2="Yes",A19="Yes")) | AND(OR(""="Yes",""="Maybe"),OR(""="Yes",""="Yes")) | S13 = "" The project involves replacing or installing new feeder station or sub-station S13 = "" The project involves replacing or installing new feeder station or sub-station A2 = "" Will the project require handling >200L of oil and/or fuel during construction (e.g. diesel generator, refuelling tank, oil-filled High Voltage cable) and/or operation (e.g. transformer, refuelling depot)? A19 = "" Will existing building, structure or equipment need to be decommissioned, demounted, demolished or stripped-out as part of the project?
[5 empty] | T98 | Waste |  | Develop Site Waste Management Plan (SWMP) including waste avoidance and reduction measures as well as details of waste carriers and disposal sites | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2018/03/Waste-management-ESD01-V.13.pdf" target=_"blank">Waste Management Guidance Note</a> <br> <br><a href="https://safety.networkrail.co.uk/wp-content/uploads/2018/02/Site-Waste-Management-Plan-What-you-need-to-know.pdf" target=_"blank">Site Waste Management Plan – What you need to know</a> | ! Mandated under NR/L2/ENV/015, Section 6.5.3.1 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {N1}="No"&&{S21&S22}<>"Yes" | Phase 2-3 | Designer / Principal Contractor | FALSE | AND(N1="No",AND(S21<>"Yes",S22<>"Yes")) | AND("Yes"="No",AND(""<>"Yes",""<>"Yes")) | N1 = "Yes" [Automated] No to ALL Project Scope activities = Non-Intrusive project S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons). S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
[5 empty] | T99 | Weather Resilience & Climate Change Adaptation (WRCCA) |  | Commission Weather Resilience & Climate Change Impact Assessment | Integrate findings and recommendations from Weather Resilience & Climate Change Impact Assessment into Option Selection/Outline Design/Detailed Design/Construction including avoidance and/or control measures within Design & Construction ESMP <br> <br><a href="https://safety.networkrail.co.uk/wp-content/uploads/2018/06/Weather-resilience-climate-change-impact-assessment-Guidance-Note.pdf" target=_"blank">Weather resilience & climate change impact assessment – Guidance Note</a> <br> <br><a href="https://safety.networkrail.co.uk/wp-content/uploads/2019/09/Climate-change-projections-Guidance-Note.pdf" target=_"blank">Climate change projections – Guidance Note</a> | ! Mandated under NR/L2/ENV/015, Section 6.11 ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [{D13¦A28}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>3 | Phase 1--2 | Designer | FALSE | AND(OR(D13="Yes",A28="Yes"),VLOOKUP(P2,tblProjectValues,2,False)>3) | AND(OR(""="Yes",""="Yes"),VLOOKUP("Select from drop down list…",tblProjectValues,2,False)>3) | D13 = "" Is the project area within or near a fluvial, coastal (i.e. Flood Zone 3) and/or surface water high flood risk area? A28 = "" Does the project include new or existing railway assets (including earthworks) vulnerable to higher temperature (e.g. rail buckling, signalling failure), heavier rainfall (e.g. land slip, power cut due to flooding) and/or more extreme coastal events (e.g. erosion, sea level rise)?
[5 empty] | T100 | Weather Resilience & Climate Change Adaptation (WRCCA) |  | Commission Flood Risk Assessment | Integrate findings and recommendations from Flood Risk Assessment into Option Selection/Outline Design/Detailed Design/Construction including avoidance and/or control measures within Design & Construction ESMP |  | {D13}="Yes" | Phase 1-2 | Designer | FALSE | D13="Yes" | ""="Yes" | D13 = "" Is the project area within or near a fluvial, coastal (i.e. Flood Zone 3) and/or surface water high flood risk area?
[5 empty] | T102 | Weather Resilience & Climate Change Adaptation (WRCCA) |  | Update Land & Consents Strategy and associated Commitments to consider flood risk permit, land drainage consent and/or marine licence and/or Code of Practice for Works Affecting the Canal & River Trust. | <a href="https://canalrivertrust.org.uk/business-and-trade/undertaking-works-on-our-property-and-our-code-of-practice"></a> |  | {D9¦D13}="Yes" | Phase 2-3 | Client | FALSE | OR(D9="Yes",D13="Yes") | OR(""="Yes",""="Yes") | D9 = "" Is the project area within 10m of a sea, estuary, watercourse (main river or ordinary watercourse such as open drainage, brook, etc.) or other surface water body (pond, canal, lake, loch, reservoir, etc.)? D13 = "" Is the project area within or near a fluvial, coastal (i.e. Flood Zone 3) and/or surface water high flood risk area?
[5 empty] | T103 | Weather Resilience & Climate Change Adaptation (WRCCA) |  | Integrate Sustainable Drainage Systems (SuDS) principles and climate change predictions into drainage design | <a href="https://www.susdrain.org/"></a> |  | [{S8}="Yes"¦¦{S8}="Maybe"]¦¦[{A27}="Yes"] | Phase 2-3 | Designer | FALSE | OR(OR(S8="Yes",S8="Maybe"),A27="Yes") | OR(OR(""="Yes",""="Maybe"),""="Yes") | S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) S8 = "" The project involves modifying, replacing and/or installing new drainage asset (e.g. track drainage, culvert, etc.) A27 = "" Will the project increase the area requiring surface water drainage (e.g. car park, roof, new track, new sidings, feeder station containment, etc.)?
[5 empty] | T104 | Water |  | Update Land & Consents Strategy and associated Commitments to consider abstraction or impoundment licence |  |  | {A25}="Yes" | Phase 2-3 | Client | FALSE | A25="Yes" | ""="Yes" | A25 = "" Will the project require water abstraction (from surface water or groundwater) during construction and/or operation?
[5 empty] | T105 | Water |  | Integrate water-efficient solutions into design |  |  | {A24}="Yes" | Phase 2-3 | Designer | FALSE | A24="Yes" | ""="Yes" | A24 = "" Will the project increase water consumption during operation?
[5 empty] | T107 | Sustainable Travel |  | Integrate multi-modal transport connections into Business Case (EV charging points, bike racks, etc.) |  |  | {A29}="Yes" | Phase 1 | Client | FALSE | A29="Yes" | ""="Yes" | A29 = "" Will the project offer an interface with other modes of transport (e.g. at station, depot, etc.) during operation?
[5 empty] | T108 | Sustainable Travel |  | Liaise with Local Authority, local transport companies and local transport action groups (including cycling) for better transport integration as part of Stakeholders Engagement Plan |  |  | {A29}="Yes" | Phase 1 | Client | FALSE | A29="Yes" | ""="Yes" | A29 = "" Will the project offer an interface with other modes of transport (e.g. at station, depot, etc.) during operation?
[5 empty] | T109 | Sustainable Travel |  | Develop Green Travel Plan for the workforce (e.g. park & ride, car sharing platform, etc.) to minimise carbon emissions, air pollution and nuisance to the local community (traffic, road noise, etc.) |  |  | {A30}="Yes" | Phase 3 | Principal Contractor | FALSE | A30="Yes" | ""="Yes" | A30 = "" Will the project involve a large workforce (>50) that will be travelling to a single location for a long period of time (>6 months) during construction?
[5 empty] | T111 | Being a caring neighbour |  | Liaise with Maintenance Protection Coordinator and Communications Manager for obtaining local knowledge on Network Rail relationship with local stakeholders (including Member of Parliament) and inclusion into Stakeholder Engagement Plan | <a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/social-performance/caring-neighbour/" target=_"blank">Being a caring neighbour</a> (Safety Central) |  | {D17¦D17.1¦D23}="Yes" | Phase 1 | Client | FALSE | OR(D17="Yes",D17.1="Yes",D23="Yes") | OR(""="Yes",""="Yes",""="Yes") | D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value D17.1 = "" If No, within 250m? D23 = "" Is the project area located where a large number of complaints (>10) has been received over the past 2 years? Username: NR.user Password: NRUser2019#
[5 empty] | T112 | Being a caring neighbour |  | Include sensitive/vulnerable receptors into Stakeholders Engagement Plan |  |  | {D18}="Yes" | Phase 1 | Client | FALSE | D18="Yes" | ""="Yes" | D18 = "" Are there sensitive/vulnerable receptors (e.g. hospital, care home) near (<200m) the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value
[5 empty] | T113 | Being a caring neighbour |  | Assess visual impact of planned asset/structure on nearby residents |  |  | [[{S12}="Yes"¦¦{S12}="Maybe"]¦¦{A31}="Yes"]&&[{D17}="Yes"] | Phase 2 | Designer | FALSE | AND(OR(OR(S12="Yes",S12="Maybe"),A31="Yes"),D17="Yes") | AND(OR(OR(""="Yes",""="Maybe"),""="Yes"),""="Yes") | S12 = "" The project involves replacing or installing new OLE S12 = "" The project involves replacing or installing new OLE D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value
[5 empty] | T114 | Being a caring neighbour |  | Notify the public in advance of planned noisy works and/or vegetation management activities (e.g. letter drop, drop-in event, etc.) | <a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/social-performance/caring-neighbour/notification/" target-_"blank">Notifying our neighbours</a> (Safety Central) |  | [{A8¦S1}="Yes"]&&[{D17¦D17.1}="Yes"] | Phase 2 | Client / Principal Contractor | FALSE | AND(OR(A8="Yes",S1="Yes"),OR(D17="Yes",D17.1="Yes")) | AND(OR(""="Yes",""="Yes"),OR(""="Yes",""="Yes")) | A8 = "" Will the project contribute to an increase local noise & vibration levels during construction (excavation/demolition works, tamping, piling, cutting, drilling, etc.)? S1 = "" The project involves vegetation management and/or land take. D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value D17.1 = "" If No, within 250m?
[5 empty] | T116 | Connecting communities with the environment |  | Engage with local communities through nature conservation initiatives (e.g. creating bug hotels with local school, building planters on platform with the Friends of the station, supporting local nature conservation group with volunteering or donations, etc.) | <a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/social-performance/connecting-communities-with-the-environment/" target=_"blank">Connecting communities with the environment</a> (Safety Central) |  | [{A1¦A35}="Yes"]¦¦[{S1}="Yes"&&{A34¦D19¦D17}="Yes"]¦¦[{S1}="Maybe"&&{A34¦D19¦D17}="Yes"] | Phase 2-3 | Designer/Principal Contractor | FALSE | OR(OR(A1="Yes",A35="Yes"),OR(AND(S1="Yes",OR(A34="Yes",D19="Yes",D17="Yes")),AND(S1="Maybe",OR(A34="Yes",D19="Yes",D17="Yes")))) | OR(OR(""="Yes",""="Yes"),OR(AND(""="Yes",OR(""="Yes",""="Yes",""="Yes")),AND(""="Maybe",OR(""="Yes",""="Yes",""="Yes")))) | A1 = "" Will vegetation management and/or land take impact an area >1,500m2? A35 = "" Will land take impact third party land? S1 = "" The project involves vegetation management and/or land take. A34 = "" Will the project affect the station and/or platform environment? D19 = "" Are there schools and/or universities within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value S1 = "" The project involves vegetation management and/or land take. A34 = "" Will the project affect the station and/or platform environment? D19 = "" Are there schools and/or universities within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value
[5 empty] | T164 | Connecting communities with the environment |  | Consider the design impact of visually prominent structures |  |  | {A40}="Yes" |  |  | FALSE | A40="Yes" | ""="Yes" | A40 = "" Will visually prominent structures be erected in the project area?
[5 empty] | T149 | Making rail a great experience |  | Integrate Network Rail Principles of Good Design into project development, supported by the local Design Champion nominated by Technical Authority (Buildings & Architecture) | <a href="https://networkrail.sharepoint.com/sites/myconnect/ste/Documents/Our Principles of Good Design_LowRes.pdf" target=_"blank">Network Rail Principles of Good Design</a> (Buildings & Architecture) <br> <br>Contact Technical Authority Head of Buildings & Architecture to identify your local champion. <br> <br><a href="https://safety.networkrail.co.uk/wp-content/uploads/2018/01/Social-value-and-design-of-the-built-environment.pdf" target=_"blank">Social Value and Design of the Built Environment</a> |  | {A34}="Yes" | Phase 1 - 2 | Client | FALSE | A34="Yes" | ""="Yes" | A34 = "" Will the project affect the station and/or platform environment?
[5 empty] | T117 | Making rail a great experience |  | Liaise with station management (TOC or NR) and local users group as part of Stakeholders Engagement Plan |  |  | {A34}="Yes" | Phase 2-3 | Client | FALSE | A34="Yes" | ""="Yes" | A34 = "" Will the project affect the station and/or platform environment?
[5 empty] | T118 | Making rail a great experience |  | Engage with Community Rail Partnership/Station adoption group as part of Stakeholders Engagement Plan when modifying platforms or stations |  |  | {A34&D17}="Yes" | Phase 2-3 | Client | FALSE | AND(A34="Yes",D17="Yes") | AND(""="Yes",""="Yes") | A34 = "" Will the project affect the station and/or platform environment? D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value
[5 empty] | T119 | Making rail a great experience |  | Support Community Rail Partnership/Station adoption group through volunteering | <a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/social-performance/making-rail-a-great-experience/" target=_"blank">Making Rail a Great Experience</a> (Safety Central) |  | {D17}="Yes" | Phase 3 | Client / Principal Contractor | FALSE | D17="Yes" | ""="Yes" | D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value
[5 empty] | T120 | Creating engaged employees and positive industry partnerships |  | Undertake Social Value Workshop based on the Common Social Industry Framework (CSIF) | <a href="https://safety.networkrail.co.uk/wp-content/uploads/2019/02/T1127-Common_Social_Impact_Framework_for_Rail-Tools-techniques.xlsx" target=_"blank">Common Social Impact Framework</a> |  | [{D16¦D19¦D20¦D21¦D22¦D17¦D26}="Yes"]&&[{P2}=">£50m"] | Phase 2-3 | Client | FALSE | AND(OR(D16="Yes",D19="Yes",D20="Yes",D21="Yes",D22="Yes",D17="Yes",D26="Yes"),P2=">£50m") | AND(OR(""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes"),"Select from drop down list…"=">£50m") | D16 = "" Is there a heritage railway near (<10km) the project area? D19 = "" Are there schools and/or universities within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value D20 = "" Is there employment a correctional facility or rehabilitation centre within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value D21 = "" Is there a homelessness service or centre within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value D22 = "" Is there a place of worship (e.g. church, mosque, temple, etc.) within 1km of the project area? Note: Please see the Social Value Framework for opportunities around social value D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value D26 = "" Does the project area include neighbourhood(s) affected by social deprivation (i.e. amongst the 10% most deprived neighbourhoods in the country)? P2 = "Select from drop down list…" Estimated Project Value (Development, Design and Construction)
[5 empty] | T121 | Creating engaged employees and positive industry partnerships |  | Build partnerships with local parish/community/town council, local charities and/or local schools through volunteering and community engagement activities (e.g. STEM) in collaboration with industry partners (e.g. TOC, NR suppliers, NR business units) as part of Stakeholders Engagement Plan | <a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/social-performance/creating-positive-industry-partnerships/" target=_"blank">Creating Positive Industry Partnerships</a> (Safety Central) |  | [{D16¦D19¦D20¦D21¦D22¦D17¦D26}="Yes"]&&[{P2}=">£50m"] | Phase 2--3 | Client | FALSE | AND(OR(D16="Yes",D19="Yes",D20="Yes",D21="Yes",D22="Yes",D17="Yes",D26="Yes"),P2=">£50m") | AND(OR(""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes"),"Select from drop down list…"=">£50m") | D16 = "" Is there a heritage railway near (<10km) the project area? D19 = "" Are there schools and/or universities within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value D20 = "" Is there employment a correctional facility or rehabilitation centre within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value D21 = "" Is there a homelessness service or centre within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value D22 = "" Is there a place of worship (e.g. church, mosque, temple, etc.) within 1km of the project area? Note: Please see the Social Value Framework for opportunities around social value D17 = "" Are there residential properties, business premises or community rail activities within 200m of the project area? Or for noisier works, within 500m? Note: Please see the Social Value Framework for opportunities around social value D26 = "" Does the project area include neighbourhood(s) affected by social deprivation (i.e. amongst the 10% most deprived neighbourhoods in the country)? P2 = "Select from drop down list…" Estimated Project Value (Development, Design and Construction)
[5 empty] | T122 | Inspiring tomorrow’s workforce |  | Stakeholder Engagement Plan to include promoting careers in the rail industry through schools visits, careers fairs, work placements and/or apprenticeships | <a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/social-performance/inspiring-tomorrows-workforce/" target=_"blank">Inspiring Tomorrow's Workforce</a> (Safety Central) |  | {D19}="Yes" | Phase 2--3 | Client | FALSE | D19="Yes" | ""="Yes" | D19 = "" Are there schools and/or universities within 20 miles of the project area? Note: Please see the Social Value Framework for opportunities around social value
[5 empty] | T165 | Inspiring tomorrow’s workforce |  | Document the requirements and any associated plans/controls |  |  | {A45}="Yes" |  |  | FALSE | A45="Yes" | ""="Yes" | A45 = "" Does the project have any section 106 requirements set by a planning authority?
[5 empty] | T166 | Inspiring tomorrow’s workforce |  | Consider providing safety messaging and early engagement (e.g. STEM, careers talks) interventions |  |  | {A41}="Yes" |  |  | FALSE | A41="Yes" | ""="Yes" | A41 = "" Are there any schools within 200m of the project area?
[5 empty] | T147 | Keeping Communities safe |  | Liaise with Community Safety Manager (for Route Insight Assessment) and the Suicide Prevention Programme (for Priority Areas) to gather local knowledge | SuicidePreventionProgramme@networkrail.co.uk |  | {D25¦S12¦S17¦S18}="Yes"¦¦{S12¦S17¦S18}="Maybe" | Phase 102 | Client | FALSE | OR(OR(D25="Yes",S12="Yes",S17="Yes",S18="Yes"),OR(S12="Maybe",S17="Maybe",S18="Maybe")) | OR(OR(""="Yes",""="Yes",""="Yes",""="Yes"),OR(""="Maybe",""="Maybe",""="Maybe")) | D25 = "" Is the project area affected by route crime (e.g. trespass) or suicide (i.e. Amber or Red Status)? Note: Use the Route Crime Excel Register S12 = "" The project involves replacing or installing new OLE S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing S12 = "" The project involves replacing or installing new OLE S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing
[5 empty] | T148 | Keeping Communities safe |  | Liaise with Level Crossing Manager to gather local knowledge |  |  | {S17¦S18}="Yes" | Phase 1-2 | Client | FALSE | OR(S17="Yes",S18="Yes") | OR(""="Yes",""="Yes") | S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing
[5 empty] | T123 | Keeping Communities safe |  | Minimise risk of trespass by design |  |  | [{D25}="Yes"]¦¦[{S12¦S17¦S18}="Yes"¦¦{S12¦S17¦S18}="Maybe"] | Phase 2 | Designer | FALSE | OR(D25="Yes",OR(OR(S12="Yes",S17="Yes",S18="Yes"),OR(S12="Maybe",S17="Maybe",S18="Maybe"))) | OR(""="Yes",OR(OR(""="Yes",""="Yes",""="Yes"),OR(""="Maybe",""="Maybe",""="Maybe"))) | D25 = "" Is the project area affected by route crime (e.g. trespass) or suicide (i.e. Amber or Red Status)? Note: Use the Route Crime Excel Register S12 = "" The project involves replacing or installing new OLE S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing S12 = "" The project involves replacing or installing new OLE S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing
[5 empty] | T124 | Keeping Communities safe |  | Launch Community Safety campaign | <a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/social-performance/keeping-communities-safe/" target=_"blank"> Keeping Communities Safe</a> (Safety Central) |  | [{D25}="Yes"]¦¦[{S12¦S17¦S18}="Yes"¦¦{S12¦S17¦S18}="Maybe"] | Phase 2--3 | Client | FALSE | OR(D25="Yes",OR(OR(S12="Yes",S17="Yes",S18="Yes"),OR(S12="Maybe",S17="Maybe",S18="Maybe"))) | OR(""="Yes",OR(OR(""="Yes",""="Yes",""="Yes"),OR(""="Maybe",""="Maybe",""="Maybe"))) | D25 = "" Is the project area affected by route crime (e.g. trespass) or suicide (i.e. Amber or Red Status)? Note: Use the Route Crime Excel Register S12 = "" The project involves replacing or installing new OLE S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing S12 = "" The project involves replacing or installing new OLE S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing
[5 empty] | T125 | Making travel accessible and inclusive |  | Undertake and update Diversity Impact Assessment (DIA) at each PACE stage and take actions to mitigate negative impacts | <a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/social-performance/making-travel-accessible/" target=_"blank">Making Travel Accessible</a> (Safety Central) | ! Mandated as a PACE Product ! ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [{S5¦S17¦S18¦A32¦A33¦A42}="Yes"¦¦{A42}="Don't Know"] | Phase 1-4 | Client | FALSE | OR(OR(S5="Yes",S17="Yes",S18="Yes",A32="Yes",A33="Yes",A42="Yes"),A42="Don't Know") | OR(OR(""="Yes",""="Yes",""="Yes",""="Yes",""="Yes",""="Yes"),""="Don't Know") | S5 = "" The project involves modifying, replacing and/or installing new building (e.g. office, station, depot). S17 = "" The project involves renewing and/or modifying a Level Crossing S18 = "" The project involves closing a Level Crossing A32 = "" Will the project involve changing the permanent or temporary access to buildings, stations or bridges? A33 = "" Could public access (including footpath, cycle path, rights of way, level crossing) require temporary closure and/or diversion during project delivery? A42 = "" Will the project impact people (e.g. passengers, employees, or lineside neighbours), including temporary works, temporary conditions, and staging works? A42 = "" Will the project impact people (e.g. passengers, employees, or lineside neighbours), including temporary works, temporary conditions, and staging works?
[5 empty] | T126 | Respecting cultural heritage and rail history |  | Minimise impact on cultural heritage by design |  |  | {D15.1¦D15.2¦D15.3¦D15.4}="Yes" | Phase 2 | Designer | FALSE | OR(D15.1="Yes",D15.2="Yes",D15.3="Yes",D15.4="Yes") | OR(""="Yes",""="Yes",""="Yes",""="Yes") | D15.1 = "" Grade I and II Listed buildings D15.2 = "" Scheduled ancient monuments D15.3 = "" Conservation areas D15.4 = "" World heritage sites
[5 empty] | T127 | Respecting cultural heritage and rail history |  | Update Land & Consents Strategy and associated Commitments to consider Cultural Heritage Impact Assessment and consultation with Local Authority |  | ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | {D15.1¦D15.2¦D15.3¦D15.4}="Yes" | Phase 2 | Client | FALSE | OR(D15.1="Yes",D15.2="Yes",D15.3="Yes",D15.4="Yes") | OR(""="Yes",""="Yes",""="Yes",""="Yes") | D15.1 = "" Grade I and II Listed buildings D15.2 = "" Scheduled ancient monuments D15.3 = "" Conservation areas D15.4 = "" World heritage sites
[5 empty] | T128 | Respecting cultural heritage and rail history |  | Undertake Landscape & Visual Impact Assessment (AONB or National Park) | Integrate findings and recommendations from Landscape & Visual Impact Assessment into Option Selection/Outline Design/Detailed Design/Construction | ! This action can only be scoped out after consultation with the project Environment & Sustainability Representative ! | [[{S12}="Yes"¦¦{S12}="Maybe"]¦¦{A31}="Yes"]&&[{D4.5¦D4.6}="Yes"] | Phase 2 | Client / Designer | FALSE | AND(OR(OR(S12="Yes",S12="Maybe"),A31="Yes"),OR(D4.5="Yes",D4.6="Yes")) | AND(OR(OR(""="Yes",""="Maybe"),""="Yes"),OR(""="Yes",""="Yes")) | S12 = "" The project involves replacing or installing new OLE S12 = "" The project involves replacing or installing new OLE D4.5 = "" Area of Outstanding Natural Beauty (AONB) D4.6 = "" National Park
[5 empty] | T129 | Respecting cultural heritage and rail history |  | Contribute to local heritage railway through volunteering, by providing technical support (e.g. design, project management, etc.) and/or offering the opportunity to bid for redundant assets. | <a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/social-performance/respecting-cultural-history-and-rail-heritage/" target=_"blank">Respecting Cultural History & Rail Heritage</a> (Safety Central) |  | {D16}="Yes" | Phase 3 | Client / Principal Contractor | FALSE | D16="Yes" | ""="Yes" | D16 = "" Is there a heritage railway near (<10km) the project area?
[5 empty] | T167 | Respecting cultural heritage and rail history |  | Undertake a heritage assessment |  |  | {D27}="Yes" |  |  | FALSE | D27="Yes" | ""="Yes" | D27 = "" Will the project area include scheduled monuments, archaeological sites and deposits, or buildings of historical and architectural interest?
[5 empty] | T130 | Supporting Britain’s economic development |  | Consider socio-economic landscape into Project Business Case development and Stakeholders Engagement Plan | <a href="https://safety.networkrail.co.uk/home-2/environment-and-sustainable-development/social-performance/supporting-britains-development/" target=_"blank">Supporting Britain's Development</a> (Safety Central) |  | {D26}="Yes" | Phase 1 | Client | FALSE | D26="Yes" | ""="Yes" | D26 = "" Does the project area include neighbourhood(s) affected by social deprivation (i.e. amongst the 10% most deprived neighbourhoods in the country)?
[5 empty] | T131 | Supporting Britain’s economic development |  | Recruit workforce locally where possible |  |  | [{A30¦D26}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>=4 | Phase 3 | Principal Contractor | FALSE | AND(OR(A30="Yes",D26="Yes"),VLOOKUP(P2,tblProjectValues,2,False)>=4) | AND(OR(""="Yes",""="Yes"),VLOOKUP("Select from drop down list…",tblProjectValues,2,False)>=4) | A30 = "" Will the project involve a large workforce (>50) that will be travelling to a single location for a long period of time (>6 months) during construction? D26 = "" Does the project area include neighbourhood(s) affected by social deprivation (i.e. amongst the 10% most deprived neighbourhoods in the country)?
[5 empty] | T132 | Supporting Britain’s economic development |  | Procure goods, materials and services locally and/or from SMEs where possible |  |  | [{A17¦D26}="Yes"]&&VLOOKUP({P2},tblProjectValues,2,False)>=4 | Phase 3 | Principal Contractor | FALSE | AND(OR(A17="Yes",D26="Yes"),VLOOKUP(P2,tblProjectValues,2,False)>=4) | AND(OR(""="Yes",""="Yes"),VLOOKUP("Select from drop down list…",tblProjectValues,2,False)>=4) | A17 = "" Will construction require significant quantities of concrete and/or steel (>100t), including track material? D26 = "" Does the project area include neighbourhood(s) affected by social deprivation (i.e. amongst the 10% most deprived neighbourhoods in the country)?
[5 empty] | T169 | Supporting Britain’s economic development |  | Consider opportunities to utilise NR procurement processes that support SMEs, local, VCSE business groups, and/or local communities. |  |  | {D29}="Yes"¦¦{D29}="Don't Know" | Phase 3 |  | FALSE | OR(D29="Yes",D29="Don't Know") | OR(""="Yes",""="Don't Know") | D29 = "" Are there opportunities available to (i) share contract opportunities with SME, local and/or VCSE business groups (ii) job opportunities with local communities? D29 = "" Are there opportunities available to (i) share contract opportunities with SME, local and/or VCSE business groups (ii) job opportunities with local communities?
[5 empty] | T133 | OTM Design / Build / Refurbishment |  | Undertake Resource Efficiency Workshop taking into consideration the whole life of the asset including construction, maintenance, repairs and decommissioning |  |  | {S21}="Yes" | Phase 1-2 | Supplier | FALSE | S21="Yes" | ""="Yes" | S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons).
[5 empty] | T134 | OTM Design / Build / Refurbishment |  | Integrate findings and recommendations from circular economy workshop into Business Case/Option Selection/Outline Design/Detailed Design/Construction e.g. reusability and recyclability of parts and components across a range of OTMs |  |  | {S21}="Yes" | Phase 1-2 | Client / Supplier | FALSE | S21="Yes" | ""="Yes" | S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons).
[5 empty] | T135 | OTM Design / Build / Refurbishment |  | Undertake Whole Life Carbon Assessment using the Rail Carbon Tool |  |  | {S21}="Yes" | Phase 1-2 | Supplier | FALSE | S21="Yes" | ""="Yes" | S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons).
[5 empty] | T136 | OTM Design / Build / Refurbishment |  | Integrate findings and recommendations from capital carbon assessment into Business Case/Option Selection/Outline Design/Detailed Design/Construction e.g. alternative low carbon materials, materials with high recycled content, LEAN design, etc. |  |  | {S21}="Yes" | Phase 2-3 | Client / Supplier | FALSE | S21="Yes" | ""="Yes" | S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons).
[5 empty] | T137 | OTM Design / Build / Refurbishment |  | Undertake 'in-use' Operational Energy assessment |  |  | {A36}="Yes" | Phase 2 | Supplier | FALSE | A36="Yes" | ""="Yes" | A36 = "" Is the OTM powered by fossil fuels (includes primary engine power source as well as auxiliary power e.g. onboard generators)?
[5 empty] | T138 | OTM Design / Build / Refurbishment |  | Integrate findings and recommendations from 'in-use' operational energy assessment into Business Case/Option Selection/Outline Design/Detailed Design/Construction e.g. alternative renewable power sources, 'best in class' diesel engine technology, energy efficiency solutions such as reduced weight and improved aerodynamics, etc. |  |  | {A36}="Yes" | Phase 2 | Client / Supplier | FALSE | A36="Yes" | ""="Yes" | A36 = "" Is the OTM powered by fossil fuels (includes primary engine power source as well as auxiliary power e.g. onboard generators)?
[5 empty] | T139 | OTM Design / Build / Refurbishment |  | Design for high reliability to prevent pollution incidents with a focus on hydraulic and fuels lines |  |  | {S21}="Yes" | Phase 2 | Supplier | FALSE | S21="Yes" | ""="Yes" | S21 = "" The project involves design and/or build or refurbishment of locomotives or on track machines and other track engineering assets (e.g. rail wagons).
[5 empty] | T140 | OTM Design / Build / Refurbishment |  | Investigate alternatives to hydrocarbon-based hydraulic or lubricating systems (e.g. compressed air) |  |  | {A37}="Yes" | Phase 2 | Supplier | FALSE | A37="Yes" | ""="Yes" | A37 = "" Does the OTM require hydrocarbon based lubricants to operate?
[5 empty] | T141 | OTM Design / Build / Refurbishment |  | Develop Decommissioning plan in accordance with the waste hierarchy |  |  | {S22}="Yes" | Phase 2 | Supplier | FALSE | S22="Yes" | ""="Yes" | S22 = "" As part of the response to the relevant invitation to tender, did the Designer/Contractor make environmental and or social commitments?
[5 empty] | T142 | OTM Design / Build / Refurbishment |  | Undertake Water Efficiency assessment |  |  | {A38}="Yes" | Phase 2 | Supplier | FALSE | A38="Yes" | ""="Yes" | A38 = "" Does the OTM use large quantities of water as part of its operational activities (e.g. water to treat the track bed or onboard dust suppression), excluding engine cooling?
[5 empty] | T143 | OTM Design / Build / Refurbishment |  | Integrate findings and recommendations from water efficiency assessment into Business Case/Option Selection/Outline Design/Detailed Design/Construction e.g. alternative waterless solutions, water reuse, water-efficient technologies, etc. |  |  | {A38}="Yes" | Phase 2 | Client / Supplier | FALSE | A38="Yes" | ""="Yes" | A38 = "" Does the OTM use large quantities of water as part of its operational activities (e.g. water to treat the track bed or onboard dust suppression), excluding engine cooling?
[5 empty] | T144 | OTM Design / Build / Refurbishment |  | Undertake Operational Noise assessment |  |  | {A39}="Yes" | Phase 2 | Supplier | FALSE | A39="Yes" | ""="Yes" | A39 = "" Is the OTM likely to be operated near lineside neighbours?
[5 empty] | T145 | OTM Design / Build / Refurbishment |  | Integrate findings and recommendations from operational noise assessment into Business Case/Option Selection/Outline Design/Detailed Design/Construction e.g. start-stop technology to present idling, acoustic containment, etc. |  |  | {A39}="Yes" | Phase 1-2 | Client / Supplier | FALSE | A39="Yes" | ""="Yes" | A39 = "" Is the OTM likely to be operated near lineside neighbours?
Validate Logic
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed A26 as it has been deleted.
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed A26 as it has been deleted.
Note on D22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ¦A22 deleted as question has been removed
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed ¦A26 as the question has been removed.
Note on D24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ¦D14 removed as question has been removed

## DROP DOWNS (hidden)
Drop down tables for tool
PROJECT INFO |  | FRAMEWORK HIDDEN TAB | FRAMEWORK HIDDEN TAB | PROJECT INFO | VARIOUS | PROJECT INFO | PROJECT INFO
Value | Code | ESR Type | Question_type | Client Org | PACE Stages | Level of Control | Regions and Routes | lstYesNo | Status
Select from drop down list… | 0 | Env | Choice | Select from drop down list… | Select from drop down list... | Select from drop down list... | Select from drop down list... | Yes | Open
Up to £20k | 1 | Soc | Heading | Capital Delivery | ES1 | 1 | Eastern - Anglia Route | No | Closed
£20k-£250k | 2 | N/A | Double Click | Route Services | ES2 | 2 | Eastern - East Midlands Route |  | N/A
£250k-£1m | 3 |  | Locked Choice | Route Businesses (e.g. RAM) | ES3 | 3 | Eastern - North and East Route
£1m-£5m | 4 |  | Free Text | System Operator | ES4 | 4 | Eastern - East Coast Route
£5m-£20m | 5 |  |  | External funder (e.g. ASPRO schemes) | ES5 |  | North West and Central - North West Route
£20m-£50m | 6 |  |  | Other | ES6 |  | North West and Central - Central Route
>£50m | 7 |  |  |  | ES7 |  | North West and Central - West Coast Mainline South Route
[5 empty] | ES8 |  | Scotland's Railway - Scotland Route
Southern - Kent Route
Southern - Sussex Route
Southern - Wessex Route
Southern - Network Rail High Speed
Wales & Western - Wales Route
Wales & Western - Western Route